## Read Me
TowerScout Comprehensive Backlog and Next Steps
As of October 1, 2026. The current board and ADRs control status; historical unchecked boxes are retained separately and do not automatically reopen completed work.
Category | Topic | Explanation
Purpose | Deliverable | Comprehensive inventory of currently open, conditional, owner-gated, and deliberately deferred work through project closeout.
Scope | Documents reviewed | All Markdown under .agent_work/tasks plus Handoff-Planning and Reprioritization Effort status folders; current board/backlog/requirements/design control interpretation.
As of | Review date | 2026-10-01
Decision | Unsigned package | ADR-023 is accepted. Signing is not a standard release gate; browser-download/hash/ordinary-user proof remains.
Important | rc4 package status | rc4 remains valid historical local runtime evidence but is not the final distribution package because shipped manuals changed.
Count | Curated action rows | 71
Count | Rows identified as release/handoff gates | 61
Count | Raw unchecked checklist items retained for traceability | 711
Count | Documentation sources registered | 122
How to use | Open Actions | Filter Recommendation, Priority, Planned week, or Task/source. This is the decision-ready backlog.
How to use | Raw Unchecked Items | This sheet prevents old unchecked boxes from disappearing. Many are historical and must not be treated as active work.
Interpretation | Completed-folder files | Historical task bodies may contain stale IN_PROGRESS labels or unchecked test plans. Current board/backlog authority wins.
Recommendation count | Work now | 2
Recommendation count | Deferred / not scheduled | 12
Authorization | External actions | Publication, cdcai mutation, account changes, and signing remain owner-controlled even when listed as plan steps.

## Open Actions
Comprehensive Open Actions
Curated current, conditional, owner-gated, and deferred work. Filter by recommendation and planned week; deferred rows are documented so they are not accidentally pulled into October.
Action ID | Workstream | Action | Plain-language summary | Current status | Priority | Recommendation | Release / handoff gate | Task or source | Created / first recorded | Why it is still open | Estimated effort | Expected outcome | Blockers / dependencies | Target date | Owner / role | Done when | Risk if skipped | Planned week | Estimate confidence | Primary source reference
R01 | Release package | Approve the updated packaged manuals | Review and accept the unsigned-package wording as the content that will ship. | In progress | Critical | Work now | Required before package freeze | TASK-092 / ADR-023 | 2026-10-01 | ADR-023 changed files that are included in the ZIP. | S: 0.25-0.5 day | One approved set of package manuals. | Documentation owner review. | 2026-10-02 | Documentation owner / release owner | No conflicting wording remains and the owner accepts the shipped text. | A later wording change creates new bytes and forces more reruns. | Opening days: Oct 1-2 | High | .agent_work/tasks/active/TASK-092-documentation-currentness.md
R02 | Release package | Choose the replacement control-package identity | Name the new CPU and CUDA control ZIPs and bind them to accepted source, exact image digests, and the asset ZIP. | Open | Critical | Work now | Required before package build | TASK-103 / W09 | 2026-09-21 plan; updated 2026-10-01 | The existing rc4 ZIPs contain older manuals. | S: 0.25 day | A unique, traceable candidate identity. | R01; accepted main; confirmed image and asset identities. | 2026-10-02 | Release owner | The release manifest and planned filenames agree on one new identity. | Old and new evidence could be mixed or mislabeled. | Opening days: Oct 1-2 | High | .agent_work/tasks/active/TASK-103/W09-EVIDENCE-INDEX.md
R03 | Release package | Build replacement CPU and CUDA control ZIPs | Repackage the accepted manuals without renaming or modifying an old ZIP. | Blocked by R01-R02 | Critical | Work now | Required before testing | TASK-103 | 2026-09-21 plan; updated 2026-10-01 | The package bytes changed after ADR-023. | M: 0.5-1 day | Two checksum-verifiable control ZIPs with current manuals. | Clean source; exact identities; package tooling. | 2026-10-05 | Release implementer | Both ZIPs and sidecars are produced from the clean accepted source. | The current rc4 ZIPs cannot be final distribution artifacts. | Week 1: Oct 5-9 | High | .agent_work/tasks/active/TASK-103-cuda128-blackwell-ml-runtime.md
R04 | Release package | Inspect package integrity and secret hygiene | Verify sidecars, internal checksums, manifests, allowlists, notices, scripts, and manuals; reject secrets and unexpected files. | Open | Critical | Work now | Required before tester distribution | W09 / TASK-103 | 2026-09-21 plan; updated 2026-10-01 | The new ZIP identity has not been inspected. | M: 0.5 day | Auditable evidence that the ZIP contains exactly the intended files. | R03. | 2026-10-06 | Release implementer / reviewer | All package checks pass and sanitized evidence records the result. | A malformed or sensitive package could be distributed. | Week 1: Oct 5-9 | High | .agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md
R05 | Release package | Repeat affected local package checks | Run setup, start, status, logs, stop, fresh-shell relaunch, device, and volume checks for Docker/Podman CPU/GPU as affected by the new ZIPs. | Open | Critical | Work now | Required before freeze | TASK-091 / TASK-103 | 2026-09-21 plan; updated 2026-10-01 | The previous local runtime evidence used rc4 package bytes. | L: 1-2 days | Local proof tied to the replacement ZIP hashes. | R03-R04; Docker and Podman availability. | 2026-10-07 | Release implementer | Affected W09/W10 cells reference the replacement ZIP hashes and pass. | Untested replacement bytes could hide packaging regressions. | Week 1: Oct 5-9 | Medium | .agent_work/tasks/active/TASK-091-owner-runnable-release-qualification.md
R06 | Release package | Record authoritative SHA-256 values | Put exact control and asset ZIP hashes in the owner-approved release record used by testers. | Open / owner-controlled | Critical | Work now | Required before extraction testing | ADR-023 / W09 | 2026-10-01 | The replacement ZIPs do not yet exist. | S: 0.25 day | One trusted place for testers to compare hashes. | R03-R04; owner-approved publication or pre-release record. | 2026-10-08 | Release owner | Displayed hashes match the exact tester downloads. | A sidecar alone does not authenticate the publisher or download. | Week 1: Oct 5-9 | High | .agent_work/decisions/023-unsigned-windows-package-support-boundary.md
R07 | Release acceptance | Test a real browser download as an ordinary user | Download the exact ZIP, verify its official hash before extraction, preserve the Windows download marker, extract to a path with spaces, and use the supplied wrapper. | Blocked by R03 and R06 | Critical | Work now | Required before acceptance | TASK-091 / TASK-103 / ADR-023 | 2026-10-01 | This is the new acceptance proof created by the unsigned decision. | M: 0.5-1 day | Evidence that the supported unsigned path works without changing persistent policy. | Download location; authoritative hash; ordinary account. | 2026-10-09 | Independent tester or separate ordinary-user session | Hash, marker, extraction, wrapper, setup, and first-use results are recorded. | The central unsigned-package support claim would remain unproven. | Week 1: Oct 5-9 | Medium | .agent_work/decisions/023-unsigned-windows-package-support-boundary.md
R08 | Release acceptance | Reserve the independent Windows tester and host | Book the suitable computer, tester time, provider accounts, and runtime prerequisites before freeze. | Blocked / external | Critical | Work immediately | Required for full four-profile claim | TASK-091 / W10 | 2026-09-22 | No independent computer is confirmed in the current evidence. | S: 0.25 day coordination | A named tester, host inventory, and test window. | Owner/tester availability; NVIDIA, Docker, Podman, Python 3.12, provider access. | 2026-10-02 | Test owner / project lead | Anonymous host ID, capabilities, dates, and owners are recorded. | Independent testing could consume the entire acceptance week or become impossible. | Opening days: Oct 1-2 | Low | .agent_work/tasks/active/TASK-091-owner-runnable-release-qualification.md
R09 | Independent qualification | Repeat Docker CPU on the independent host | Follow only shipped instructions and run models, Google/Azure, review/export, cancel/error recovery, stop/relaunch, and persistence. | Blocked by R03 and R08 | Critical | Work after freeze | Required for full acceptance | TASK-091 / W10 | 2026-09-21 | Only first-host evidence exists. | M: 0.5-1 day | Independent Docker CPU pass tied to exact hashes. | Frozen package; assets; provider accounts; independent host. | 2026-10-13 | Independent tester | Every required Docker CPU cell has a pass or an explicit blocker. | The four-profile release claim remains incomplete. | Week 2: Oct 12-16 | Medium | .agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-prioritization-v2.md
R10 | Independent qualification | Repeat Docker GPU on the independent host | Prove both models use CUDA with no CPU fallback, then repeat the user workflow and recovery checks. | Blocked by R03 and R08 | Critical | Work after freeze | Required for full acceptance | TASK-091 / TASK-103 / W10 | 2026-09-21 | Only first-host CUDA evidence exists. | M: 0.5-1 day | Independent Docker GPU pass with actual CUDA evidence. | Compatible NVIDIA host/driver/VRAM; frozen package. | 2026-10-14 | Independent tester | Both models and a kernel run on CUDA and all workflow checks pass. | A readiness label or CPU fallback could be mistaken for GPU support. | Week 2: Oct 12-16 | Medium | .agent_work/tasks/active/TASK-103/W10-LOCAL-FIRST-HOST-EVIDENCE-INDEX.md
R11 | Independent qualification | Repeat Podman CPU on the independent host | Install/use the documented package-local Compose provider with supported Python, then run the full workflow. | Blocked by R03 and R08 | Critical | Work after freeze | Required for full acceptance | TASK-097 / W10 | 2026-09-22 | Only first-host Podman evidence exists. | M: 0.5-1 day | Docker-Desktop-free independent Podman CPU proof. | Podman machine/connection; Python 3.12; assets/providers. | 2026-10-14 | Independent tester | Podman target binding, CPU models, providers, exports, and recovery pass. | Podman support would remain a local-only result. | Week 2: Oct 12-16 | Medium | .agent_work/tasks/active/TASK-097-podman-final-path-qualification.md
R12 | Independent qualification | Repeat Podman GPU on the independent host | Prove the intended WSL2/NVIDIA CDI path and both models on CUDA, then run the complete workflow. | Blocked by R03 and R08 | Critical | Work after freeze | Required for full acceptance | TASK-097 / TASK-103 / W10 | 2026-09-22 | Only first-host Podman CUDA evidence exists. | L: 0.75-1.25 days | Independent Podman GPU proof with no Docker Desktop dependency. | NVIDIA/CDI/Podman prerequisites; frozen package. | 2026-10-15 | Independent tester | CDI, exact digest, CUDA models, providers, persistence, and exports pass. | The highest-risk advertised profile would remain unverified. | Week 2: Oct 12-16 | Low-Medium | .agent_work/tasks/active/TASK-097-podman-final-path-qualification.md
R13 | Independent qualification | Repeat recovery, reboot, and shared failure cases | Confirm eight volumes, provider/settings persistence, cancellation/error recovery, reboot behavior, wrong-target protection, and selected safe failure injections. | Blocked by R09-R12 | Critical | Work after profile runs | Required for acceptance | TASK-093 / W10 | 2026-09-23 | Recovery has passed only on the first host. | L: 0.75-1.5 days | Independent evidence that normal failures do not lose data or target the wrong installation. | Profile setup; permission to reboot; isolated test state. | 2026-10-16 | Independent tester / release implementer | All required recovery cells pass without destructive volume cleanup. | Data loss or a false recovery claim could reach end users. | Week 2: Oct 12-16 | Medium | .agent_work/tasks/active/TASK-093-persistent-data-recovery.md
R14 | Release acceptance | Perform the final evidence reconciliation | Check every profile, host, hash, digest, device, provider, skip, limitation, and redaction before making the release claim. | Open | Critical | Work after R09-R13 | Required for acceptance | TASK-091 / TASK-103 / W10 | 2026-09-21 | The final independent matrix does not yet exist. | M: 0.5 day | One accurate pass/fail/blocked matrix and evidence index. | All test results and final artifact identities. | 2026-10-16 | Release owner / independent reviewer | No missing or blocked cell is labeled pass; hashes and evidence references agree. | The project could overstate readiness or lose traceability. | Week 2: Oct 12-16 | High | .agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md
R15 | Release acceptance | Make the acceptance or qualified-subset decision | Approve the full four-profile candidate only if every required cell passes; otherwise name the exact supported subset and blockers. | Open / owner decision | Critical | Decision gate | October 16 milestone | TASK-091 / project requirements | 2026-07-23 roadmap | Independent acceptance has not finished. | S: 1-2 hours | A truthful, owner-approved acceptance result. | R14; owner availability. | 2026-10-16 | Project lead and release owner | Written sign-off identifies passes, limitations, residuals, and next actions. | Publication could outrun evidence. | Week 2: Oct 12-16 | High | .agent_work/requirements.md
D01 | Documentation | Finalize shipped documentation for the exact candidate | Insert final version, filenames, prerequisites, support limits, and tested behavior in Markdown and HTML before freeze. | In progress | High | Work now | Required before package freeze | TASK-092 | 2026-09-22 | The unsigned boundary is aligned, but final artifact-specific values do not yet exist. | M: 0.5-1 day | Shipped instructions match the exact package. | R02; observed package behavior. | 2026-10-07 | Documentation owner | Markdown/HTML pairs and package-local copies agree. | Instructions could describe different bytes than testers receive. | Week 1: Oct 5-9 | High | .agent_work/tasks/active/TASK-092-documentation-currentness.md
D02 | Documentation | Verify in-app Help, links, and packaged guide copies | Open the served Help pages, check navigation and repository links, and inspect the final ZIP/image for intended versions. | Open | High | Work before freeze and acceptance | Required before acceptance | TASK-092 / post-Day-7 guide | 2026-09-21 | Text updates alone do not prove the app serves or packages them. | M: 0.5 day | Users reach working, current instructions from the app and package. | D01; running frozen candidate. | 2026-10-09 | Documentation owner / tester | All maintained pages render and links work in their supported context. | Users may see stale or broken Help despite correct repository Markdown. | Week 1: Oct 5-9 | High | .agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md
D03 | Documentation | Update the external Setup Guide | Make the owner-held guide follow the exact accepted workflow and record its owner, storage location, editing access, and current link. | Open / external | High | Work before publication | Required before owner handoff | TASK-092 | 2026-07-23 roadmap | The guide is outside the repository and final package details were not known. | M: 0.5-1 day | An owner-controlled external guide matching the candidate. | Access to external document; final artifact values. | 2026-10-16 | Project lead / documentation owner | The guide is reviewed against the frozen workflow and custody is recorded. | A prominent external guide could lead users down an obsolete path. | Week 2: Oct 12-16 | Medium | .agent_work/requirements.md
D04 | Documentation | Prepare final release notes and download record | Add exact URLs, hashes, prerequisites, tested profiles, unsigned support boundary, limitations, and rollback/support links. | Open | High | Work before publication | Required before publication | TASK-092 / TASK-089 | 2026-09-21 | Final URLs, hashes, and acceptance results are not yet available. | M: 0.5 day | A clear authoritative release record for users and maintainers. | R06, R14-R15; final identity. | 2026-10-19 | Release owner / documentation owner | Notes agree with final artifacts and never overclaim blocked cells. | Users cannot safely identify or verify the intended downloads. | Week 3: Oct 19-23 | High | .agent_work/tasks/active/TASK-092-documentation-currentness.md
D05 | Documentation | Confirm the Podman Python prerequisite | Verify the independent instructions clearly require a supported Python version and do not promise Python 3.14 compatibility. | Open independent confirmation | High | Do with Podman tests | Required for Podman support | TASK-097 | 2026-09-22 | Python 3.12 passed and 3.14 failed only on the first host. | S: 0.25 day | Accurate prerequisite wording backed by an independent run. | R11-R12; suitable Python 3.12 installation. | 2026-10-15 | Podman tester / documentation owner | The supported version works and the guide states the tested boundary. | A new user could fail during provider installation. | Week 2: Oct 12-16 | High | .agent_work/tasks/active/TASK-103/W09-EVIDENCE-INDEX.md
D06 | Documentation | Verify administrator model-upload guidance | Ensure the final owner/user materials explain the opt-in upload key, approved model hash, disabled-by-default behavior, rotation, and safe troubleshooting. | Open verification | High | Work before handoff | Required by DOC-001 | TASK-092 / requirements | 2026-07-23 requirements | Current support contract text exists, but the public/owner documentation acceptance is not closed. | M: 0.25-0.5 day | Clear separation between normal user setup and restricted model administration. | Final owner guide and public docs. | 2026-10-09 | Documentation owner / security reviewer | All required controls are documented without a live secret. | An owner could enable a sensitive feature without both controls. | Week 1: Oct 5-9 | Medium | .agent_work/requirements.md
D07 | Installation video | Write the video script and shot list | Choose a permitted demo area, neutral desktop, recording location, primary profile, and short inserts for Podman/GPU differences. | Open | High | Work now | Required before video capture | TASK-092 / post-Day-7 guide | 2026-09-21 | The recording must wait for the current workflow decision, but planning can start now. | S: 0.25-0.5 day | A privacy-safe plan for a 4-6 minute user video. | Demo area/media permission; recording owner. | 2026-10-02 | Recorder / documentation owner | Script identifies every screen, redaction pause, version statement, and owner-controlled destination. | Late planning could expose credentials or force rushed recapture. | Opening days: Oct 1-2 | High | .agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md
D08 | Installation video | Dry-run the video workflow | Walk through the exact frozen-package steps without recording final footage; fix unclear instructions first. | Blocked by frozen candidate | High | Work by freeze | Required before final capture | TASK-092 | 2026-09-21 | The replacement package does not yet exist. | S: 0.25-0.5 day | A smooth, accurate recording path with no hidden setup. | R03-R07; D07. | 2026-10-09 | Recorder / tester | The full demonstrated path succeeds and matches the written guide. | The final video could show unsupported or undocumented steps. | Week 1: Oct 5-9 | Medium | .agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md
D09 | Installation video | Capture, edit, caption, and privacy-review the video | Record the accepted package, add captions/transcript/chapters, and inspect every frame and audio segment for sensitive or misleading content. | Blocked by acceptance candidate | High | Work after freeze | Required before approved distribution | TASK-092 | 2026-09-21 | Final footage must use the inventoried candidate. | L: 1-1.5 days | A concise, accessible installation demonstration. | Frozen candidate; recording/editing tools; privacy review. | 2026-10-16 | Recorder/editor / privacy reviewer | The clip identifies version/profile, hides credential entry, and passes frame/audio review. | A leaked key or outdated workflow could be published. | Week 2: Oct 12-16 | Medium | .agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md
D10 | Installation video | Independent video comparison and custody transfer | Have a tester repeat the demonstrated path, confirm audience access, and transfer video, transcript, editable project, and hosting permissions. | Open | High | Work before owner rehearsal | Required before handoff | TASK-092 / TASK-095 | 2026-09-21 | The final video and owner-controlled destination do not yet exist. | M: 0.5 day | A usable video that does not depend on the outgoing developer. | D09; independent tester; owner-controlled hosting. | 2026-10-23 | Independent tester / receiving owner | Tester succeeds and owner can access/edit/host all deliverables. | The video may become inaccessible or impossible to maintain. | Week 3: Oct 19-23 | Medium | .agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md
H01 | Owner handoff | Draft the owner operations guide | Explain ownership, access, maintenance setup, release qualification, rollback, security, providers/assets/models, routine support, and backlog decisions in plain language. | Open | Critical | Work in parallel now | Required before rehearsal | TASK-095 Phase B | 2026-07-23 | Phase B is still open and the exact candidate is only now stabilizing. | L: 1-1.5 days | A tool-neutral guide usable without this conversation or a specific AI product. | Current tested procedures; owner role decisions. | 2026-10-09 | Maintainer / receiving owner reviewer | Every chapter links maintained procedures and includes verification and rollback. | Knowledge transfer would remain person-dependent. | Opening days and Week 1 | Medium | .agent_work/tasks/active/TASK-095-governance-ai-ready-handoff.md
H02 | Owner handoff | Document tool-neutral maintenance procedures | Write how to plan, implement, test, release, roll back, and maintain TowerScout using repository-native steps. | Open | Critical | Work before rehearsal | Required by HANDOFF-001 | TASK-095 Phase B | 2026-07-23 | This was intentionally deferred to Phase B and final evidence. | M: 0.5-1 day | The owner can safely change and verify the project without Codex-specific knowledge. | H01; final build/test procedures. | 2026-10-16 | Maintainer | A new maintainer can prepare an environment and run a focused check from the guide. | Future work could be blocked by missing process knowledge. | Week 2: Oct 12-16 | Medium | .agent_work/requirements.md
H03 | Owner handoff | Agree owner roles and maintenance cadence | Name primary/backup roles and agree how often to review support, security, access, backups, storage, and qualification needs. | Open / owner input | High | Work before owner review | Required before handoff | TASK-095 | 2026-07-23 | Repository documents cannot assign real people or schedules by themselves. | S: 0.25 day | Clear responsibility and a realistic operating rhythm. | Receiving owner and backup availability. | 2026-10-16 | Project lead / receiving owner | Roles, escalation expectations, and accepted cadence are recorded without personal details in public files. | Important work could have no accountable owner. | Week 2: Oct 12-16 | Low-Medium | .agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md
H04 | Owner handoff | Verify access and custody | Primary and backup demonstrate access to repositories, CI, packages, release tooling, assets, guides/video, test fixtures, and support records. | Open / external | Critical | Work early | Required before closeout | TASK-095 / TASK-089 | 2026-07-23 | Access cannot be proven by repository text and final destinations are not all selected. | M: 0.5 day plus coordination | No critical asset depends on the outgoing developer's personal account. | Owner participation; account administrators. | 2026-10-09 | Project lead / receiving owner / backup | Each role demonstrates its own access and missing permissions have named remediation owners. | The project could end with inaccessible releases or support records. | Opening days and Week 1 | Low-Medium | .agent_work/tasks/active/TASK-095-governance-ai-ready-handoff.md
H05 | Owner handoff | Owner and backup review the guide | Walk through the owner guide, record confusion and required assistance, and correct it before the formal rehearsal. | Blocked by H01-H04 | Critical | Work by acceptance | Required before rehearsal | TASK-095 | 2026-09-21 guide | The draft and confirmed access are not ready. | M: 0.5 day | An owner-reviewed guide and final rehearsal checklist. | H01-H04; owner availability. | 2026-10-16 | Receiving owner and backup | Review comments are resolved or listed as blockers. | The formal rehearsal could discover basic gaps too late. | Week 2: Oct 12-16 | Medium | .agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md
H06 | Owner handoff | Run the owner-operated release and recovery rehearsal | The receiving owner performs package/release identification, support diagnosis, rollback/recovery, and evidence checks with minimal prompting. | Blocked by acceptance and H05 | Critical | Work in Week 3 | Required by October 23 | TASK-091 / TASK-095 | 2026-07-23 roadmap | The final candidate and owner guide are not accepted yet. | L: 1 day | Proof that ownership can continue after project end. | Accepted candidate; owner/backup; isolated recovery target. | 2026-10-23 | Receiving owner; maintainer observes | The owner completes critical procedures and all assistance/corrections are recorded. | Operational dependence on the outgoing developer would remain. | Week 3: Oct 19-23 | Medium | .agent_work/requirements.md
H07 | Backlog and governance | Draft the owner-facing post-handoff backlog | Turn open, conditional, and deferred work into one plain-language maintenance decision list with entry criteria and acceptance checks. | Open | High | Work now | Required before backlog review | TASK-095 | 2026-09-21 guide | The current backlog is agent-oriented and the successor has not been created. | M: 0.5-1 day | A proposed owner-readable backlog without duplicating active authority. | This workbook; current task dispositions. | 2026-10-05 | Project lead / maintainer | Each carried item has impact, evidence, workaround, priority, effort, owner role, and last-reviewed date. | The owner may need to reconstruct priorities from historical documents. | Opening days and Week 1 | High | .agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md
H08 | Backlog and governance | Review 30/60/90-day priorities with the owner | Agree which future items matter first without promising unallocated staff or time. | Blocked by H07 | High | Work before rehearsal close | Required before backlog cutover | TASK-095 | 2026-09-21 guide | Owner priorities and available capacity are not yet known. | S: 0.25-0.5 day | An owner-accepted near-term maintenance order. | Receiving owner participation. | 2026-10-23 | Receiving owner / project lead | The first maintenance review has agreed priorities and explicit deferrals. | A technically complete backlog may still be unusable for real planning. | Week 3: Oct 19-23 | Medium | .agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md
H09 | Backlog and governance | Cut over to one canonical maintenance backlog | Update handoff and task entrypoints, archive or mark the outgoing board read-only, and preserve task-ID history. | Blocked by H08 | Critical | Work at closeout | Required by October 30 | TASK-095 | 2026-09-21 guide | The project is still actively using the current board. | M: 0.5 day | One location the new owner updates after closeout. | H08; final task dispositions. | 2026-10-30 | Project lead / maintainer | All entrypoints point to the chosen backlog and old boards are clearly historical. | Conflicting task authorities could confuse future maintainers or agents. | Week 4: Oct 26-30 | High | .agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md
H10 | Backlog and governance | Record optional AI-assisted workflows | Describe optional ways an owner may use AI while keeping every core procedure tool-neutral. | Open | Medium | Work after core guide | Required by TASK-095, not a release gate | TASK-095 | 2026-07-23 | Phase B has not completed. | S: 0.25 day | AI help is optional rather than a maintenance dependency. | H02. | 2026-10-23 | Maintainer | Guide clearly separates required repository processes from optional AI assistance. | The handoff could accidentally require unavailable vendor tooling. | Week 3: Oct 19-23 | High | .agent_work/tasks/active/TASK-095-governance-ai-ready-handoff.md
H11 | Backlog and governance | Decide whether GitHub Issues supplement the backlog | Choose one canonical destination and avoid two separately edited backlogs. | Open / owner decision | Medium | Decide, do not overbuild | Required before backlog transfer | TASK-095 / TASK-089 | 2026-07-23 | Issues availability and owner preference are unknown. | S: 1-2 hours | A documented backlog destination decision. | Receiving owner; cdcai Issues availability. | 2026-10-23 | Receiving owner | Decision and migration/cutover method are recorded. | Duplicate lists could drift immediately after handoff. | Week 3: Oct 19-23 | Medium | .agent_work/tasks/active/TASK-095-governance-ai-ready-handoff.md
H12 | Owner handoff | Create the sanitized custody index | List source, image/ZIP hashes, model/fixture provenance, evidence, guide/video versions, and storage locations without secrets. | Open | Critical | Work before sign-off | Required for closeout | TASK-095 / W10 | 2026-09-21 guide | Final identities and external locations are not complete. | M: 0.5 day | A durable map of what exists and who holds it. | R14; D03-D10; H04; sanitization results. | 2026-10-23 | Maintainer / receiving owner | Every final deliverable and private-custody pointer is accounted for. | Evidence or media could be lost after the outgoing developer leaves. | Week 3: Oct 19-23 | Medium | .agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md
H13 | Owner handoff | Complete final operational sign-off | Reconcile completed acceptance, known limitations, residual risks, open owner decisions, custody, access, and canonical backlog. | Open | Critical | Work at closeout | Hard closeout requirement | TASK-095 / HANDOFF-002 | 2026-07-23 | All other work feeds this final decision. | M: 0.5 day | No planned work depends on the outgoing developer after October 31. | All critical actions; owner availability. | 2026-10-30 | Project lead and receiving owner | Signed closeout states either completed adoption or the exact migration-ready fallback. | Project responsibilities could remain ambiguous after the deadline. | Week 4: Oct 26-30 | High | .agent_work/requirements.md
S01 | Sanitization | Inventory the transfer scope and sensitive-material custody | List paths and categories for source, branches, artifacts, fixtures, screenshots, logs, certificates, keys, environment files, media, and external assets without printing their contents. | Open | High | Work now | Required before transfer review | TASK-095 / post-Day-7 guide | 2026-09-21 | The intended final transfer set was not previously fixed. | M: 0.5 day | A bounded scan scope and custody map. | Owner-approved scope; access to relevant locations. | 2026-10-02 | Maintainer / security reviewer | Every transfer surface is categorized as public, private, historical, or excluded. | Later scanning may miss important artifacts or expose private data. | Opening days: Oct 1-2 | Medium | .agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md
S02 | Sanitization | Run controlled redacting scans and remediate findings | Scan an isolated transfer view, privately triage findings, replace private examples, fix allowlists/ignore rules, and arrange credential rotation if needed. | Blocked by S01 | High | Work before candidate review | Required before transfer | TASK-095 | 2026-09-21 | No final transfer scope or approved method is recorded. | L: 0.5-1 day; more if incident found | No known unresolved sensitive exposure in the intended transfer set. | Approved redacting tools; private findings process. | 2026-10-09 | Security reviewer / maintainer / credential owner | All findings have a disposition and any real credential is rotated by its owner. | Public release or handoff could expose keys, personal paths, or private evidence. | Week 1: Oct 5-9 | Low-Medium | .agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md
S03 | Sanitization | Inspect the accepted candidate and media outputs | Review final source, ZIPs, relevant image contents, reports, and video for inappropriate private content or missing notices. | Blocked by candidate outputs | High | Work by acceptance | Required before publication | TASK-095 | 2026-09-21 | Final candidate and media do not yet exist. | M: 0.5 day | A recorded candidate-level sanitization pass. | R03; D09; S02. | 2026-10-16 | Security reviewer / release reviewer | Reviewed artifacts, methods, exclusions, and dispositions are recorded. | A clean source tree could hide problems in packaged or media outputs. | Week 2: Oct 12-16 | Medium | .agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md
S04 | Sanitization | Run the final closeout delta review | Check only changes since the candidate pass and verify the intended audience can access the sanitized destination material. | Blocked by S03 | High | Work at closeout | Required by October 30 | TASK-095 | 2026-09-21 | Closeout changes are not known yet. | S: 0.25-0.5 day | Final sanitization evidence for the actual transferred state. | S03; final artifact/ownership state. | 2026-10-30 | Security reviewer / receiving owner | No undisposed delta remains and destination access is verified. | Late changes could bypass the earlier review. | Week 4: Oct 26-30 | High | .agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md
A01 | Adoption | Review pilot feedback and final candidate findings | Summarize actionable owner-held feedback and compare it with the qualified candidate without copying private feedback into the repo. | Owner-gated / open | High | Schedule before adoption decision | Required before cdcai adoption | TASK-089 | 2026-07-10 | The repository does not contain the external feedback review result. | M: 0.25-0.5 day | A documented candidate/adoption recommendation. | Project lead; external feedback document; R15. | 2026-10-19 | Project lead / cdcai owner | Feedback is reviewed and every blocker has an owner or disposition. | The official repository could adopt a baseline that ignores user findings. | Week 3: Oct 19-23 | Low-Medium | .agent_work/tasks/active/TASK-089-cdcai-migration-execution.md
A02 | Adoption | Complete the migration-ready handoff packet | Record candidate source, tags, image/package choices, hashes, evidence, backlog, namespace plan, and safe verification sequence without changing cdcai. | Open preparation | High | Work regardless of adoption outcome | Required for closeout fallback | TASK-089 | 2026-07-08 | Final candidate inputs and owner decisions are not known. | M: 0.5-1 day | A safe packet that can be executed later if adoption is delayed. | R14-R15; D04; H12. | 2026-10-23 | Release owner / maintainer | Packet contains exact current inputs and non-destructive steps. | A delayed adoption would leave the new owner without an executable path. | Week 3: Oct 19-23 | Medium | .agent_work/tasks/active/TASK-089-cdcai-migration-execution.md
A03 | Adoption | Obtain the explicit adoption decision | The project lead and cdcai owner approve a final baseline or decide to leave cdcai unchanged for now. | Owner-gated | Critical | Decision gate | Required before any cdcai mutation | TASK-089 | 2026-07-08 | Technical access is not authorization and qualification is unfinished. | S: 1-2 hours | A recorded go/no-go adoption decision. | A01-A02; R15; owner availability. | 2026-10-23 | Project lead and cdcai owner | Decision names the baseline and authorized actions, or explicitly selects the fallback. | Unauthorized source, package, or release changes could occur. | Week 3: Oct 19-23 | Low-Medium | .agent_work/tasks/active/TASK-089-cdcai-migration-execution.md
A04 | Adoption | Select official tag, title, and namespace strategy | Before an official build, choose the cdcai version/title and decide whether URLs/image defaults are rebuilt or explicitly carried forward. | Blocked by A03 | High | Do only if adoption approved | Required before official build | TASK-089 | 2026-07-08 | Candidate naming does not reserve the official identity. | S: 0.25 day | One approved official identity and namespace plan. | A03; cdcai owner decision. | 2026-10-23 | cdcai owner / project lead | Tag, display title, release URLs, image paths, and disclosure strategy are written down. | Packages and release records could disagree or silently change tag meaning. | Week 3: Oct 19-23 | High | .agent_work/requirements.md
A05 | Adoption | Confirm cdcai permissions and backlog destination | Verify collaborator write, Actions, GHCR package ownership, release publication, and the approved durable backlog location. | Owner-gated / open | Critical | Work early; mutate nothing | Required before transfer | TASK-089 | 2026-07-08 | Execution-time permissions and Issues availability are unconfirmed. | M: 0.25-0.5 day coordination | A confirmed execution window with accountable owners. | Account administrators; A03-A04 for execution. | 2026-10-23 | cdcai maintainer / project lead | Primary and backup demonstrate required access and destination choices are recorded. | The final week could be blocked by basic access gaps. | Opening days through Week 3 | Low | .agent_work/tasks/active/TASK-089-cdcai-migration-execution.md
A06 | Adoption | Build official cdcai images and packages | Build from the approved tagged tree using the official identity; do not rename candidate ZIPs. | Conditional on A03 approval | High | Do only if authorized | Required for adopted release | TASK-089 | 2026-07-08 | Adoption and official identity are not approved. | L: 0.5-1 day plus CI | Official artifacts whose manifests, filenames, checksums, source refs, and docs agree. | A03-A05; build/registry availability. | 2026-10-27 | Release owner / cdcai maintainer | Official build completes with exact identity and required scans/checks. | Renamed or inconsistently rebuilt artifacts would invalidate candidate evidence. | Week 4: Oct 26-30 | Low-Medium | .agent_work/tasks/active/TASK-089-cdcai-migration-execution.md
A07 | Adoption | Push approved history and tags safely | Use the reviewed non-destructive sequence; no force push, squash of selected history, or bulk tag push. | Conditional on A03 approval | High | Do only if authorized | Required for adopted repository | TASK-089 | 2026-07-08 | The approved baseline/tag set is unknown. | S: 0.25 day | Traceable official source history without unintended tags. | A03-A05; final tag list. | 2026-10-27 | cdcai maintainer | Only approved refs are present and source provenance is verified. | History or misleading historical tags could be published incorrectly. | Week 4: Oct 26-30 | Medium | .agent_work/tasks/active/TASK-089-cdcai-migration-execution.md
A08 | Adoption | Publish official images and release | Publish the approved GHCR images and recreate the cdcai release from validated official artifacts. | Conditional / owner-gated | High | Do only if authorized | Required for adopted release | TASK-089 | 2026-07-08 | All qualification and adoption gates must pass first. | M: 0.5 day plus propagation | Owner-controlled official downloads and images. | A06-A07; publication authorization. | 2026-10-28 | cdcai maintainer / release owner | Visibility/linkage, assets, checksums, and release notes are correct. | Users could receive incomplete or unverified official artifacts. | Week 4: Oct 26-30 | Low-Medium | .agent_work/tasks/active/TASK-089-cdcai-migration-execution.md
A09 | Adoption | Verify the transfer from a fresh consumer path | Clone, pull, download, verify, and smoke the official package/source identities after transfer. | Conditional on A08 | Critical | Do after publication | Required for adopted release | TASK-089 | 2026-07-08 | Official artifacts are not published. | M: 0.5 day | Evidence that the public official path works independently. | A08; fresh test location; registry/release access. | 2026-10-29 | Independent tester / receiving owner | Clone, image pull, ZIP verification, package smoke, and source-ref checks pass. | A publication could look complete while downloads or provenance are broken. | Week 4: Oct 26-30 | Medium | .agent_work/tasks/active/TASK-089-cdcai-migration-execution.md
A10 | Adoption | Transfer the backlog to the approved destination | Move or link the accepted maintenance backlog once, then stop independently editing the old board. | Blocked by H11 and A05 | High | Work at closeout | Required before ownership transfer | TASK-089 / TASK-095 | 2026-07-08 | The durable destination has not been chosen. | M: 0.25-0.5 day | One owner-controlled backlog after project end. | H08-H11; A05. | 2026-10-30 | Receiving owner / maintainer | All carried items are present with working references and one canonical status location. | Open work could be lost or split across duplicate systems. | Week 4: Oct 26-30 | Medium | .agent_work/tasks/active/TASK-089-cdcai-migration-execution.md
A11 | Adoption | Use the no-adoption fallback if approval is late | Leave cdcai unchanged and deliver the qualified fork, evidence, feedback pointers, backlog, and migration-ready packet. | Ready fallback | Critical | Use if A03 is not approved | Required closeout alternative | TASK-089 | 2026-07-10 | Adoption is explicitly optional and owner-controlled. | S: 0.25 day after A02 | A clean project closeout without unauthorized cdcai changes. | A02; H12-H13. | 2026-10-30 | Project lead / receiving owner | Closeout explicitly states the adoption blocker, owner, and next authorized action. | The deadline could pressure the team into unauthorized publication. | Week 4: Oct 26-30 | High | .agent_work/context/status/Handoff-Planning/PILOT-FEEDBACK-AND-CDC-AI-ADOPTION-PLAN.md
Q01 | Security and compliance | Recheck final package/image scans, SBOM, notices, and licenses | Confirm the exact final identities have the required scan/SBOM and compliance inventory; rerun image checks if an official rebuild changes digests. | Open final-identity check | High | Work before publication | Required for final identity | TASK-103 / compliance requirements | 2026-09-24 | Existing evidence is tied to earlier image/package identities. | M: 0.25-0.75 day | Security/compliance evidence matches the actual released artifacts. | Final digests/ZIPs; A06 if official rebuild occurs. | 2026-10-16 or after A06 | Release reviewer / compliance reviewer | Every released digest/ZIP has its matching evidence and unresolved findings are dispositioned. | Evidence could be incorrectly carried to changed bytes. | Week 2 and conditional Week 4 | Medium | .agent_work/tasks/active/TASK-103/NVIDIA-RUNTIME-COMPONENT-INVENTORY.md
Q02 | Security and compliance | Carry forward the remaining torch advisory and bridge exit triggers | Keep the one residual advisory visible and explain when a future owner must leave or replace the CUDA 12.8 bridge. | Open handoff note | Medium | Document for future owner | Not a current release blocker if accepted | TASK-103 / ADR-022 | 2026-09-24 | The advisory has no current compatible replacement and must not disappear from handoff. | S: 1-2 hours | A transparent future upgrade trigger and security monitoring note. | Owner guide/backlog. | 2026-10-23 | Security reviewer / maintainer | Residual risk and exit triggers are present in the owner backlog/guide. | A future owner may assume the dependency state is permanently accepted. | Week 3: Oct 19-23 | High | .agent_work/tasks/active/TASK-103/DEPENDENCY-SECURITY-DISPOSITION.md
Q03 | Contingency | Fix only acceptance blockers and rerun affected gates | After freeze, make no optional changes. If a blocker is found, create a new identity and repeat only the checks affected by changed bytes. | Reserved contingency | Critical | Use only when triggered | Protects acceptance truth | W09/W10 stop rule | 2026-09-21 | Independent testing may reveal real defects. | Reserve 2-3 person-days | A corrected candidate or an honest blocked result without scope creep. | Observed blocker; owner decision; available buffer. | 2026-10-19 to 2026-10-21 | Release implementer / reviewer | Every change has a new identity and affected evidence is rerun before acceptance. | Late untracked fixes could invalidate all release evidence. | Week 3 contingency | Low | .agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md
B01 | Conditional backlog | TASK-076 provider key ownership and restriction guidance | Clarify account ownership, key restrictions, billing/quota responsibility, rotation, and safe error guidance; change code only for observed ambiguity. | Required guidance / not selected | Medium | Complete guidance during owner docs; defer code unless evidence requires it | Conditional code; handoff guidance | TASK-076 | Current backlog by 2026-09-24 | It was not needed for the bounded W00-W10 fixes and depends on owner/account decisions. | S-M: 0.25-1 day | Safe provider administration guidance. | Owner/account input; observed errors for code work. | 2026-10-16 guidance; code future if needed | Provider account owner / docs maintainer | Owner guide covers restrictions/rotation and any reproduced ambiguity is resolved. | Keys may be over-permissioned or support ownership unclear. | Week 2 guidance only | Medium | .agent_work/task-backlog.md
B02 | Conditional backlog | TASK-077 manifest and asset-import hardening | Select only if replacement-package testing shows an integrity, import, or recovery gap. | Evidence-selected / not currently selected | Medium | Do not start unless triggered | Conditional | TASK-077 | Current backlog by 2026-09-24 | Current package evidence has not demonstrated a remaining gap. | M-L: 1-3 days if triggered | A bounded fix for a real artifact-integrity failure. | Reproduced W09/W10 gap. | Before acceptance if triggered; otherwise post-handoff | Release implementer | The reproduced gap has a focused test and replacement artifact evidence. | Starting speculative hardening would consume closeout capacity. | Contingency only | Low | .agent_work/task-backlog.md
B03 | Conditional backlog | TASK-027 enhanced error handling | Fix only a reproduced user-facing release blocker that is not already owned by the current W02-W08 work. | Conditional / not selected | Medium | Do not start unless triggered | Conditional | TASK-027 | Existing backlog; reconfirmed 2026-09-24 | No unowned blocking error is currently recorded. | M-L: 1-3 days if triggered | A clear error and recoverable user path for the specific failure. | Reproduced blocker; acceptance test. | Before acceptance if triggered; otherwise future | Application maintainer | The exact failure is tested and recovery works without broad framework changes. | A broad error-system rewrite could displace acceptance work. | Contingency only | Low | .agent_work/task-backlog.md
B04 | Conditional backlog | TASK-070 restricted-network enhancements | Add offline/restricted distribution only if the owner explicitly claims that environment; keep normal managed-network support accurate. | Conditional / not selected | Low-Medium | Defer unless required environment is claimed | Conditional | TASK-070 | Existing backlog; reconfirmed 2026-09-24 | The standard claim does not require fully offline installation. | L-XL: 3-8 days | A separately qualified restricted-network path. | Owner scope decision; network/test environment; revised schedule. | Post-handoff unless urgently required | Future owner / runtime maintainer | The new environment has explicit artifacts, instructions, and acceptance evidence. | Selecting it now would threaten the fixed end date. | Not scheduled | Low | .agent_work/task-backlog.md
B05 | Conditional backlog | TASK-094 sanitized support snapshot | Add a small redacted support export only if real cases cannot be resolved with current status/log procedures. | Evidence-gated / not selected | Low-Medium | Do not start unless support evidence demands it | Conditional | TASK-094 | 2026-07-23 roadmap | No unresolved support case demonstrates the need. | M-L: 1-3 days | A bounded support bundle with no keys or private data. | Real support gap; privacy design/review. | Post-handoff unless triggered before closeout | Support maintainer / security reviewer | A real case is solved and redaction tests pass. | A speculative collector creates privacy and maintenance risk. | Not scheduled | Low | .agent_work/task-backlog.md
B06 | Conditional backlog | TASK-026 CPU optimization | Tune only after a measured bottleneck on the smallest supported host; preserve output and memory behavior. | Conditional / not selected | Low | Defer unless measured regression blocks acceptance | Conditional | TASK-026 | Existing backlog; reconfirmed 2026-09-24 | No current supported-host performance blocker is recorded. | L: 2-5 days | Measured improvement without correctness regression. | Repeatable measurement; protected qualification time. | Post-handoff unless release blocker | ML/runtime maintainer | Benchmark, output parity, memory, and four-profile affected checks pass. | Speculative optimization could destabilize the qualified ML runtime. | Not scheduled | Low | .agent_work/task-backlog.md
F01 | Deferred | TASK-087 launcher and guided TLS control plane | Preserve PR #64/#67 tags, commits, reviews, and evidence; do not resume or merge during this project closeout. | Archived / deferred | Low | Do not work before October 31 | Not a release gate | TASK-087 | 2026-06-29 | The current command-based path passed the required first-host workflows and the redesign is explicitly deferred. | XL: 4-7 days plus managed-network validation | Future owner can reconsider from current main with preserved history. | New owner scope and fresh branch. | Post-handoff only | Future owner | History is preserved and the maintenance backlog states entry criteria. | Resuming now would conflict with ADR-021 and consume acceptance/handoff time. | Not scheduled | High | .agent_work/tasks/active/TASK-087-host-side-tls-repair-control-plane.md
F02 | Deferred | TASK-096 browser Exit/helper | Continue using the tested command-based stop/start workflow; leave browser Exit redesign for a future owner. | Deferred | Low | Do not work before October 31 | Not a release gate | TASK-096 | 2026-07-23 roadmap | The existing lifecycle now satisfies the current supported outcome. | L: multi-day feature | Future optional convenience feature with its own safety review. | New owner decision; TASK-087 design questions. | Post-handoff only | Future owner | Deferred rationale and current safe commands are documented. | A late host-control UI could introduce security and lifecycle defects. | Not scheduled | High | .agent_work/task-backlog.md
F03 | Deferred | TASK-058 background detection jobs | Do not start the job-queue/state-machine redesign; retain only the bounded admission/cancellation fixes already accepted. | Deferred architecture | Low | Do not work before October 31 | Not a release gate | TASK-058 | Existing pre-July backlog | The synchronous path is qualified and closeout work has higher priority. | XL: >5 days | Future durable job architecture if owner selects it. | Separate design, migration, recovery, and UI scope. | Post-handoff only | Future application owner | Owner selects a new scoped task with tests and rollback plan. | Large architecture work would threaten project completion. | Not scheduled | High | .agent_work/task-backlog.md
F04 | Deferred | TASK-059 backend decomposition | Do not restructure backend layers during release closeout. | Deferred architecture | Low | Do not work before October 31 | Not a release gate | TASK-059 | Existing pre-July backlog | No current acceptance blocker requires the refactor. | XL: >5 days | Future maintainability improvement after release stability. | Owner priority; preferably after TASK-058 decision. | Post-handoff only | Future application owner | A separately approved plan protects APIs, data, and regression coverage. | Refactoring now creates broad regression risk. | Not scheduled | High | .agent_work/task-backlog.md
F05 | Deferred | TASK-060 frontend build modernization | Keep the current maintained build because it is not blocking acceptance. | Deferred maintenance | Low | Do not work before October 31 | Not a release gate | TASK-060 | Existing backlog | The current bundle build and parity checks pass. | L-XL: 3-8 days | A future modern build pipeline with migration evidence. | Owner selection; frontend compatibility plan. | Post-handoff only | Future frontend owner | New pipeline preserves generated bundle behavior and support docs. | Build-system churn could invalidate the tested candidate. | Not scheduled | High | .agent_work/task-backlog.md
F06 | Deferred | TASK-061 coordinated NumPy 2 migration | Do not add a dependency migration to the current qualified ML/runtime line. | Deferred dependency track | Low | Do not work before October 31 | Not a release gate | TASK-061 | Existing backlog | The current dependency set is qualified and no blocker requires this change. | L-XL: 3-8 days | Future coordinated compatibility migration. | Dependency compatibility and full CPU/CUDA requalification. | Post-handoff only | Future runtime owner | All dependent packages and runtime profiles pass together. | A late dependency migration could break models or geospatial behavior. | Not scheduled | High | .agent_work/task-backlog.md
F07 | Deferred | TASK-078 Apache-only runtime migration | Retain the current compliant runtime and notices; treat a permissive-only migration as a future release track. | Deferred release track | Low | Do not work before October 31 | Not a release gate | TASK-078 | Existing backlog | It is not required for the current owner-approved release boundary. | XL: >5 days | A separately designed replacement runtime if future ownership requires it. | Legal/compliance/product decisions and model requalification. | Post-handoff only | Future owner / compliance reviewer | A new track has approved requirements and equivalent model results. | Attempting it now would create major scope and model risk. | Not scheduled | High | .agent_work/task-backlog.md
F08 | Deferred | TASK-029 multi-provider fallback | Keep explicit Google/Azure selection and current error guidance; do not add automatic fallback during closeout. | Deferred product work | Low | Do not work before October 31 | Not a release gate | TASK-029 | Existing backlog | Provider policy/error behavior must stay stable through release. | L: 3-5 days | Future explicit fallback behavior with billing and state rules. | Product policy; provider state design; user consent. | Post-handoff only | Future product owner | Fallback cannot leak keys, surprise billing, or corrupt selection state. | Late fallback work would broaden provider/race risk. | Not scheduled | High | .agent_work/task-backlog.md
F09 | Deferred | TASK-028 mobile responsiveness | Keep the supported Windows desktop/browser boundary; treat mobile layout as parking-lot work. | Deferred / parking lot | Low | Do not work before October 31 | Not a release gate | TASK-028 | Existing backlog | Mobile is outside the current product boundary. | L: 2-5 days | Future mobile usability improvements if scope changes. | Product support decision; device/browser testing. | Post-handoff only | Future product owner | A new support claim is explicitly defined and tested. | It would spend closeout time on an unsupported platform. | Not scheduled | High | .agent_work/task-backlog.md

## W00-W10 Crosswalk
W00-W10 Current Status Crosswalk
The original implementation-plan checkboxes were not maintained as a live tracker. This crosswalk applies current task/evidence status after ADR-022 and ADR-023.
Work package | Purpose | Current status | Verified completed evidence | Still required | Planning note
W00 | Direction and agent entrypoints | Complete | ADR-021/022/023, board, agent instructions, skills, and current direction are aligned. | Keep aligned through closeout; final entrypoint check is part of H09/H13. | Not a current implementation blocker.
W01 | Baseline package and feasibility | Complete for first host; independent resources still open | Real package attempts, host/runtime inventory, assets, accounts, and at-risk forecast were recorded. | Reserve and inventory the independent host/tester (R08). | External host availability remains critical.
W02 | Dormant helper dependency | Complete | Task-068 merged and final rc4 package lifecycle passed on the first host. | Preserve completed evidence; no new Task-087 work. | Move the completed task at sprint closeout.
W03 | Bound processes and target Podman | Complete for first host | Bounded commands, explicit rootless target, and package-local provider passed. | Repeat target behavior on the independent host under R11-R12. | Independent proof remains.
W04 | Transactional TLS repair | Complete for first host | Docker and Podman provider TLS repair passed dry-run/apply/relaunch and persistence. | Repeat applicable managed-network steps during independent testing. | Do not broaden into deferred launcher work.
W05 | Combined model qualification | Complete for current local images | Exact CPU/CUDA digests passed real YOLO and EfficientNet device/output gates. | Reference the same model/device contract during independent W10 runs. | No threshold or output relaxation.
W06 | Model failure and allocation limits | Complete | Bounded code changes merged and local/runtime evidence passed. | Only reopen for a reproduced final-candidate blocker. | Use contingency Q03 if triggered.
W07 | Rate limits, admission, recovery | Complete for first host | Cancellation readiness, next-request success, and controlled error recovery passed in all local profiles. | Repeat on the independent host under R09-R13. | Broad job-queue redesign remains deferred.
W08 | Google first-use bounds and bundle | Complete | Fix merged; live Google/Azure paths passed locally. | Repeat live provider workflows on the independent host. | No additional provider redesign planned.
W09 | Freeze and verify exact downloads | Incomplete after ADR-023 docs change | Images and rc4 local evidence are valid, but rc4 control ZIPs contain older manuals. | R01-R07: new ZIP identity, integrity checks, local reruns, official hashes, browser-download proof. | Must finish before tester distribution/freeze.
W10 | Independent reproduction and handoff | Incomplete / blocked on independent host | Complete first-host four-profile provider/recovery/reboot matrix exists. | R08-R15 plus documentation, handoff, and evidence reconciliation. | Full release claim is blocked until independent cells pass.

## Task Registry
Task Documentation Registry
One row per task ID found in top-level task files or the current backlog. Current disposition overrides stale status text inside historical completed files.
Task ID | Title | Current disposition | Authority | Status text found in task files | Created | Estimated effort | Unchecked boxes | Included in Open Actions | Interpretation | Top-level source files
TASK-025 | Docker / OCI Containerization | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED - MERGED TO MAIN | Not recorded in current task metadata | 1-2 days (8-16 hours) | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-025-docker-containerization.md
TASK-026 | CPU Optimization | Conditional | Current backlog | No top-level task status | Not recorded in current task metadata | Not estimated in current task metadata | 0 | Yes | Current open work is represented in the curated Open Actions sheet. | .agent_work/task-backlog.md
TASK-027 | Enhanced Error Handling | Conditional | Current backlog | No top-level task status | Not recorded in current task metadata | Not estimated in current task metadata | 0 | Yes | Current open work is represented in the curated Open Actions sheet. | .agent_work/task-backlog.md
TASK-028 | Mobile Responsiveness | Deferred / parking lot | Current backlog | No top-level task status | Not recorded in current task metadata | Not estimated in current task metadata | 0 | Yes | Current open work is represented in the curated Open Actions sheet. | .agent_work/task-backlog.md
TASK-029 | Multi-Provider Fallback | Deferred | Current backlog | No top-level task status | Not recorded in current task metadata | Not estimated in current task metadata | 0 | Yes | Current open work is represented in the curated Open Actions sheet. | .agent_work/task-backlog.md
TASK-031 | Interactive Highlighting System | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED | Not recorded in current task metadata | 1.5 hours | 2 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-031-interactive-highlighting.md
TASK-035 | Memory Management & Map Object Cleanup | Historical / completed; not current work unless reselected | Completed-task history | ✅ IMPLEMENTATION COMPLETE - READY FOR TESTING ¦ COMPLETED ✅ | Not recorded in current task metadata | 2 days | 41 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-035-IMPLEMENTATION-SUMMARY.md .agent_work/tasks/completed/TASK-035-memory-management.md .agent_work/tasks/completed/TASK-035-TESTING-PLAN.md
TASK-037 | User Journey Verification Exercise (Stages 1-4) | Historical / completed; not current work unless reselected | Completed-task history | READY TO RESUME (TASK-041 Complete - 5 Critical Issues Resolved) | Not recorded in current task metadata | 2-3 days | 25 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-037-UPDATE-SUMMARY.md .agent_work/tasks/completed/TASK-037-user-journey-verification.md
TASK-038 | Frontend Code Quality & Refactoring | Historical / completed; not current work unless reselected | Completed-task history | ✅ COMPLETE ¦ ✅ COMPLETE | 2026-02-18 | 41 hours (6 stages) | 22 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-038-COMPLETION-SUMMARY.md .agent_work/tasks/completed/TASK-038-frontend-refactoring.md
TASK-039 | Emergency Geocoding Fixes + Model Resolution Discovery + Google Maps Provider Fixes | Historical / completed; not current work unless reselected | Completed-task history | ✅ COMPLETED ¦ IN_PROGRESS (Phase 4B Complete - Ready for Phase 5 Comprehensive Testing) | February 17, 2026 | 14-27 hours (actual Phase 1-4B: ~18 hours including 9 bug fixes) | 45 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-039-emergency-geocoding-fixes.md .agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md
TASK-040 | Azure Maps Visual Consistency | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED | February 11, 2026 | 2-3 hours | 43 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md
TASK-041 | Implement Deep Dive Priority 2 (State Management & Memory Cleanup) | Historical / completed; not current work unless reselected | Completed-task history | COMPLETE (Phase 1: ✅ COMPLETE, Phase 2: ✅ COMPLETE) | February 13, 2026 | 8-13 hours (Phase 1: 4-6 hours, Phase 2: 4-7 hours) | 110 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md
TASK-042 | Deferred Testing Resolution - Action Log | Historical / completed; not current work unless reselected | Completed-task history | IN_PROGRESS | Not recorded in current task metadata | Not estimated in current task metadata | 5 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-042-testing-action-log.md
TASK-043 | Global Variable Deprecation Continuation | Historical / completed; not current work unless reselected | Completed-task history | Implementation Complete, Ready for Testing ¦ NOT_STARTED | March 10, 2026 | 2-4 hours | 40 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-043-CLEANUP-PLAN.md .agent_work/tasks/completed/TASK-043-CLEANUP-TESTING.md .agent_work/tasks/completed/TASK-043-global-variable-deprecation.md
TASK-044 | Documentation Updates | Historical / completed; not current work unless reselected | Completed-task history | IN_PROGRESS | February 17, 2026 | 2-3 hours | 42 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-044-documentation-updates.md
TASK-045 | Backend Boundary Accumulation Bug Investigation | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED | March 10, 2026 | 4-6 hours | 9 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-045-boundary-accumulation-bug.md
TASK-046 | Setup Wizard and Settings Screen Implementation | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED | March 16, 2026 | 5-9 days (1.5-2 weeks with testing) | 88 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md
TASK-047 | UI Formatting and Polish | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED | April 1, 2026 | 6-10 hours | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-047-ui-formatting-and-polish.md
TASK-049 | Legacy Code Cleanup | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED | March 31, 2026 | 4-6 hours | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-049-legacy-code-cleanup.md
TASK-050 | Full-Repo Stale Code and Performance Audit | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED | March 23, 2026 | 6-10 hours | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-050-full-repo-stale-code-and-performance-audit.md
TASK-051 | Runtime Dependency Audit and Decision Gate | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED | April 8, 2026 | 12-18 hours across Phase 1 audit plus selected Phase 2 cleanup | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-051-runtime-dependency-audit-and-decision-gate.md
TASK-052 | Current Integration Smoke Test Baseline | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED | April 13, 2026 | 4-8 hours | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-052-current-integration-smoke-test-baseline.md
TASK-053 | Detection Workflow Stabilization and Live Browser Validation | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED | April 2, 2026 | 12-20 hours | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-053-detection-workflow-stabilization.md
TASK-054 | Local Launch UX | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED - PHASE 1 MVP | Not recorded in current task metadata | 1-2 days (8-12 hours) | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-054-local-launch-ux.md
TASK-055 | YOLO Torch Hub Pinned-Ref Hardening | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED | April 9, 2026 | 6-10 hours | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-055-yolo-torch-hub-pinned-ref-hardening.md
TASK-056 | First-Run Reliability and Runtime Determinism Hardening | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED | April 10, 2026 | 12-20 hours | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-056-first-run-reliability-and-runtime-determinism-hardening.md
TASK-057 | Local YOLO Runtime Ownership and Torch Hub Independence | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED | April 10, 2026 | 12-20 hours | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-057-local-yolo-runtime-ownership-and-offline-readiness.md
TASK-058 | Background Detection Jobs | Deferred | Current backlog | No top-level task status | Not recorded in current task metadata | Not estimated in current task metadata | 0 | Yes | Current open work is represented in the curated Open Actions sheet. | .agent_work/task-backlog.md
TASK-059 | Backend Layer Decomposition | Deferred | Current backlog | No top-level task status | Not recorded in current task metadata | Not estimated in current task metadata | 0 | Yes | Current open work is represented in the curated Open Actions sheet. | .agent_work/task-backlog.md
TASK-060 | Frontend Build Modernization | Deferred | Current backlog | No top-level task status | Not recorded in current task metadata | Not estimated in current task metadata | 0 | Yes | Current open work is represented in the curated Open Actions sheet. | .agent_work/task-backlog.md
TASK-061 | Coordinated NumPy 2 Migration | Deferred | Current backlog | No top-level task status | Not recorded in current task metadata | Not estimated in current task metadata | 0 | Yes | Current open work is represented in the curated Open Actions sheet. | .agent_work/task-backlog.md
TASK-062 | Pre-Docker Runtime Cleanup and YOLO Loader Hardening | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED | April 14, 2026 | 6-10 hours | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-062-pre-docker-runtime-cleanup-and-yolo-loader-hardening.md
TASK-063 | Pre-Docker Release Hardening And CI Reproducibility Gate | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED | Not recorded in current task metadata | 1-2 days (8-16 hours) | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-063-pre-docker-release-hardening.md
TASK-064 | Targeted Runtime Responsiveness And Inference Baseline | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED | Not recorded in current task metadata | 0.5-1 day (4-8 hours) | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-064-runtime-responsiveness-inference-baseline.md
TASK-065 | Release Packaging And Runtime Support Follow-Through | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED | Not recorded in current task metadata | 1-2 days (8-16 hours) | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-065-release-packaging-runtime-support.md
TASK-066 | Release Candidate Validation Gate | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED - RC1 package gate passed with bounded caveats; later RC7.1 validation superseded the tester-facing release identity | Not recorded in current task metadata | 1-2 days (8-16 hours) | 3 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-066-release-candidate-validation-gate.md
TASK-067 | CI Release Gate Tightening | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED - PR #19 merged May 27, 2026 | Not recorded in current task metadata | 0.5-1 day (4-8 hours) | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-067-ci-release-gate-tightening.md
TASK-068 | Windows Test Portability And Script Validation | Completed current-sprint record; move at sprint closeout | Current board | COMPLETED - W02 merged as `8976222`; no-blocker review, exact-head CI, and final `rc4` four-profile package setup/start/stop/relaunch repetition pass with eight volumes preserved per profile | Not recorded in current task metadata | Not estimated in current task metadata | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/active/TASK-068-windows-script-validation.md
TASK-070 | Restricted-Network Package Enhancements | Conditional | Current backlog | No top-level task status | Not recorded in current task metadata | Not estimated in current task metadata | 0 | Yes | Current open work is represented in the curated Open Actions sheet. | .agent_work/task-backlog.md
TASK-071 | End-User Release Package Documentation | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED - focused validation passed; ready for TASK-066 | Not recorded in current task metadata | 1-2 days (8-16 hours) | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-071-end-user-release-docs.md
TASK-072 | Release Asset Bundle Contract | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED | Not recorded in current task metadata | 1-2 days (8-16 hours) | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-072-release-asset-bundle-contract.md
TASK-073 | Clean-Machine Pilot / UAT Execution Plan | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED - RC7.1 handoff packet approved for tester use with exact CPU/CUDA package values, public-safe evidence boundary, support contacts, default smoke fixture, official RC7.1 publication, and downloaded-artifact CPU/GPU validation; no named tester/cohort, approver, or approval-date gate is required before tester send | Not recorded in current task metadata | 0.5-1 day (4-8 hours) | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-073-clean-machine-uat-plan.md
TASK-074 | Runtime Prerequisite Preflight | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED - post-merge package-artifact bootstrap validation passed | Not recorded in current task metadata | 1-2 days (8-16 hours) for RC1 MVP; additional polish can follow after pilot feedback | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-074-runtime-prerequisite-preflight.md
TASK-075 | Single GPU-Capable Package Implementation | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED - CPU-safe GPU-capable package implementation completed; live GPU support evidence and package delivery continued through TASK-083 and TASK-084 | Not recorded in current task metadata | 1-3 days (8-24 hours), split by validation availability | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-075-single-gpu-capable-package.md
TASK-076 | Provider API Key Exposure And Restriction Policy | Required guidance / conditional code | Current backlog | No top-level task status | Not recorded in current task metadata | Not estimated in current task metadata | 0 | Yes | Current open work is represented in the curated Open Actions sheet. | .agent_work/task-backlog.md
TASK-077 | Public Release Manifest And Asset Import Hardening | Evidence-selected | Current backlog | No top-level task status | Not recorded in current task metadata | Not estimated in current task metadata | 0 | Yes | Current open work is represented in the curated Open Actions sheet. | .agent_work/task-backlog.md
TASK-078 | Permissive Apache-Only Runtime Migration | Deferred | Current backlog | No top-level task status | Not recorded in current task metadata | Not estimated in current task metadata | 0 | Yes | Current open work is represented in the curated Open Actions sheet. | .agent_work/task-backlog.md
TASK-079 | RC1 Reliability Fixes And Performance Instrumentation | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED - Phase 3 CPU optimization validated; single GPU-capable package plan handed to TASK-075 | Not recorded in current task metadata | Phase 1: 1-2 days (8-16 hours); Phase 2A/2B: 0.5-1 day investigation; Phase 3 follow-up depends on benchmark and GPU/CUDA evidence | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-079-rc1-reliability-fixes.md
TASK-080 | RC1 UAT User Guide And Setup Process Simplification | Historical / completed; not current work unless reselected | Completed-task history | SUPERSEDED_COMPLETED - RC2/RC3 UAT guide simplification completed; final tester approval moved to TASK-073 RC7.1 handoff | Not recorded in current task metadata | 1-2 days (8-16 hours), plus optional launcher follow-through | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-080-uat-user-guide-process-simplification.md
TASK-081 | RC3 Runtime Hardening And Podman Independence | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED - runtime hardening and CPU validation completed; live GPU evidence continued through TASK-083 and package delivery through TASK-084 | Not recorded in current task metadata | 2-4 days (16-32 hours), split between CPU-dev-able fixes and hardware-dependent GPU validation | 4 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-081-rc3-runtime-hardening-podman-independence.md
TASK-082 | RC4 Documentation And Package Organization | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED - landed on `main` as `v0.1.0-rc4` in commit `32074a7`; stable docs naming, package docs, app docs links, and repo-organization triage are validated for the rc4 baseline | Not recorded in current task metadata | 1-2 days (8-16 hours), plus optional package-smoke validation | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-082-rc4-docs-package-organization.md
TASK-083 | RC5 Podman Independence, GPU CDI, And Release Validation | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED - Source implementation, Podman 5.8.2 blocker fixes, rc5 candidate image/package assembly, local Docker CPU smoke, live Docker GPU, Docker-Desktop-free Podman CPU, Podman GPU CDI, and fixed-fixture runtime parity are validated for RC5 candidate 3. PR #33 merged on June 16, 2026; GA package distribution polish is split to `TASK-084`. | Not recorded in current task metadata | 3-6 days (24-48 hours), split across CPU-dev-able implementation, GPU-host validation, and package release validation | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-083-rc5-podman-independence-gpu-release.md
TASK-084 | GA Packaging Hardening And Podman Provider Onboarding | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED - implementation, package rebuild, Docker CPU, Docker CUDA CPU-fallback, Podman CPU, CPU-package `-Gpu on` guardrail, Docker GPU, Podman GPU CDI, public-safe evidence, official `v0.1.0-rc6` publication, and post-publication downloaded-release verification passed on June 17, 2026; remaining external tester launch gates belong to `TASK-073`. | Not recorded in current task metadata | 2-4 days (16-32 hours), including runtime-defect cleanup, two-package generation, Podman provider onboarding, docs, and validation | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-084-ga-packaging-hardening-and-podman-provider-onboarding.md
TASK-085 | Dataset ZIP Restore Path Traversal Hardening | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED - source hardening and focused validation passed on June 16, 2026; keep active until sprint closeout | Not recorded in current task metadata | 0.5-1 day (4-8 hours) | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-085-dataset-zip-restore-path-traversal-hardening.md
TASK-086 | Provider TLS Auto-Repair And Setup Triage | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED - RC7.1 published and downloaded-artifact CPU/GPU validation passed with the Task-086 TLS repair baseline; keep Task-087 as a follow-on one-click helper plan, not an RC7.1 baseline blocker | Not recorded in current task metadata | 3-5 days (24-40 hours) plus one managed-network validation pass | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-086-provider-tls-auto-repair-and-setup-triage.md
TASK-087 | Host-Side TLS Repair Control Plane | Archived / deferred; no October implementation | Current board | ARCHIVED / DEFERRED - PRs #64/#67 closed without merge; ADR-021 removes their reconciliation, merge, and launcher completion from the current release path. Historical unpassed gates remain unpassed. | 2026-06-29 | 4-7 days (32-56 hours), plus package validation on a managed TLS-inspected network | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/active/TASK-087-host-side-tls-repair-control-plane.md
TASK-088 | Stable Release And Handoff Closeout | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED - pilot sent, support coverage confirmed, and durable release/evidence custody recorded | 2026-07-08 | 2-4 days | 1 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-088-stable-release-and-handoff-closeout.md
TASK-089 | cdcai Adoption Preparation And Deferred Ownership Transfer | Blocked / owner-gated preparation and possible adoption | Current board | BLOCKED / OWNER-GATED - prepare for the final qualified candidate, but do not change cdcai until explicit owner adoption approval | 2026-07-08 | 0.5-1 day preparation now; 1-2 days execution after adoption approval | 18 | Yes | Current open work is represented in the curated Open Actions sheet. | .agent_work/tasks/active/TASK-089-cdcai-migration-execution.md
TASK-090 | Runtime, Custom-Image, And Dependency Security Investigation | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED | Not recorded in current task metadata | 1-3 days for investigation and classification only | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-090-runtime-custom-image-dependency-security.md
TASK-091 | Owner-Runnable Release Qualification | At risk; replacement package, browser download, and independent host remain | Current board | AT_RISK - local `rc4` CPU/CUDA W05, four-profile W09, and first- host provider/cancel/error/review-export/relaunch/reboot cells pass. ADR-023 resolves policy/signing through an unsigned, narrower support boundary. Replacement packaged documentation, a real browser-download run, and independent-host evidence remain | Not recorded in current task metadata | Not estimated in current task metadata | 0 | Yes | Current open work is represented in the curated Open Actions sheet. | .agent_work/tasks/active/TASK-091-owner-runnable-release-qualification.md
TASK-092 | Documentation Currentness And Information Architecture | In progress; final artifact/external documentation remains | Current board | IN_PROGRESS - ADR-023 unsigned-package alignment active; final artifact-specific manuals, external Setup Guide, and demo material complete before final W09 package freeze and independent-tester distribution | Not recorded in current task metadata | Not estimated in current task metadata | 0 | Yes | Current open work is represented in the curated Open Actions sheet. | .agent_work/tasks/active/TASK-092-documentation-currentness.md
TASK-093 | Persistent Data Lifecycle And Recovery Rehearsal | In progress; independent-host recovery remains | Current board | IN_PROGRESS - final `rc4` first-host stop/relaunch, controlled failure, cancellation recovery, and export persistence pass on all four profiles, including exact-candidate reboot; independent-host recovery remains | Not recorded in current task metadata | Not estimated in current task metadata | 0 | Yes | Current open work is represented in the curated Open Actions sheet. | .agent_work/tasks/active/TASK-093-persistent-data-recovery.md
TASK-094 | Evidence-Gated Support Snapshot | Evidence-gated | Current backlog | No top-level task status | Not recorded in current task metadata | Not estimated in current task metadata | 0 | Yes | Current open work is represented in the curated Open Actions sheet. | .agent_work/task-backlog.md
TASK-095 | Governance And AI-Ready Handoff Foundation | In progress; Phase B governance/handoff remains | Current board | IN_PROGRESS - W00 main-based direction aligned; prior Phase A remains complete and Phase B continues through handoff | July 23, 2026 | Phase A 1-2 days; Phase B 2-4 distributed days | 8 | Yes | Current open work is represented in the curated Open Actions sheet. | .agent_work/tasks/active/TASK-095-governance-ai-ready-handoff.md
TASK-096 | User-Initiated Exit And Container Stop | Deferred | Current backlog | No top-level task status | Not recorded in current task metadata | Not estimated in current task metadata | 0 | Yes | Current open work is represented in the curated Open Actions sheet. | .agent_work/task-backlog.md
TASK-097 | Podman CPU/GPU Final Path Qualification | At risk; independent Podman proof remains | Current board | AT_RISK - final `rc4` Podman CPU/GPU package paths pass on the first host, including provider workflows, TLS repair, cancellation recovery, exports, persistence, reboot restoration, and real CUDA execution; independent-host proof remains | Not recorded in current task metadata | Not estimated in current task metadata | 0 | Yes | Current open work is represented in the curated Open Actions sheet. | .agent_work/tasks/active/TASK-097-podman-final-path-qualification.md
TASK-098 | Dependency Security Remediation And Release Gate | Historical / completed; not current work unless reselected | Completed-task history | COMPLETED - PR #51 MERGED AS `e499b50`; POST-MERGE CI PASSED; DEPENDABOT RECONCILED TO EIGHT DOCUMENTED NON-BLOCKING TORCH ADVISORIES | Not recorded in current task metadata | Mandatory slices 4-8 days; full coordinated hardening 6-11 days, plus required GPU/runtime host availability | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/completed/TASK-098-dependency-security-remediation.md
TASK-099 | August Dependency Advisory Follow-Up | Completed current-sprint record; move at sprint closeout | Current board | COMPLETED | Not recorded in current task metadata | 0.5-1.5 days plus CI and Dependabot reconciliation | 0 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/active/TASK-099-august-dependency-advisory-follow-up.md
TASK-101 | extract-zip Advisory Assessment And Release-Gate Disposition | Completed; unchecked PR #67 items are superseded, not open | Current board | COMPLETED - PR #72 squash-merged as `0cc189c`, alert `#76` closed as fixed without dismissal, and exact-main CI passed August 19, 2026. ADR-021 supersedes the former downstream PR #67 integration gate; that gate did not pass and is not required for the main-based delivery. | August 19, 2026 | 1-2 days plus CI rerun timing | 3 | No | Unchecked boxes or old status text are historical residue and do not reopen the task. | .agent_work/tasks/active/TASK-101-extract-zip-advisory-release-gate.md
TASK-103 | CUDA 12.8 Blackwell ML Runtime | In progress; replacement package/browser/independent host remain | Current board | IN_PROGRESS - local `rc4` CPU/CUDA images and control ZIPs pass G10, W05, four-profile W09 setup/device/lifecycle, and the complete local W10 provider/cancel/error/review-export/relaunch/reboot matrix. ADR-023 resolves the unsigned support boundary; replacement packaged docs, browser-download validation, and independent-host evidence remain | Not recorded in current task metadata | Not estimated in current task metadata | 2 | Yes | Current open work is represented in the curated Open Actions sheet. | .agent_work/tasks/active/TASK-103-cuda128-blackwell-ml-runtime.md

## Raw Unchecked Items
Raw Unchecked Checklist Items
Traceability inventory across all requested task and status documentation. Use Authority and Included in Open Actions before treating any row as current work.
Source file | Line | Nearest heading | Unchecked item | Authority / lifecycle | Included in curated backlog | Disposition guidance
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 89 | Updating the board without duplicating work | Review each relevant task against actual Day-7 evidence; classify it as complete, remaining closeout work, conditional, deferred, or superseded. Do not restart completed slices because an old estimate lists the whole task. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 90 | Updating the board without duplicating work | Keep existing TASK identifiers. Use named child deliverables under 092/095 rather than inventing conflicting task numbers. Create a missing task file only when it is selected and assign its canonical location through the existing workflow. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 91 | Updating the board without duplicating work | Replace expired dates and PR #67 dependencies in active entrypoints. Preserve completed security work and distinguish superseded branch-integration gates from tests that actually passed. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 92 | Updating the board without duplicating work | For every selected item record owner, backup/reviewer, input evidence, deliverable path, due date, acceptance test and current blocker. A role without an assigned person is an unresolved assignment. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 93 | Updating the board without duplicating work | Reconcile `HANDOFF.md`, `.agent_work` board/backlog/status pointers, the current roadmap and the v2 instruction/skill corrections. Keep history dated; do not rewrite it to imply the new direction was always in force. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 94 | Updating the board without duplicating work | Run `python .agent_work/scripts/validate_agent_work.py` after tracking changes, inspect its exit status, and manually check links and conflicting directions. A validator pass does not establish semantic consistency. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 130 | Required content | Draft chapters from the actual v2 procedures and accepted candidate, linking existing maintained instructions instead of copying long command sequences into multiple manuals. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 131 | Required content | For each how-to include prerequisites/permissions, inputs, exact version-appropriate commands or UI steps, expected results, verification, failure/rollback steps and evidence location. Clearly label examples; no live credentials or invented digests. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 132 | Required content | Agree a realistic owner maintenance cadence: review support/security notifications during active use; periodically check access, backups and resource growth; rerun qualification for relevant release changes. Record the accepted cadence rather than promising unattended maintenance that does not exist. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 133 | Required content | Have the receiving owner and backup walk through the guide before October 16, then perform the critical procedures by October 23. Record unprompted completion, assistance required, corrections and remaining blockers. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 134 | Required content | Confirm ownership of external accounts, source media, guides and test fixtures; a successful document handoff without usable access is incomplete. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 148 | Required execution and acceptance | Map each common user journey to one primary guide: choose/download the right package, verify/extract/import assets, choose engine/device, configure providers, perform first detection, review/export, cancel/recover, stop/relaunch, obtain help. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 149 | Required execution and acceptance | Remove active PR #67 launcher assumptions and stale version/CUDA/package claims. State the actual supported profiles and prerequisites, including the approved Podman Compose-provider/Python requirement. Distinguish immutable pilot instructions from the new release. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 150 | Required execution and acceptance | Synchronize each Markdown/HTML pair manually; there is no maintained HTML-doc generator in the current workflow. `node webapp/build.js` regenerates JavaScript, not these guides. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 151 | Required execution and acceptance | Keep in-app instructions focused on user tasks and actionable recovery. Put maintainer responsibilities, source/build internals and backlog discussions in the owner's guide. Do not add an owner-guide route or new frontend framework just to deliver documentation. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 152 | Required execution and acceptance | Verify all three actual in-app Help links, navigation anchors, CSS and relevant downloads on the running candidate. The existing docs route rejects nested paths: a new `docs/maintenance/` page cannot be assumed available through `/docs/maintenance/`. Prefer repository links for owner-only material. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 153 | Required execution and acceptance | Test repository-rendered links separately from app-served HTML links. Root-relative `/docs/` URLs are intended for the running app and may not work by double-clicking an extracted HTML file; document supported viewing rather than claiming offline file viewing was tested when it was not. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 154 | Required execution and acceptance | Inspect the final ZIP and runtime image for the intended guide versions. If changing an allowlist or route, run the relevant assertions in `tests/unit/test_flask_routes.py` and `tests/unit/test_release_package_script.py`; extend only for an actual changed contract. A pure prose change needs link/rendering/workflow review, not artificial source-string tests. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 155 | Required execution and acceptance | Have an independent user follow the installation and in-app first-use guide without undocumented help. Record each point of confusion and resolve discrepancies before acceptance. Ensure the written guide remains usable without the video. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 171 | 7. Recreate the installation and demo clip | By October 2, write the script/shot list and choose a permitted demonstration area, neutral desktop/profile and recording location. Define the primary profile, version and which differences need inserts. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 172 | 7. Recreate the installation and demo clip | Dry-run by October 9 on the actual package workflow. Fix confusing instructions before final capture. Prepare placeholder/example screens for credential entry; never record private values in raw footage. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 173 | 7. Recreate the installation and demo clip | After freeze, record against the inventoried candidate, then add readable captions, transcript and chapter markers. Identify version/profile and qualify any shortened waits. If the final published identity changes, review every version/download reference and recapture affected portions. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 174 | 7. Recreate the installation and demo clip | Review every frame and the audio/captions for keys, personal paths, notifications, account details, private imagery and misleading steps. Check permitted use of imagery/music/assets. Keep necessary raw media in approved private storage. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 175 | 7. Recreate the installation and demo clip | Have an independent tester compare the clip to the written guide and repeat the demonstrated path. Verify the intended audience can access the approved hosting link without the outgoing developer's account. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 176 | 7. Recreate the installation and demo clip | Transfer the finished video, transcript/captions, editable project, permitted source assets and editing/hosting permissions to the receiving owner. Record custody in the owner's guide. Publish only under the applicable authorization. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 188 | Scope to record before scanning | **Early inventory, by October 2:** inventory path names and custody; identify tracked/untracked/ignored material, private fixtures, screenshots/traces, logs, certificates, keys, `.env` files, personal paths/contact details and undocumented external assets. Do not dump their contents into the chat or a public report. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 189 | Scope to record before scanning | **Use controlled scans:** scan the intended transfer set with approved tooling that redacts values and records path/category/status privately. Review history and artifacts separately from the current tree. A secret-like variable name or synthetic test key is not automatically a leaked credential; triage findings before changing tests/docs. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 190 | Scope to record before scanning | **Account for the existing scanner:** `.agents/skills/towerscout-secret-and-provider-key-safety/scripts/scan_for_sensitive_terms.py` recursively reads files including `.env`, prints matching line snippets, and returns 0 even when it finds matches. Do not run it on a live working directory into a shared transcript or interpret exit 0 as clean. Prefer an approved redacting scan of an isolated transfer copy with findings kept private. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 191 | Scope to record before scanning | **Remediate current content:** replace private examples with synthetic data, remove accidental sensitive artifacts from the intended public set, correct ignore/allowlist rules and verify tests/docs still work. Ignoring a file does not remove it from Git history. Preserve license notices, attribution, required lockfiles and asset provenance. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 192 | Scope to record before scanning | **Handle actual credentials distinctly:** notify the authorized owner through the approved process and arrange revocation/rotation; removing a visible string does not invalidate an exposed credential. Record confirmation without recording the value. For historical exposure, prepare a scoped remediation proposal; history rewriting, force pushes and destructive branch deletion require explicit coordination/authorization and are not routine cleanup. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 193 | Scope to record before scanning | **Preserve evidence:** retain unique PR #67/release/test evidence in the appropriate controlled archive; publish a sanitized summary/pointer where suitable. Do not delete untracked qualification evidence, user data or parent-folder documents because they appear temporary. If archiving requires a move, verify exact resolved paths, reparse points, intended boundaries and destination copies/hashes first. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 194 | Scope to record before scanning | **Candidate pass, by October 16:** inspect the source transfer set, actual ZIPs, relevant image contents/layers and approved media/report outputs. Confirm private configuration, raw traces, recordings and model payloads are absent from places they should not be distributed. Check all newly added guide examples. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 195 | Scope to record before scanning | **Final delta pass, by October 30:** repeat the scoped review for changes since the candidate pass; verify the sanitized destination material and intended audience access. Record reviewed revisions/artifacts, methods, finding categories, dispositions, exclusions and reviewer. Do not claim inaccessible/unreviewed history or external assets were checked. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 203 | 9. Create a useful post-handoff backlog | Draft `docs/maintenance/post-handoff-backlog.md` by October 2 using existing TASK IDs and links to retained context. Keep `.agent_work/task-backlog.md` authoritative during current execution; clearly label the owner-facing draft as a proposed successor so there are not two live assignment boards. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 204 | 9. Create a useful post-handoff backlog | For each carried item include: ID/title; observed problem and affected profiles; user impact; reproduction/evidence reference; existing workaround; severity and suggested priority; recommended next action; dependencies/entry criteria; acceptance checks; risks; rough effort confidence; proposed responsible role; and last-reviewed date. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 205 | 9. Create a useful post-handoff backlog | Keep resolved items out of the active future queue, with links to completion evidence where useful. Explain why deferred architecture work is deferred. Sensitive findings go through the owner's private process; use a sanitized public summary when appropriate. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 206 | 9. Create a useful post-handoff backlog | Seed the first maintenance review with continuing dependency/provider monitoring, periodic access/backup/qualification checks, measured performance issues, and any outstanding support findings. Carry Tasks 026/027/068/070/076/077/094 only to the extent that work remains. Tasks 058/059/060/061/078/029/028 remain optional decisions with explicit justification gates; PR #67 has no automatic restart date. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 207 | 9. Create a useful post-handoff backlog | Review with the receiving owner by October 23. Agree the first 30/60/90-day priorities without committing staff/time that have not been allocated. If the owner prefers GitHub Issues, migrate through an approved scoped process and choose that destination as canonical; do not maintain duplicate independently edited copies. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 208 | 9. Create a useful post-handoff backlog | By October 30, switch `HANDOFF.md`, the owner's guide and task/instruction entrypoints to the agreed canonical maintenance backlog. Archive the dated outgoing board or leave a clear read-only pointer. Verify all links and preserve task-ID history. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 214 | 10. Closeout checklist and rules for the executing agent | Reconcile Day-7 outcomes and selected backlog work; no leftover release gate is hidden in the post-handoff queue. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 215 | 10. Closeout checklist and rules for the executing agent | All six requested additions have evidence: replacement video, owner's guide, post-handoff backlog, repository sanitization, public-facing guides and in-app guides. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 216 | 10. Closeout checklist and rules for the executing agent | Shipped guides match the final accepted artifacts; any later package/image change has a new identity and affected checks rerun. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 217 | 10. Closeout checklist and rules for the executing agent | Primary and backup owners have demonstrated needed access and critical operating procedures. Open adoption decisions have a named owner and explicit next action. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 218 | 10. Closeout checklist and rules for the executing agent | A sanitized custody index identifies source, image/ZIP hashes, model/fixture provenance, qualification evidence, guide/video versions and storage locations. Private credentials remain outside it. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 219 | 10. Closeout checklist and rules for the executing agent | Current task/instruction/skill entrypoints agree with the main-based direction; old PR #67 gates and expired dates do not control new agents. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | 220 | 10. Closeout checklist and rules for the executing agent | Final sign-off identifies completed acceptance, known limitations, approved residuals and the canonical maintenance backlog. If adoption remains unapproved, deliver the migration-ready packet without changing cdcai. | Current suggested closeout guide | Yes | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 113 | W00 - Establish one direction and correct agent entrypoints | Inventory status, worktrees, branches and untracked path names. Record assessed main and PR #67 head `93d22f2ce0551defb79c852e0e879947cc611521` as historical references; verify the PR head again only if actually dispositioning it. Preserve unique work before any later archive. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 114 | W00 - Establish one direction and correct agent entrypoints | Add the short current-direction text below to the existing handoff/board and link this pair. Do not duplicate the complete plan into each file. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 124 | W00 - Establish one direction and correct agent entrypoints | Record the decision and its consequences. Recommend closing PR #67 unmerged under the applicable authorization; preparing the local decision does not require changing GitHub first. Preserve its commits/review evidence. Do not describe it as unrelated Git history: a common ancestor exists. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 125 | W00 - Establish one direction and correct agent entrypoints | Correct all repeated PR #67 merge/resume directives in `.github/copilot-instructions.md`, not only its first paragraph. Replace the single GPU-package assumption with the two-image CPU/CUDA contract. Update active Task-101's obsolete PR integration gate without claiming that gate passed. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 126 | W00 - Establish one direction and correct agent entrypoints | Keep completed security work completed, mark deferred launcher/UI/governance work accurately, and map current implementation to existing Tasks 091/092/093/097 and relevant owners. Task-097 acceptance must not depend on Task-087 or a new Task-096 Exit UI. Do not mark deferred tasks completed merely to satisfy a validator. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 127 | W00 - Establish one direction and correct agent entrypoints | Replace the blanket instruction to seek approval before every IMPLEMENT step with honoring the current session's authorized plan/scope. Preserve genuine external-action and scope-change boundaries. Replace requests for unabridged logs with sanitized evidence and private raw-log custody. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 128 | W00 - Establish one direction and correct agent entrypoints | Apply the release-critical skill corrections in section 4 now: wrong flags/paths, unowned cleanup, bypass-as-proof, and misleading qualification claims. Leave cosmetic rewrites alone. Create a short root `AGENTS.md` pointer, at most about 30 lines, linking the current board, v2 pair, and skill router; retain one authoritative instruction source for each subject. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 129 | W00 - Establish one direction and correct agent entrypoints | Run the strict validator and search active entrypoints for remaining conflicting direction. Historical documents may mention PR #67; a raw match is not automatically an error. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 144 | W01 - Attempt the baseline package and establish feasibility immediately | Reserve one CPU-only host and two different NVIDIA hosts where possible. Repeat CPU profiles on two suitable hosts, and GPU profiles on both NVIDIA hosts. Include a Podman installation without Docker Desktop. Record Windows build, RAM, free disk, GPU/VRAM/driver, WSL, engine/provider versions, Python prerequisite, endpoint policy, and anonymous host IDs. Unconfirmed access is a blocker, not an assumed resource. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 145 | W01 - Attempt the baseline package and establish feasibility immediately | Assign an owner to asset/model access, approved Google/Azure accounts, TLS certificates, signing if policy requires it, builds, and independent testing. Confirm whether downloaded unsigned scripts can run under the claimed policy. The target may require organization-approved signing; determine this before building final ZIPs. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 146 | W01 - Attempt the baseline package and establish feasibility immediately | Select a new baseline candidate identifier and accepted main SHA. Obtain/build its CPU and CUDA images using the existing workflow and authorized publication route. Pin image digests; do not reuse a mutable tag or call an old `v0.1.2` ZIP evidence for current main. If builds consume Day 1, record the delay and perform the first package attempt as soon as available. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 147 | W01 - Attempt the baseline package and establish feasibility immediately | Locate the authorized asset ZIP, confirm its SHA256 and model contract, and build a real control ZIP using W09's existing package arguments. Record that packaging does not create the asset ZIP. Fail asset provenance early instead of secretly mounting the developer's models. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 148 | W01 - Attempt the baseline package and establish feasibility immediately | Download and extract to a user-writable path containing spaces. On an ordinary account, attempt setup immediately using explicit engine/GPU flags. Capture actual error category, command/exit status, and time to health/model-ready/first result. Do not use `-SkipAssetImport`, a source build, or developer-populated volumes as fresh-user proof. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 164 | Run from the extracted control package, not the source checkout. | Freeze a small permitted fixed-image set with hashes and settings. Confirm that at least one image produces a real YOLO candidate in the existing EN confidence band; do not alter thresholds to manufacture that result. Record YOLO-only and combined expected outputs separately. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 165 | Run from the extracted control package, not the source checkout. | Before candidate results, declare tolerances from repeated baseline runs: counts, normalized boxes, confidences/EN scores, and ordering treatment. Sort corresponding detections deterministically for comparison; do not hide missing detections with loose tolerances. Keep CPU and CUDA baselines distinct if measured numeric variation requires it. If no stable permitted fixture exercises EN, W05 remains blocked until one is obtained. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 166 | Run from the extracted control package, not the source checkout. | Measure cold startup/model load and one warm-up plus three measured warm runs on the same host/settings. Record median time, peak host/container memory, GPU memory, workload size, and errors. Synchronize CUDA before/after measured inference. Flag more than 10% warmed-median slowdown for explanation/retest, not immediate speculative optimization. No supported minimum hardware claim until the smallest claimed host passes. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 176 | W02 - Remove the disabled host-helper dependency | Reproduce with a temporary copy of the necessary scripts and fake engine commands: remove the helper module in the copy, leave the helper disabled, and run launch/stop under `powershell.exe`. Assert no helper file access/profile creation and no missing-module failure. Cover both failing preflight and successful fake preflight followed by a controlled fake Compose failure, so execution reaches the profile-write location without starting a real container. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 177 | W02 - Remove the disabled host-helper dependency | Gate the helper import and `Save-TowerScoutHostHelperLaunchProfile` call using the actual existing enablement condition. The current launch import is unconditional; stop also imports outside its guarded cleanup. Keep the condition and imports close to their call sites. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 178 | W02 - Remove the disabled host-helper dependency | Exercise enabled-path behavior with a fake helper in the sandbox, plus disabled-path launch/stop on a real package during W09. Assert scalar nonzero engine failures remain nonzero. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 192 | W03 - Repair existing process boundaries and bind the runtime target | Inspect the current adapters before reusing them. The Podman/bootstrap process paths wait before draining redirected output; enough output can deadlock. The GPU adapter ignores its declared timeout, and engine/provider/Compose probes still have raw unbounded native calls. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 193 | W03 - Repair existing process boundaries and bind the runtime target | Extend `test_windows_runtime_behavior.py` with owned fake children: stdout and stderr each exceed pipe capacity; child returns 7 after output; child hangs; child spawns a hanging grandchild; executable/path/arguments contain spaces; arguments include an empty string and a trailing backslash. Compare received arguments exactly and assert bounded completion, exit-status propagation, and cleanup of only owned PIDs. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 194 | W03 - Repair existing process boundaries and bind the runtime target | Include the real approved provider shape: a `.cmd` wrapper invokes `.venv\Scripts\podman-compose.exe` with `%*`. Do not assume `System.Diagnostics.Process` can directly execute a CMD wrapper with `UseShellExecute=false`. Implement/reuse a separately tested batch invocation path; reject ambiguous quoting rather than concatenating unchecked shell text. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 195 | W03 - Repair existing process boundaries and bind the runtime target | Repair the existing adapters to drain both streams while running and keep bounded retained output. Use asynchronous reads or the existing compatible mechanism with verified Windows PowerShell 5.1 behavior; continue draining after the retention cap. Starting `ReadToEndAsync` alone removes the pipe stall but does not bound retained memory. Avoid PowerShell event callbacks on threads without a runspace. Do not wait for exit before starting the reads. Capture final status once, terminate the owned process tree on expiry, then bound cleanup/drain time too. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 196 | W03 - Repair existing process boundaries and bind the runtime target | Preserve the existing 30-second short-probe default where applicable. Distinguish short readiness probes from image pulls/imports/builds, which need a larger configured outer deadline and progress. Do not impose a 15/30-second limit on a large download. Treat `logs -Follow` as streaming interactive behavior, not a hung probe. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 197 | W03 - Repair existing process boundaries and bind the runtime target | Route the currently unbounded engine `info`, provider-version, Podman Compose-version and GPU-discovery calls through corrected boundaries. Audit error consumers so timeout/nonzero does not become an empty success or a fallback to another engine. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 198 | W03 - Repair existing process boundaries and bind the runtime target | On setup, resolve and record the explicit engine, package root/project, and for Podman the selected machine, connection, and rootful/rootless mode. Use existing configuration where possible; if it cannot hold that binding, add a small versioned target record to package state, without credentials. Validate the record before mutation. Do not create a ten-script profile/discovery subsystem. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 199 | W03 - Repair existing process boundaries and bind the runtime target | Invoke Podman operations with the selected connection/machine explicitly where supported. If a Compose provider cannot select that target, compare its effective target to the recorded one and fail before mutation on mismatch. An informative warning is insufficient. Never silently switch the user's global connection/default machine/rootful mode. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 200 | W03 - Repair existing process boundaries and bind the runtime target | Add fake-command sequence assertions: both engines installed but explicit Podman chosen; current default points elsewhere; selected machine missing/stopped; connection changed in a new shell. On mismatch assert zero `up`, `down`, import, repair, or stop calls. On matching target assert lifecycle operations use that target. Test actual non-default connection behavior on Podman in W09. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 212 | W04 - Make TLS repair transactional enough to preserve working trust | Add a fake import command that writes two diagnostic lines and exits 7. Through the repair wrapper assert exactly integer 7 is interpreted as status and the outer process fails. Repeat exit 0 and paths with spaces under Windows PowerShell 5.1. This regression addresses output captured together with a returned exit code. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 213 | W04 - Make TLS repair transactional enough to preserve working trust | Keep diagnostics on the host stream and return only the captured scalar status in `Invoke-TowerScoutImport`: | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 221 | W04 - Make TLS repair transactional enough to preserve working trust | Use a uniquely named candidate certificate/bundle. Copy/build it using existing container-copy and verification helpers, then verify the selected provider against that candidate before touching active `.env` values. `VerifyProvider none` is not acceptance evidence. A candidate failure must leave the existing bundle and environment bytes unchanged. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 222 | W04 - Make TLS repair transactional enough to preserve working trust | Protect the short repair transaction using one package-scoped exclusive lock or equivalent; a second repair reports busy without changing either candidate's active state. Re-read/check the original environment bytes before promotion to detect an unrelated concurrent edit. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 223 | W04 - Make TLS repair transactional enough to preserve working trust | Update only `REQUESTS_CA_BUNDLE` and `SSL_CERT_FILE` after successful verification. Preserve unrelated keys, comments, encoding and line endings; reject duplicate active keys rather than guessing. Write a same-directory temporary file and atomically replace/rename as supported, keeping a rollback copy only for the bounded transaction and removing it afterward. Do not create a persistent full `.env` backup or a general recovery journal. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 224 | W04 - Make TLS repair transactional enough to preserve working trust | Leave the previously working bundle available until adoption is confirmed. If promotion fails, keep prior configuration; if restart/adoption fails, report that state and retain the previous paths for explicit rollback. Do not claim automatic running-container adoption just because `.env` was updated. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 225 | W04 - Make TLS repair transactional enough to preserve working trust | Fault cases: missing certificate; nonzero copy/build; invalid candidate; verification timeout; denied environment write; changed environment during transaction; second simultaneous repair; interruption before promotion; failed restart after promotion. Assert original bytes/paths and bundle usability where promotion has not succeeded, not just an error string. Run a successful repair and subsequent recovery using approved certificates on a qualified host. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 254 | W05 - Extend existing external qualification; do not build a new product self-test | Freeze a manifest with `schema_version: 1`, `required_device` (`cpu` or `cuda`), `tiles` (objects with `path` and `sha256`), `model_sha256` (keys `yolo` and `en`), `expected_detections` (one list per input tile using the detector's result fields), and `tolerances` (keys `box_abs`, `confidence_abs`, `secondary_abs`). Require exact per-tile count and class correspondence; compare the named numeric fields after deterministic ordering. Store baseline source and image in `baseline_identity`. Keep profile-specific manifests explicit. Validate paths stay inside the fixture root; reject missing/hash-mismatched files. Populate these data from W01, never from the candidate's own output. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 255 | W05 - Extend existing external qualification; do not build a new product self-test | Extend the existing Python probe with the optional combined mode, preserving its original synthetic checks. Load actual `/app/webapp/model_params/yolov5/newest.pt` and `/app/webapp/model_params/EN/b5_unweighted_best.pt` through `YOLOv5_Detector(str(yolo_path))` and `EN_Classifier()` and their trusted loading. Use `ExitEvents()` and `PerformanceMetrics(run_id)`, allocating/freeing the event in `try/finally`. Build each tile as `{"filename": str(validated_tile_path)}`. Validate manifests before imports/loads; the existing module imports may need to move behind argument/device setup. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 269 | Core call inside the new mode after manifest/hash/device validation. | Record `model_device`, `secondary_classifier_device`, `secondary_classifier_candidate_count`, and `secondary_classifier_batches` from the actual run. Require positive secondary candidates and batches. Inspect actual model parameter/input devices at forward execution using narrowly scoped instrumentation/hooks if existing telemetry only proves configured labels; remove hooks afterward. Require both observed devices to match the requested profile. Do not replace inference with fabricated detections in this combined mode. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 270 | Core call inside the new mode after manifest/hash/device validation. | Use one warm-up and three measured warm runs; create fresh per-run metrics/detection input objects because classification appends scores. Synchronize CUDA for timing. Compare actual output to the manifest, recording separate YOLO-only historical parity if run. Enforce every mandatory check; never emit `passed: true` merely because inference returned. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 271 | Core call inside the new mode after manifest/hash/device validation. | Extend the existing report with a versioned combined section: tool/fixture/model hashes, required/observed devices, candidate/batch counts, per-run outputs and comparisons, timing/memory, individual check results, and overall pass. The outer runner records inspected image digest, package hashes and source identity; an environment variable containing an expected identity is not independent proof of it. Missing fields fail report validation. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 272 | Core call inside the new mode after manifest/hash/device validation. | Implement the thin external runner using the extracted package's Compose library/configuration and W03 target checks. Use the exact pinned image and the assets actually imported by setup. Mount the operator probe/fixtures read-only and its dedicated evidence directory writable. Do not mount the developer's model directory or rebuild an image. Do not call the legacy `_startup_probe` during combined mode: importing the full app in another process can load another model copy; measure actual app startup separately. Keep fixtures/probe out of the release-image payload. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 273 | Core call inside the new mode after manifest/hash/device validation. | Rehearse the existing providers' `compose run --rm --no-deps --entrypoint python` path early. Add only the required volume/environment arguments with array-based quoting. Stop only the test-owned service before a separate probe loads both models, to avoid a second full GPU model allocation; relaunch that service afterward. Reuse the intended named asset volumes without deleting or recreating them. If provider semantics differ, fix that bounded invocation and test both engines rather than assuming Docker behavior on Podman. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 274 | Core call inside the new mode after manifest/hash/device validation. | Adapt the copied HTTP harness: `SkipLive` must avoid all provider calls including geocoding; required live failures must affect the process exit code; assertions must check terminal success/results/export, not just HTTP 200; selected-device readiness remains informational. Keep upload pacing within its legitimate per-operation quota after W07; remove only workarounds for unrelated map traffic consuming the upload quota. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 275 | Core call inside the new mode after manifest/hash/device validation. | Add report-contract tests with complete synthetic report objects: reject wrong device, zero EN candidates/batches, changed model/fixture/image identity, missing comparison results, output outside tolerance and child nonzero status. These tests validate the evaluator, not actual models. Retain legacy no-argument mode coverage. Then run the new probe outside pytest on CPU and CUDA; mocked pytest loading is not real-model evidence. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 285 | W06 - Propagate classifier failure and reject excessive allocation early | Add this regression to the existing secondary-metrics module, which already provides `_FakeModel` and `_FakeEvents`; add the shown imports. Run it before fixing both exception layers. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 315 | W06 - Propagate classifier failure and reject excessive allocation early | Replace the secondary catch-and-continue with a typed failure and propagate it through the outer per-tile/batch catch. Preserve `operation="secondary_classifier"`; do not overwrite it with a generic operation during wrapping. Preserve recognized resource/OOM handling without allocating enough real memory to crash the test host. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 316 | W06 - Propagate classifier failure and reject excessive allocation early | Add success/YOLO-only/noncandidate/OOM cases using the existing fakes. Preserve the current CUDA guard through tensor conversion and its release before secondary work; existing guard tests must still pass. Through the map route assert an error response and successful next request, not a partial successful result. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 320 | W06 - Propagate classifier failure and reject excessive allocation early | Extend the signature to `Map.make_tiles(self, bounds, overlap_percent=5, crop_tiles=False, max_candidate_tiles=None)`. Existing non-request callers retain compatibility; every production request caller passes the validator's candidate budget. After computing `nx`/`ny`, reject their product above that cap before constructing the tile list or making provider calls. Preserve current return tuple and geometry. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 321 | W06 - Propagate classifier failure and reject excessive allocation early | Raise `ts_validation.ValidationError("Selected area exceeds the candidate tile limit. Select a smaller area.", field="bounds")`, matching the existing route handling; `ts_errors.ValidationError` has a different constructor and is not an interchangeable import. Pass the same candidate budget through `_build_tiles_for_request`, `estimate_detection_tiles`, and `_run_detection_request`; enforce it before model initialization. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 322 | W06 - Propagate classifier failure and reject excessive allocation early | At uploaded-image open, validate dimensions/pixel product before full decode, conversion, copying, or model execution. Convert Pillow decompression-bomb conditions to the existing validation response. Preserve the body limit. The error should tell the user to choose a smaller area/image without exposing server paths. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 323 | W06 - Propagate classifier failure and reject excessive allocation early | Test candidate cap and cap+1 using small configured test limits and spies that assert zero enumeration/provider/model calls on rejection. Test a narrow polygon over a huge bounding grid, not only a large retained result. Test image pixel/edge equality and one above, corrupt headers, and a compressed large-dimension fixture without allocating a huge image in the test process. Confirm an ordinary accepted image/map retains existing output. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 344 | Call-site pattern; retain that route's existing numeric quota/window. | Add route tests that perform enough allowed map fetches to exceed the custom route's smaller quota, then assert the first valid custom request is still accepted. Assert its own 11th request in the same 60-second window is rejected; verify unrelated operation windows do not prune each other's histories. Use a controlled clock, synthetic provider/images/models and fresh limiter; do not mock `is_allowed` to always return true. Preserve bounded key count and concurrent-limit tests. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 345 | Call-site pattern; retain that route's existing numeric quota/window. | Audit every `rate_limiter.is_allowed` call and assign the same stable key to equivalent work. Validate provider/service before including them in the scope. Avoid a new generic rate-limit framework. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 366 | Module-level lock; import threading if not already imported. | Use `threading.Event` barriers in a test worker with its own Flask test client to hold the first map request inside a fake detector. Issue a second map/custom request with another client; assert 429/`DETECTION_BUSY`, no second detector call and no progress/event/session overwrite. Release the barrier and assert success. Repeat first-job failure and cancellation; assert a following request acquires the lock and succeeds. Avoid arbitrary sleeps and shared test clients across threads. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 367 | Module-level lock; import threading if not already imported. | Allocate a cancellation event before exposing its progress record, closing the current early-cancel race. Exercise cancellation during download, during inference boundaries, and immediately before final result publication; inspect actual behavior before larger edits. Native model calls may finish their current batch before cancellation is observed; document measured bounds instead of promising immediate interruption. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 368 | Module-level lock; import threading if not already imported. | Assert interrupted/failed work does not publish partial results or leave session metadata pointing to deleted files. Preserve successful tile/result files needed for review/export. If late cancellation reveals current metadata writes occurring before terminal success, stage only those new fields until the success decision; do not rewrite the whole session architecture or attempt to restore files already removed by unrelated operations. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 369 | Module-level lock; import threading if not already imported. | Exercise slow/broken provider and missing-response scenarios. Existing aiohttp timeouts are not a single guaranteed whole-job deadline across retry waves. Record actual cancellation/deadline behavior. If acceptance fails, make the smallest bounded cancellation fix, explicitly await owned tasks before closing the event loop, and handle `asyncio.CancelledError` intentionally; a generic `except Exception` may not catch it. Keep ordinary network error classifications distinct from cancellation. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 381 | W08 - Correct Google first-use bounds and regenerate the bundle | Reproduce Google detection on first use with no drawn boundary. In `buildDetectionPayload`, bounds are currently read before adding the viewport boundary; Google can return an invalid empty union. Assert the outgoing payload has valid viewport bounds on the first click, not only after a retry. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 382 | W08 - Correct Google first-use bounds and regenerate the bundle | Select/create the fallback viewport boundary before reading request bounds, using the existing provider contract. Preserve explicit user polygons and selection state; do not switch providers or silently use stale bounds. Retain Azure's working viewport behavior. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 383 | W08 - Correct Google first-use bounds and regenerate the bundle | Add deterministic cases for Google empty-boundary first use, explicit Google polygon, Azure empty-boundary behavior, and provider switch. Verify bounds numerically and assert no duplicate boundary addition on repeat submission. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 384 | W08 - Correct Google first-use bounds and regenerate the bundle | Rebuild the checked-in JavaScript bundle and run focused contracts. Then run authorized real Google/Azure smoke, including cancellation, using a sanitized fixture and the test's existing supported options (`--provider=google` or `--provider=azure`, `--fixture=path`, `--base-url=url`, `--browser-path=path`, `--cancel-smoke`). The value-bearing options require the equals-sign form. Do not print a private local fixture or network trace to discover its secrets. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 402 | W09 - Freeze, build and verify exact downloadable artifacts | Finish the first consolidated review by Day 3, focused on process/target boundaries, TLS preservation, model errors, admission and harness truthfulness. Resolve release blockers; defer unrelated refactoring. Freeze an accepted source commit before final image builds. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 403 | W09 - Freeze, build and verify exact downloadable artifacts | Use the existing image workflow's `pytorch_flavor` values `cpu` and `cuda126`, with explicit candidate tag and `push_latest` disabled. Registry pushes are publication actions. Record actual resolved digest for each variant and confirm its source label, dependency versions and expected flavor; a tag string is insufficient. Local-only rehearsal is useful but does not establish another computer can download the image. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 404 | W09 - Freeze, build and verify exact downloadable artifacts | Set package variables from the actual inventory: `$releaseId`, `$packageOutputRoot`, `$cpuImageReference`, `$cpuDigest`, `$cudaImageReference`, `$cudaDigest`, `$assetBundleVersion`, `$assetZipSha256`. Set `$packageOutputRoot` to a new directory under ignored `dist/`, such as `dist/$releaseId`, so the CPU output cannot dirty the tracked worktree before the CUDA package clean-tree check. Each image digest must be `sha256:` plus 64 lowercase hex characters; asset SHA256 is 64 hex characters, optionally prefixed `sha256:`. Keep CPU and CUDA output identities distinct. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 420 | W09 - Freeze, build and verify exact downloadable artifacts | Inspect the explicit package file allowlist. Include any new runtime file needed by W03/W04 and all required guides/notices. External qualification tools need not be user-package contents. Inspect a real ZIP: sidecar SHA256, internal `SHA256SUMS`, release manifest, CPU/CUDA flavor/digest, asset contract and actual scripts/docs. Reject `.env`, credentials, private evidence, model payloads in the control ZIP, unrelated developer state and unexpected executables. Warning-only helper output is not a blocking gate unless the caller enforces its result. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 421 | W09 - Freeze, build and verify exact downloadable artifacts | Execute package scripts on Windows PowerShell 5.1 from a spaced path, including unavailable engine/provider, a noisy/hanging child, helper-off launch, scalar TLS failure and matching/mismatched Podman target. Rehearse Docker and actual approved Podman provider setup/import/status/logs/stop/relaunch. Reopen a fresh shell before lifecycle checks. Never run unconditional `compose down` against an unverified project. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 422 | W09 - Freeze, build and verify exact downloadable artifacts | Run focused artifact tests and the repository's existing required checks for touched areas. New meaningful Windows tests must run on Windows and report their result; platform-skipped CI does not satisfy them. No wholesale audit suppression, lint reformat, or dependency update to obtain green output. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 428 | W09 - Freeze, build and verify exact downloadable artifacts | Run baseline-versus-candidate W05 comparisons on the same host with frozen inputs, then complete the user-manual changes in section 5. Record any >10% warmed-median slowdown and determine whether it is repeatable/caused by the fix. Do not relax model correctness to recover speed. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 429 | W09 - Freeze, build and verify exact downloadable artifacts | Freeze distribution bytes and make exactly those downloads available to authorized independent testers. If code, signed bytes, image, package, model, or fixtures change later, issue a new identity and rerun affected gates; explain unaffected evidence rather than copying a blanket pass. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 437 | W10 - Reproduce the installation and hand over evidence | For each profile, record first host and independent repeat host, artifact/download hashes, image digest, model/fixture/tool hashes, versions, declared settings, result and evidence reference. Example allocation: Docker CPU and Podman CPU on `cpu-a` plus explicit-CPU `gpu-a`; Docker NVIDIA and Podman NVIDIA on `gpu-a` plus `gpu-b`. Isolate projects/ports and do not run competing profiles simultaneously when that distorts resource measurements. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 438 | W10 - Reproduce the installation and hand over evidence | A tester follows only the shipped instructions on an ordinary account: download, verify, extract, setup with asset import, open UI, configure authorized provider, perform real map detection, review and export. No source checkout, developer model mount, preloaded application volumes, or undocumented manual repair is allowed in a fresh-install pass. Existing engine prerequisites can be installed through the documented approved procedure. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 439 | W10 - Reproduce the installation and hand over evidence | In every profile, run the external fixed combined probe, then the live Google/Azure workflow in the actual app process. Record both model devices and positive EN work for the fixed case, expected output comparisons, startup/warm performance and memory. Provider-dependent live counts may vary; assert valid terminal outcome/review/export rather than forcing the historical count 53. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 440 | W10 - Reproduce the installation and hand over evidence | On each host/profile exercise cancellation, a controlled recoverable error, and next-request success; stop/relaunch from a new shell and reboot. Confirm intended engine/target, assets, provider setup, sessions and export inputs persist. An explicit GPU-required run with CUDA unavailable must fail clearly rather than become a CPU pass. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 441 | W10 - Reproduce the installation and hand over evidence | Exhaustively inject shared-script failures once per relevant engine and smoke-check the remaining profiles: interrupted import/pull where safe, port occupied, missing provider/Python, wrong Podman target, TLS failure/repair, failed restart. Use test-owned state and approved synthetic/organizational certificates. If an engine-specific failure is found, repeat its fix across affected profiles. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 442 | W10 - Reproduce the installation and hand over evidence | Exercise instructions on the actual claimed endpoint/network policy, including approved proxy/CA setup. For the ADR-023 standard scope, exercise the unsigned wrapper path from a browser-downloaded ZIP under an ordinary account; do not present process-scoped `ExecutionPolicy Bypass` as proof for a signature-enforcing managed endpoint. Record those endpoints as outside the support claim unless a future, separately qualified signing path is adopted. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 448 | W10 - Reproduce the installation and hand over evidence | Perform the second consolidated review on Day 7: reconcile every matrix cell with the final identities; inspect skips, absent hosts, hidden manual steps, keys/redaction, output comparisons and performance regressions. Resolve blocker findings or report the precise qualified subset and remaining owners/actions. Do not release under the full four-profile claim with incomplete cells. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 449 | W10 - Reproduce the installation and hand over evidence | Prepare the handoff: exact download references/hashes, supported prerequisites, four explicit setup command variants, troubleshooting/status/logs/TLS recovery, stop/relaunch and volume-preserving rollback, evidence custody, known limitations, and deferred backlog. Check that an independent tester can follow it. Publish/close the PR/update external repositories only within applicable authorization; local preparation can be completed beforehand. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 538 | 7. Agent completion checklist | W00-W10 evidence agrees with the v2 spec and the current board; no old v1 tasks were added merely because their files remain present. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 539 | 7. Agent completion checklist | No PR #67 dependency, silent CPU fallback, mocked real-model pass, unowned cleanup, bypass-based endpoint claim or unverified candidate identity remains in the claimed outcome. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 540 | 7. Agent completion checklist | Actual Windows 5.1/package/provider behavior, both model devices and independent-host repetition are documented; required skips are not passes. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 541 | 7. Agent completion checklist | Final public docs, instruction entrypoints and skill commands agree with the tested direction; historical records remain distinguishable. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | 542 | 7. Agent completion checklist | Final report lists tested artifacts/profiles, performance comparison, outstanding limits/blockers and next owner/action. It never says deployment-ready solely because static review or unit tests passed. | Current controlling work plan | Partial | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/tasks/active/TASK-089-cdcai-migration-execution.md | 106 | Acceptance Criteria | A migration-ready handoff packet records the candidate source ref, selected tags, image/package choices, evidence, backlog, and verification sequence without executing them against cdcai. | Current task detail | Yes | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-089-cdcai-migration-execution.md | 109 | Acceptance Criteria | The cdcai owner explicitly approves the adoption baseline after feedback. | Current task detail | Yes | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-089-cdcai-migration-execution.md | 110 | Acceptance Criteria | cdcai collaborator write and package-publish ownership are confirmed for the approved execution window. | Current task detail | Yes | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-089-cdcai-migration-execution.md | 112 | Acceptance Criteria | The selected stable history and tags are pushed without force or bulk-tag mistakes. | Current task detail | Yes | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-089-cdcai-migration-execution.md | 114 | Acceptance Criteria | `ghcr.io/cdcai/towerscout` publishes the intended stable images and the visibility/linkage requirements are satisfied. | Current task detail | Yes | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-089-cdcai-migration-execution.md | 116 | Acceptance Criteria | The cdcai-side stable release is recreated from validated artifacts. | Current task detail | Yes | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-089-cdcai-migration-execution.md | 117 | Acceptance Criteria | Post-transfer verification confirms clone, pull, package, and source-ref integrity. | Current task detail | Yes | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-089-cdcai-migration-execution.md | 119 | Acceptance Criteria | The chosen cdcai package-facing release URL and image-default strategy is explicitly recorded and, if fork-facing values remain in the tagged tree, disclosed in the cdcai release notes. | Current task detail | Yes | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-089-cdcai-migration-execution.md | 122 | Acceptance Criteria | The selected cdcai migration tag/image set excludes the historical asset-less `v0.1.0` and `v0.1.1` tags and instead uses the validated owner-approved baseline (`v0.1.2` or a later validated successor). | Current task detail | Yes | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-089-cdcai-migration-execution.md | 125 | Acceptance Criteria | Backlog transfer lands in cdcai Issues or an explicitly approved alternate durable destination. | Current task detail | Yes | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-089-cdcai-migration-execution.md | 360 | Acceptance Criteria Validation | **Migration-ready handoff packet completed**: Pending | Current task detail | Yes | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-089-cdcai-migration-execution.md | 361 | Acceptance Criteria Validation | **Adoption baseline approved**: Pending feedback review | Current task detail | Yes | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-089-cdcai-migration-execution.md | 362 | Acceptance Criteria Validation | **Execution permissions confirmed**: Pending approved execution window | Current task detail | Yes | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-089-cdcai-migration-execution.md | 363 | Acceptance Criteria Validation | **History and tags pushed safely**: Pending | Current task detail | Yes | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-089-cdcai-migration-execution.md | 364 | Acceptance Criteria Validation | **cdcai GHCR publication complete**: Pending | Current task detail | Yes | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-089-cdcai-migration-execution.md | 365 | Acceptance Criteria Validation | **cdcai release recreated**: Pending | Current task detail | Yes | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-089-cdcai-migration-execution.md | 366 | Acceptance Criteria Validation | **Post-transfer verification complete**: Pending | Current task detail | Yes | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-089-cdcai-migration-execution.md | 367 | Acceptance Criteria Validation | **Backlog transfer destination completed**: Pending | Current task detail | Yes | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-095-governance-ai-ready-handoff.md | 60 | Acceptance Criteria | Keep task disposition and milestone status current through freeze. | Current task detail | Yes | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-095-governance-ai-ready-handoff.md | 61 | Acceptance Criteria | Maintain a prioritized, owner-readable Markdown backlog. | Current task detail | Yes | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-095-governance-ai-ready-handoff.md | 62 | Acceptance Criteria | Document tool-neutral task planning, implementation, validation, release, rollback, and maintenance procedures. | Current task detail | Yes | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-095-governance-ai-ready-handoff.md | 64 | Acceptance Criteria | Record optional AI-assisted workflows without requiring a particular vendor or tool. | Current task detail | Yes | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-095-governance-ai-ready-handoff.md | 66 | Acceptance Criteria | Decide whether GitHub Issues supplement the Markdown backlog. | Current task detail | Yes | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-095-governance-ai-ready-handoff.md | 67 | Acceptance Criteria | Verify repository access, release/package custody, and external guide/ video custody. | Current task detail | Yes | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-095-governance-ai-ready-handoff.md | 69 | Acceptance Criteria | Ensure final documentation identifies current, historical, and archived sources unambiguously. | Current task detail | Yes | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-095-governance-ai-ready-handoff.md | 71 | Acceptance Criteria | Complete owner review and final sign-off by October 30. | Current task detail | Yes | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-101-extract-zip-advisory-release-gate.md | 85 | Acceptance Criteria | **SUPERSEDED, NOT PASSED:** Task-087's tracker and task file would have changed from paused to resumed only after PR #67 integration and exact-head validation. ADR-021 removed this condition from the current release path. | Completed / superseded | No | PR #67 integration boxes were superseded by ADR-021.
.agent_work/tasks/active/TASK-101-extract-zip-advisory-release-gate.md | 322 | Focused Remediation - August 19, 2026 | The accepted change is semantically reconciled into PR #67 and validated at its new exact head before Task-087 resumes. | Completed / superseded | No | PR #67 integration boxes were superseded by ADR-021.
.agent_work/tasks/active/TASK-101-extract-zip-advisory-release-gate.md | 335 | Post-Merge Gate - August 20, 2026 | PR #67 contains the semantically reconciled accepted change and passes its required exact-head matrix before Task-087 resumes. | Completed / superseded | No | PR #67 integration boxes were superseded by ADR-021.
.agent_work/tasks/active/TASK-103-cuda128-blackwell-ml-runtime.md | 96 | W09 Package Assembly And First-Host Qualification - Completed 2026-09-28 | Repackage the updated manuals under a new control-ZIP identity, then complete browser-download and independent-host W10 acceptance cells before claiming release readiness. | Current task detail | Yes | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-103-cuda128-blackwell-ml-runtime.md | 148 | W10 Local First-Host Rehearsal - Started 2026-09-28 | Complete replacement-package browser-download and independent-host cells. | Current task detail | Yes | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/completed/TASK-031-interactive-highlighting.md | 42 | Acceptance Criteria | Performance remains smooth with 100+ detections (DEFERRED TO TASK-037) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-031-interactive-highlighting.md | 43 | Acceptance Criteria | No memory leaks or event listener buildup (DEFERRED TO TASK-037) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 179 | Acceptance Criteria | **AC-007**: Manual towers persist across page refreshes (session storage) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 181 | Acceptance Criteria | **AC-009**: Delete button removes manual towers from both map and list | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 185 | Acceptance Criteria | **AC-013**: Manual tower polygons are editable/draggable after creation | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 187 | Acceptance Criteria | **AC-015**: Performance: 100+ manual towers render without lag | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 242 | Phase 0: Discovery & Root Cause Analysis (2-4 hours) - NEW | Button handlers located and documented | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 243 | Phase 0: Discovery & Root Cause Analysis (2-4 hours) - NEW | Method implementations found and analyzed | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 244 | Phase 0: Discovery & Root Cause Analysis (2-4 hours) - NEW | Google Maps error root cause identified | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 245 | Phase 0: Discovery & Root Cause Analysis (2-4 hours) - NEW | Azure Maps silent failure root cause identified | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 246 | Phase 0: Discovery & Root Cause Analysis (2-4 hours) - NEW | Drawing event disconnection diagnosed | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 247 | Phase 0: Discovery & Root Cause Analysis (2-4 hours) - NEW | NEW-ISSUE-001 cleanup code located | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 291 | Phase 1: Bug Fixes & Core Restoration (4-6 hours) - COMPLETE âœ… | Google Maps "Add Locations" button works without errors | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 292 | Phase 1: Bug Fixes & Core Restoration (4-6 hours) - COMPLETE âœ… | Azure Maps "Add Locations" button triggers method execution | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 293 | Phase 1: Bug Fixes & Core Restoration (4-6 hours) - COMPLETE âœ… | Drawing polygon creates manual tower detection (both providers) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 294 | Phase 1: Bug Fixes & Core Restoration (4-6 hours) - COMPLETE âœ… | Manual towers appear in detection list with addresses | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 295 | Phase 1: Bug Fixes & Core Restoration (4-6 hours) - COMPLETE âœ… | Drawing tools persist across provider switches | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 626 | Phase 2: Visual Enhancement & Polish (4-8 hours) - REVISED | Manual towers display with purple border, no fill | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 627 | Phase 2: Visual Enhancement & Polish (4-8 hours) - REVISED | Detection list shows "âœ‹ Manual" badge | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 628 | Phase 2: Visual Enhancement & Polish (4-8 hours) - REVISED | Delete button removes manual towers correctly | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 629 | Phase 2: Visual Enhancement & Polish (4-8 hours) - REVISED | Session persistence working (if feature exists) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 663 | Phase 3: Integration & Cross-Provider Testing (2-4 hours) - REVISED | Manual towers work on both Google Maps and Azure Maps | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 664 | Phase 3: Integration & Cross-Provider Testing (2-4 hours) - REVISED | Provider switching preserves manual towers and drawing tools | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 665 | Phase 3: Integration & Cross-Provider Testing (2-4 hours) - REVISED | CSV export includes manual towers with correct type flag | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 666 | Phase 3: Integration & Cross-Provider Testing (2-4 hours) - REVISED | KML export includes manual towers with distinct styling | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 667 | Phase 3: Integration & Cross-Provider Testing (2-4 hours) - REVISED | YOLO export excludes manual towers | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 668 | Phase 3: Integration & Cross-Provider Testing (2-4 hours) - REVISED | Performance acceptable with 100+ manual towers | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 842 | Testing Status âœ… COMPLETE | 10 manual towers render: <100ms | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 843 | Testing Status âœ… COMPLETE | 50 manual towers render: <500ms | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 844 | Testing Status âœ… COMPLETE | 100 manual towers render: <2s | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 845 | Testing Status âœ… COMPLETE | Geocoding request: <1s average | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 846 | Testing Status âœ… COMPLETE | Provider switching with 20 manual towers: <1s | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 849 | Testing Status âœ… COMPLETE | All 15 acceptance criteria met (AC-001 through AC-015) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 850 | Testing Status âœ… COMPLETE | 0 regressions in ML detection workflow | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 851 | Testing Status âœ… COMPLETE | 0 console errors during manual tower addition | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 852 | Testing Status âœ… COMPLETE | Cross-browser compatibility (Chrome, Edge, Firefox) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 1070 | Success Metrics | 100% of acceptance criteria met (15 criteria) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 1071 | Success Metrics | 0 regressions in ML detection workflow | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 1072 | Success Metrics | 0 console errors during manual tower addition | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 1073 | Success Metrics | <2s render time for 100 manual towers | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 1076 | Success Metrics | Intuitive UI (no user confusion during testing) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 1077 | Success Metrics | Clear visual distinction between manual and ML towers | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 1078 | Success Metrics | Seamless integration with existing workflows | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 1081 | Success Metrics | All new code follows modular architecture patterns from TASK-038 | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 1082 | Success Metrics | Test coverage >80% for new Detection.js methods | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 1083 | Success Metrics | ESLint passes with 0 warnings | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | 1595 | Acceptance Criteria Validation | AC-001 through AC-015 validation results | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-phase-0-gap-analysis.md | 576 | Next Steps | Google Maps "Add Locations" works without errors | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-phase-0-gap-analysis.md | 577 | Next Steps | Azure Maps "Add Locations" provides user feedback | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-phase-0-gap-analysis.md | 578 | Next Steps | Manual towers appear in detection list with confidence=1.0 | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-phase-0-gap-analysis.md | 579 | Next Steps | Drawing tools persist across provider switches | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-phase-0-gap-analysis.md | 580 | Next Steps | Error messages guide users when prerequisites missing | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-IMPLEMENTATION-SUMMARY.md | 120 | Testing Status | Browser testing with DevTools | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-IMPLEMENTATION-SUMMARY.md | 121 | Testing Status | Memory profiling with heap snapshots | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-IMPLEMENTATION-SUMMARY.md | 122 | Testing Status | Extended session testing (30+ minutes) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-IMPLEMENTATION-SUMMARY.md | 123 | Testing Status | Legacy feature validation | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-memory-management.md | 310 | 2026-02-04 - Implementation Complete & Testing Ready | Test 1: Basic provider switching (10 switches) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-memory-management.md | 311 | 2026-02-04 - Implementation Complete & Testing Ready | Test 2: Memory stability with heap snapshots (20 switches) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-memory-management.md | 312 | 2026-02-04 - Implementation Complete & Testing Ready | Test 3: Drawing manager cleanup verification | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-memory-management.md | 313 | 2026-02-04 - Implementation Complete & Testing Ready | Test 4: Search infrastructure cleanup verification | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-memory-management.md | 314 | 2026-02-04 - Implementation Complete & Testing Ready | Test 5: Boundary cleanup verification | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-memory-management.md | 315 | 2026-02-04 - Implementation Complete & Testing Ready | Test 6: Extended session test (30 minutes) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-memory-management.md | 316 | 2026-02-04 - Implementation Complete & Testing Ready | Test 7: Rapid switching stress test (50 switches) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-memory-management.md | 317 | 2026-02-04 - Implementation Complete & Testing Ready | Test 8: Legacy feature validation | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-TESTING-PLAN.md | 24 | Prerequisites | Flask development server running (`python towerscout.py dev`) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-TESTING-PLAN.md | 25 | Prerequisites | Browser: Chrome/Edge with DevTools open | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-TESTING-PLAN.md | 26 | Prerequisites | Memory Profiler tab ready | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-TESTING-PLAN.md | 27 | Prerequisites | Console cleared and monitoring for errors | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-TESTING-PLAN.md | 151 | Test 4: Search Infrastructure Cleanup | "Cleaning up Google search infrastructure" logged | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-TESTING-PLAN.md | 152 | Test 4: Search Infrastructure Cleanup | "Cleaning up Azure search infrastructure" logged | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-TESTING-PLAN.md | 153 | Test 4: Search Infrastructure Cleanup | Search results display correctly after each switch | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-TESTING-PLAN.md | 154 | Test 4: Search Infrastructure Cleanup | No stale markers or boundaries from previous provider | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-TESTING-PLAN.md | 177 | Test 5: Boundary Cleanup | Azure resetBoundaries shows enhanced cleanup logs | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-TESTING-PLAN.md | 178 | Test 5: Boundary Cleanup | Google resetBoundaries executes correctly | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-TESTING-PLAN.md | 179 | Test 5: Boundary Cleanup | Only current search boundary visible on map | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-TESTING-PLAN.md | 180 | Test 5: Boundary Cleanup | No overlapping boundaries from previous searches | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-TESTING-PLAN.md | 207 | Test 6: Extended Session Test (30 minutes) | Browser remains responsive throughout | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-TESTING-PLAN.md | 208 | Test 6: Extended Session Test (30 minutes) | No memory-related slowdowns | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-TESTING-PLAN.md | 209 | Test 6: Extended Session Test (30 minutes) | No console errors | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-TESTING-PLAN.md | 210 | Test 6: Extended Session Test (30 minutes) | Memory usage plateaus (no continuous growth) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-TESTING-PLAN.md | 234 | Test 7: Rapid Switching Stress Test | "Provider switch already in progress" queuing works | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-TESTING-PLAN.md | 235 | Test 7: Rapid Switching Stress Test | All cleanup operations complete successfully | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-TESTING-PLAN.md | 236 | Test 7: Rapid Switching Stress Test | No race conditions or errors | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-TESTING-PLAN.md | 237 | Test 7: Rapid Switching Stress Test | System remains stable | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-TESTING-PLAN.md | 251 | Test 8: Legacy Feature Validation | Location search (address, zipcode) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-TESTING-PLAN.md | 252 | Test 8: Legacy Feature Validation | Polygon drawing tool | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-TESTING-PLAN.md | 253 | Test 8: Legacy Feature Validation | Rectangle drawing tool | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-TESTING-PLAN.md | 254 | Test 8: Legacy Feature Validation | Boundary display | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-TESTING-PLAN.md | 255 | Test 8: Legacy Feature Validation | Detection workflow (if backend available) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-TESTING-PLAN.md | 256 | Test 8: Legacy Feature Validation | Result filtering | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-TESTING-PLAN.md | 257 | Test 8: Legacy Feature Validation | Export functionality | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-TESTING-PLAN.md | 260 | Test 8: Legacy Feature Validation | All legacy features work as before | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-TESTING-PLAN.md | 261 | Test 8: Legacy Feature Validation | No functional regressions | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-036/TASK-036-SCOPE-ANALYSIS.md | 259 | 📊 TASK-036 Completion Status | Format selection dropdown (LOW priority - skip) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-036/TASK-036-SCOPE-ANALYSIS.md | 260 | 📊 TASK-036 Completion Status | Progress indicators (MEDIUM priority - optional) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-036/TASK-036-SCOPE-ANALYSIS.md | 261 | 📊 TASK-036 Completion Status | Advanced filtering (LOW priority - defer) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-036/TASK-036-SCOPE-ANALYSIS.md | 262 | 📊 TASK-036 Completion Status | Error handling polish (HIGH priority - recommend) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-036/TASK-036-SCOPE-ANALYSIS.md | 263 | 📊 TASK-036 Completion Status | ML training docs (HIGH priority - recommend) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-036/TASK-036-TESTING-CHECKLIST.md | 229 | Test 12: README Content Verification | "About This Dataset" header | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-036/TASK-036-TESTING-CHECKLIST.md | 230 | Test 12: README Content Verification | "Dataset Contents" section | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-036/TASK-036-TESTING-CHECKLIST.md | 231 | Test 12: README Content Verification | "File Structure" explanation | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-036/TASK-036-TESTING-CHECKLIST.md | 232 | Test 12: README Content Verification | "Label Format (YOLO)" with example | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-036/TASK-036-TESTING-CHECKLIST.md | 233 | Test 12: README Content Verification | "Detection Types" (ML vs Manual) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-036/TASK-036-TESTING-CHECKLIST.md | 234 | Test 12: README Content Verification | "Using This Dataset for Training" with YOLOv5 commands | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-036/TASK-036-TESTING-CHECKLIST.md | 235 | Test 12: README Content Verification | "Dataset Metadata" reference to contents.txt | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-036/TASK-036-TESTING-CHECKLIST.md | 236 | Test 12: README Content Verification | "Quality Notes" about confidence scores | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-036/TASK-036-TESTING-CHECKLIST.md | 237 | Test 12: README Content Verification | "Citation" with Lancet Digital Health paper | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-036/TASK-036-TESTING-CHECKLIST.md | 238 | Test 12: README Content Verification | "Support" with GitHub links | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-036/TASK-036-TESTING-CHECKLIST.md | 239 | Test 12: README Content Verification | "License" (CC-BY-NC-SA-4.0) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-036/TASK-036-TESTING-CHECKLIST.md | 287 | Test 15: Chrome Validation | Test 3: CSV Export Success | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-036/TASK-036-TESTING-CHECKLIST.md | 288 | Test 15: Chrome Validation | Test 6: KML Export Success | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-036/TASK-036-TESTING-CHECKLIST.md | 289 | Test 15: Chrome Validation | Test 9: Dataset Export with README | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-036/TASK-036-TESTING-CHECKLIST.md | 299 | Test 16: Firefox Validation | Test 3: CSV Export Success | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-036/TASK-036-TESTING-CHECKLIST.md | 300 | Test 16: Firefox Validation | Test 6: KML Export Success | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-036/TASK-036-TESTING-CHECKLIST.md | 301 | Test 16: Firefox Validation | Test 9: Dataset Export with README | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-037-user-journey-verification.md | 113 | Acceptance Criteria | **Stage 1 (Setup)**: Server starts without errors, both providers load correctly | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-037-user-journey-verification.md | 114 | Acceptance Criteria | **Stage 2 (AOI Definition)**: Address search returns valid locations with map navigation | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-037-user-journey-verification.md | 115 | Acceptance Criteria | **Stage 2 (AOI Definition)**: Radius tool creates visible circle on map with correct geometry | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-037-user-journey-verification.md | 116 | Acceptance Criteria | **Stage 3 (Processing)**: Tile estimation completes and displays accurate count | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-037-user-journey-verification.md | 117 | Acceptance Criteria | **Stage 3 (Processing)**: "Find Towers" executes without crashes or unhandled exceptions | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-037-user-journey-verification.md | 118 | Acceptance Criteria | **Stage 4 (Results)**: Results display in right-hand panel with complete address information | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-037-user-journey-verification.md | 119 | Acceptance Criteria | **Stage 4 (Results)**: Map markers appear for detected towers at correct coordinates | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-037-user-journey-verification.md | 120 | Acceptance Criteria | **Stage 4 (Results)**: Confidence scores display correctly for each detection | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-037-user-journey-verification.md | 121 | Acceptance Criteria | **Cross-Stage**: No console errors during entire workflow | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-037-user-journey-verification.md | 122 | Acceptance Criteria | **Cross-Stage**: Provider switching works at any stage without losing progress | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-037-user-journey-verification.md | 1096 | towerscout.py line 1158 | Select Google Maps → Flask logs show "Geocoding successful via google_maps" | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-037-user-journey-verification.md | 1097 | towerscout.py line 1158 | Select Azure Maps → Flask logs show "Geocoding successful via azure_maps" | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-037-user-journey-verification.md | 1098 | towerscout.py line 1158 | Provider switch mid-session → Geocoding follows new provider | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-037-user-journey-verification.md | 1099 | towerscout.py line 1158 | Preferred provider fails → Fallback to alternate provider still works | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-037-user-journey-verification.md | 1100 | towerscout.py line 1158 | No provider preference specified → Defaults to Azure → Google order | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-037-user-journey-verification.md | 1687 | Stage 3: Processing | **Detection results accurate** - ⏸️ PENDING (0 detections returned, needs validation with known tower location) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-037-user-journey-verification.md | 1690 | Stage 4: Results | **Results display in right-hand panel** - ⏸️ PENDING TASK-031/032 | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-037-user-journey-verification.md | 1691 | Stage 4: Results | **Map markers appear at correct coordinates** - ⏸️ PENDING TASK-031 | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-037-user-journey-verification.md | 1692 | Stage 4: Results | **Confidence scores display correctly** - ⏸️ PENDING TASK-032 | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-037-user-journey-verification.md | 1697 | Cross-Stage | **No console errors during workflow** - ⚠️ PARTIAL (only deprecation warnings for Google Maps remain) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-037-user-journey-verification.md | 1771 | Sign-off | Stage 2 re-testing with architectural fixes validated | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-037-user-journey-verification.md | 1772 | Sign-off | TASK-031 (Interactive Highlighting) completed for Stage 4 marker display | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-037-user-journey-verification.md | 1773 | Sign-off | TASK-032 (Enhanced Details Panel) completed for Stage 4 address display | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-037-user-journey-verification.md | 1774 | Sign-off | Stage 4 testing with complete infrastructure | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-037-user-journey-verification.md | 1775 | Sign-off | Full user journey functional without workarounds | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-038-frontend-refactoring.md | 149 | Stage 5: UI & Final Integration (5 hours) ✅ COMPLETE | Bundle builds successfully: `node webapp/build.js` exits 0 | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-038-frontend-refactoring.md | 150 | Stage 5: UI & Final Integration (5 hours) ✅ COMPLETE | Pre-commit hook functional: Detects source changes, rebuilds bundle, stages changes | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-038-frontend-refactoring.md | 151 | Stage 5: UI & Final Integration (5 hours) ✅ COMPLETE | All validation tests pass: - `bash validate_stage_0.sh` (Stage 0 only) - `node tests/frontend/test_global_contract.js` - `python tests/backend/test_endpoint_contract.py` - `node tests/integration/test_task_041_stability.js` | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-038-frontend-refactoring.md | 156 | Stage 5: UI & Final Integration (5 hours) ✅ COMPLETE | Manual browser testing: No console errors, all features functional | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-038-frontend-refactoring.md | 157 | Stage 5: UI & Final Integration (5 hours) ✅ COMPLETE | Code review: Approved by stakeholder | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-038-frontend-refactoring.md | 839 | Implementation - Detection System Extraction (6 hours) | Search → Draw boundary → Detect workflow | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-038-frontend-refactoring.md | 840 | Implementation - Detection System Extraction (6 hours) | Detection list renders with address grouping | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-038-frontend-refactoring.md | 841 | Implementation - Detection System Extraction (6 hours) | Confidence slider filters detections correctly | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-038-frontend-refactoring.md | 842 | Implementation - Detection System Extraction (6 hours) | Inside/Outside checkbox filtering works | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-038-frontend-refactoring.md | 843 | Implementation - Detection System Extraction (6 hours) | Detection navigation (prev/next buttons) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-038-frontend-refactoring.md | 844 | Implementation - Detection System Extraction (6 hours) | Tile navigation (prev/next buttons) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-038-frontend-refactoring.md | 845 | Implementation - Detection System Extraction (6 hours) | Detection highlighting (click list → map highlights) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-038-frontend-refactoring.md | 846 | Implementation - Detection System Extraction (6 hours) | Map click → list highlights (reverse direction) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-038-frontend-refactoring.md | 847 | Implementation - Detection System Extraction (6 hours) | Review pane controls functional | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-038-frontend-refactoring.md | 848 | Implementation - Detection System Extraction (6 hours) | No console errors during operations | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-038-frontend-refactoring.md | 865 | Stage 4 Acceptance Criteria 🔄 IN VALIDATION | `Detection.number()` method functional from template line 161 | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-038-frontend-refactoring.md | 866 | Stage 4 Acceptance Criteria 🔄 IN VALIDATION | `Tile.number()` method functional from template line 173 | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-038-frontend-refactoring.md | 867 | Stage 4 Acceptance Criteria 🔄 IN VALIDATION | Detection navigation (prev/next) works | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-038-frontend-refactoring.md | 868 | Stage 4 Acceptance Criteria 🔄 IN VALIDATION | Tile navigation (prev/next) works | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-038-frontend-refactoring.md | 869 | Stage 4 Acceptance Criteria 🔄 IN VALIDATION | Confidence slider filtering works | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-038-frontend-refactoring.md | 870 | Stage 4 Acceptance Criteria 🔄 IN VALIDATION | Review mode toggle functional | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-038-frontend-refactoring.md | 871 | Stage 4 Acceptance Criteria 🔄 IN VALIDATION | Global contract test passes | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 60 | Acceptance Criteria | **AC-001**: No deprecation warnings appear in browser console for Drawing Library or SearchBox | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 61 | Acceptance Criteria | **AC-002**: Rectangle drawing tool works identically to current implementation (stroke color, fill opacity, editable, draggable) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 62 | Acceptance Criteria | **AC-003**: Polygon drawing tool works identically to current implementation | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 63 | Acceptance Criteria | **AC-004**: Address search provides suggestions and centers map on selection | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 64 | Acceptance Criteria | **AC-005**: City and neighborhood searches return boundaries via OpenStreetMap integration | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 65 | Acceptance Criteria | **AC-006**: Zipcode searches (5-digit, quoted) continue to work with special case handling | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 66 | Acceptance Criteria | **AC-007**: Provider switching (Google ↔ Azure) works without errors or memory leaks | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 67 | Acceptance Criteria | **AC-008**: Detection workflow (search → draw → estimate tiles → detect) produces accurate coordinate data | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 68 | Acceptance Criteria | **AC-009**: All 23 existing frontend tests pass (TASK-042 test suite) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 69 | Acceptance Criteria | **AC-010**: Cross-browser compatibility maintained (Chrome, Edge, Firefox, Safari) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 70 | Acceptance Criteria | **AC-011**: Map load time equivalent or faster than current v3.55.1 | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 71 | Acceptance Criteria | **AC-012**: Drawing responsiveness (polygon with many points) equivalent or better | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 72 | Acceptance Criteria | **AC-013**: Circle tool (radius search) continues to work (no changes needed - uses mathematical generation) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 73 | Acceptance Criteria | **AC-014**: Documentation updated with new API implementation details | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 204 | Phase 1: Research New Google Maps APIs (2-3 hours) | API Version Strategy: Pinned / Weekly / Quarterly / Remove version parameter | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 205 | Phase 1: Research New Google Maps APIs (2-3 hours) | Drawing Tools Approach: Custom overlays / Advanced Markers / Third-party library | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 206 | Phase 1: Research New Google Maps APIs (2-3 hours) | Autocomplete Configuration: Required fields, types, bounds biasing options | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 231 | Phase 2: API Version Update & Core Validation (1-2 hours) | No version-related console warnings | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 232 | Phase 2: API Version Update & Core Validation (1-2 hours) | Map renders correctly with satellite imagery | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 233 | Phase 2: API Version Update & Core Validation (1-2 hours) | Provider switching works seamlessly | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 234 | Phase 2: API Version Update & Core Validation (1-2 hours) | All basic map operations functional | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 276 | Phase 3: Drawing Tools Migration (4-8 hours) | Draw rectangle → verify bounds extraction | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 277 | Phase 3: Drawing Tools Migration (4-8 hours) | Draw polygon → verify path extraction | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 278 | Phase 3: Drawing Tools Migration (4-8 hours) | Draw multiple shapes → verify accumulation in `this.newShapes` | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 279 | Phase 3: Drawing Tools Migration (4-8 hours) | Edit shape → verify boundary updates | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 280 | Phase 3: Drawing Tools Migration (4-8 hours) | Clear shapes → verify cleanup | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 281 | Phase 3: Drawing Tools Migration (4-8 hours) | Toggle drawing modes → verify UI state | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 325 | Phase 4: SearchBox → Autocomplete Migration (2-4 hours) | Address search (e.g., "123 Main St, New York, NY") → suggestions appear | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 326 | Phase 4: SearchBox → Autocomplete Migration (2-4 hours) | Select suggestion → map centers and queries boundary | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 327 | Phase 4: SearchBox → Autocomplete Migration (2-4 hours) | City search (e.g., "San Francisco") → boundary displayed | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 328 | Phase 4: SearchBox → Autocomplete Migration (2-4 hours) | Neighborhood search (e.g., "Brooklyn") → boundary displayed | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 329 | Phase 4: SearchBox → Autocomplete Migration (2-4 hours) | Zipcode search (e.g., "10001" or "10001") → special case handled | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 330 | Phase 4: SearchBox → Autocomplete Migration (2-4 hours) | Invalid search → proper error handling | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 331 | Phase 4: SearchBox → Autocomplete Migration (2-4 hours) | Viewport biasing → suggestions prioritize visible area | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 398 | Phase 5: Comprehensive Testing & Validation (2-5 hours) | All 23 existing frontend tests pass (TASK-042 test suite) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 399 | Phase 5: Comprehensive Testing & Validation (2-5 hours) | No deprecation warnings in any browser console | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 400 | Phase 5: Comprehensive Testing & Validation (2-5 hours) | All legacy features remain functional (per USER-JOURNEY-GUIDE.md) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 401 | Phase 5: Comprehensive Testing & Validation (2-5 hours) | Provider switching works without errors in all browsers | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 402 | Phase 5: Comprehensive Testing & Validation (2-5 hours) | Detection pipeline receives correct coordinates (validated against known test case) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 403 | Phase 5: Comprehensive Testing & Validation (2-5 hours) | Performance equivalent or better than v3.55.1 baseline | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 443 | Phase 6: Documentation & Handoff (1-2 hours) | Updated copilot-instructions.md | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 444 | Phase 6: Documentation & Handoff (1-2 hours) | Migration notes document (in .agent_work/context/guides/) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 445 | Phase 6: Documentation & Handoff (1-2 hours) | Updated Developer-Architecture-Guide.md | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 446 | Phase 6: Documentation & Handoff (1-2 hours) | Deployment validation checklist | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | 447 | Phase 6: Documentation & Handoff (1-2 hours) | User release notes (if UI changes present) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 60 | Acceptance Criteria | **Search boundaries**: Blue outline, no fill (both providers) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 61 | Acceptance Criteria | **Tile boundaries**: Not visible on map (both providers) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 62 | Acceptance Criteria | **Detection boxes**: Red outline with light transparent fill (both providers) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 63 | Acceptance Criteria | **Selected detection**: Green outline with light green fill on Azure, green flash on Google | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 64 | Acceptance Criteria | **Visual parity**: Azure Maps matches Google Maps visual clarity | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 65 | Acceptance Criteria | **No regressions**: Google Maps functionality unchanged | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 66 | Acceptance Criteria | **Outbreak workflow**: Investigators can assess imagery quality under overlays | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 67 | Acceptance Criteria | **Provider switching**: No visual inconsistencies when toggling providers | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 201 | Phase 1: Search Boundary Styling (30 min) - LOWEST RISK | Draw circle search radius → blue outline, no fill | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 202 | Phase 1: Search Boundary Styling (30 min) - LOWEST RISK | Draw polygon search area → blue outline, no fill | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 203 | Phase 1: Search Boundary Styling (30 min) - LOWEST RISK | Switch providers → consistent appearance | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 204 | Phase 1: Search Boundary Styling (30 min) - LOWEST RISK | Multiple boundaries → no visual conflicts | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 229 | Phase 2: Tile Visibility Investigation (45 min) - MEDIUM RISK | Run detection → no tile boundaries visible | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 230 | Phase 2: Tile Visibility Investigation (45 min) - MEDIUM RISK | Check console logs → tiles not added to rendering pipeline | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 231 | Phase 2: Tile Visibility Investigation (45 min) - MEDIUM RISK | Verify detection boxes still render correctly | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 232 | Phase 2: Tile Visibility Investigation (45 min) - MEDIUM RISK | Test with 50+ tiles → performance unchanged | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 256 | Phase 3: Detection Box Opacity Fix (30 min) - MEDIUM RISK | Detection boxes have light red transparent fill | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 257 | Phase 3: Detection Box Opacity Fix (30 min) - MEDIUM RISK | Underlying imagery clearly visible | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 258 | Phase 3: Detection Box Opacity Fix (30 min) - MEDIUM RISK | Multiple overlapping boxes distinguishable | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 259 | Phase 3: Detection Box Opacity Fix (30 min) - MEDIUM RISK | Provider switch maintains transparency | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 297 | Phase 4: Selected Detection Highlighting (45 min) - HIGHER RISK | Click list item → marker turns green with enhanced visibility | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 298 | Phase 4: Selected Detection Highlighting (45 min) - HIGHER RISK | Click another item → previous marker returns to red | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 299 | Phase 4: Selected Detection Highlighting (45 min) - HIGHER RISK | Click marker → same green highlighting appears | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 300 | Phase 4: Selected Detection Highlighting (45 min) - HIGHER RISK | Rapid clicking → no flickering or style conflicts | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 301 | Phase 4: Selected Detection Highlighting (45 min) - HIGHER RISK | Provider switch → highlighting state preserved | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 342 | Phase 5: Cross-Provider Validation (30 min) - CRITICAL | All visual elements consistent between providers | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 343 | Phase 5: Cross-Provider Validation (30 min) - CRITICAL | No performance degradation | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 344 | Phase 5: Cross-Provider Validation (30 min) - CRITICAL | No regressions in existing functionality | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 345 | Phase 5: Cross-Provider Validation (30 min) - CRITICAL | Outbreak workflow seamless on both providers | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 368 | Or revert entire commit | Google Maps functionality intact | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 369 | Or revert entire commit | Azure Maps returns to previous (broken but functional) state | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 370 | Or revert entire commit | No new errors introduced | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 624 | Phase 1 Expected Outcomes | Azure Maps search boundaries: Blue outline, transparent fill | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 625 | Phase 1 Expected Outcomes | Google Maps behavior: Unchanged (no regression) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 626 | Phase 1 Expected Outcomes | Provider switching: Consistent styling maintained | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 627 | Phase 1 Expected Outcomes | No console errors or warnings | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 1100 | 2026-02-11 - Phase 4 - Selected Detection Highlighting (Azure Maps Only) | Hard refresh browser (Ctrl+Shift+R) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 1101 | 2026-02-11 - Phase 4 - Selected Detection Highlighting (Azure Maps Only) | Run detection on Azure Maps | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 1102 | 2026-02-11 - Phase 4 - Selected Detection Highlighting (Azure Maps Only) | Click detection in right panel → Verify marker becomes more prominent green on map | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 1103 | 2026-02-11 - Phase 4 - Selected Detection Highlighting (Azure Maps Only) | Click another detection → Verify previous reverts to light red, new becomes prominent green | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 1104 | 2026-02-11 - Phase 4 - Selected Detection Highlighting (Azure Maps Only) | Test rapid clicking → No flickering or style conflicts | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 1105 | 2026-02-11 - Phase 4 - Selected Detection Highlighting (Azure Maps Only) | Switch to Google Maps → Verify existing green flash still works (no regression) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | 1106 | 2026-02-11 - Phase 4 - Selected Detection Highlighting (Azure Maps Only) | Switch back to Azure → Verify highlighting still works after provider change | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 92 | Cross-Phase Validation | All Stage 2 TASK-037 acceptance criteria pass without workarounds | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 93 | Cross-Phase Validation | No console errors during complete user journey (Stages 1-3) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 94 | Cross-Phase Validation | Provider switching stable with shapes visible | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 95 | Cross-Phase Validation | ISSUE-001, ISSUE-002, ISSUE-003, ISSUE-004 all marked RESOLVED | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 96 | Cross-Phase Validation | Documentation updated with architectural improvements | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 178 | Step 1.1: Extend ProviderStateManager (1-2 hours) | `providerManager.getMap()` returns current map instance | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 179 | Step 1.1: Extend ProviderStateManager (1-2 hours) | `providerManager.getCurrentProvider()` returns 'google' or 'azure' | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 180 | Step 1.1: Extend ProviderStateManager (1-2 hours) | `providerManager.isFullyInitialized()` checks all required states | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 181 | Step 1.1: Extend ProviderStateManager (1-2 hours) | Console logs show initialization milestone completion | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 213 | Step 1.2: Update Azure Maps Initialization (1-2 hours) | Azure Maps initialization completes all 3 milestones | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 214 | Step 1.2: Update Azure Maps Initialization (1-2 hours) | Console shows "✅ azure - styleLoaded complete" | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 215 | Step 1.2: Update Azure Maps Initialization (1-2 hours) | Console shows "✅ azure - drawingManagerReady complete" | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 216 | Step 1.2: Update Azure Maps Initialization (1-2 hours) | Console shows "✅ azure - dataSourceReady complete" | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 217 | Step 1.2: Update Azure Maps Initialization (1-2 hours) | `providerManager.isFullyInitialized('azure')` returns true after complete | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 231 | Step 1.3: Update Google Maps Initialization (30 mins) | Google Maps initialization completes 2 milestones | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 232 | Step 1.3: Update Google Maps Initialization (30 mins) | `providerManager.isFullyInitialized('google')` returns true after complete | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 261 | Step 1.4: Update Drawing Tool Handlers (1-2 hours) | Circle tool checks initialization before proceeding | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 262 | Step 1.4: Update Drawing Tool Handlers (1-2 hours) | Polygon tool checks initialization before proceeding | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 263 | Step 1.4: Update Drawing Tool Handlers (1-2 hours) | User sees helpful message if map not ready | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 264 | Step 1.4: Update Drawing Tool Handlers (1-2 hours) | No "providers not initialized" errors in console | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 281 | Step 1.5: Deprecate Global Variables (30 mins) | All critical code paths use ProviderStateManager | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 282 | Step 1.5: Deprecate Global Variables (30 mins) | Drawing tools access map via `providerManager.getMap()` | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 283 | Step 1.5: Deprecate Global Variables (30 mins) | Provider switching updates ProviderStateManager state | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 326 | Step 2.1: Implement Shape Reference Tracking (1-2 hours) | All circle creations tracked in `activeShapes.circles` | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 327 | Step 2.1: Implement Shape Reference Tracking (1-2 hours) | All polygon creations tracked in `activeShapes.polygons` | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 328 | Step 2.1: Implement Shape Reference Tracking (1-2 hours) | Shape references accessible for cleanup operations | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 377 | Step 2.2: Fix Circle Replacement Logic (1 hour) | Creating new circle removes previous circles | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 378 | Step 2.2: Fix Circle Replacement Logic (1 hour) | Only one circle visible on map at a time | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 379 | Step 2.2: Fix Circle Replacement Logic (1 hour) | Console logs show circle removal and creation | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 380 | Step 2.2: Fix Circle Replacement Logic (1 hour) | ISSUE-003 marked RESOLVED | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 447 | Step 2.3: Fix Viewport Bounds vs Boundary Bounds (2-3 hours) | Small circle in large viewport generates minimal tiles | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 448 | Step 2.3: Fix Viewport Bounds vs Boundary Bounds (2-3 hours) | Large polygon generates appropriate tile coverage | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 449 | Step 2.3: Fix Viewport Bounds vs Boundary Bounds (2-3 hours) | No boundaries defaults to viewport bounds (backwards compatible) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 450 | Step 2.3: Fix Viewport Bounds vs Boundary Bounds (2-3 hours) | Multiple boundaries: bounding box encompasses all | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 451 | Step 2.3: Fix Viewport Bounds vs Boundary Bounds (2-3 hours) | Console logs show boundary bounding box calculation | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 452 | Step 2.3: Fix Viewport Bounds vs Boundary Bounds (2-3 hours) | No detections outside drawn boundaries | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 453 | Step 2.3: Fix Viewport Bounds vs Boundary Bounds (2-3 hours) | Tile estimation reflects boundary area, not viewport area | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 454 | Step 2.3: Fix Viewport Bounds vs Boundary Bounds (2-3 hours) | ISSUE-010 marked RESOLVED | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 507 | Step 2.4: Fix Clear Button Implementation (1-2 hours) | Click Clear button removes all visible shapes | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 508 | Step 2.4: Fix Clear Button Implementation (1-2 hours) | Console shows successful cleanup steps | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 509 | Step 2.4: Fix Clear Button Implementation (1-2 hours) | Map displays clean state with no shapes | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 510 | Step 2.4: Fix Clear Button Implementation (1-2 hours) | Multiple Clear clicks work correctly (idempotent) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 511 | Step 2.4: Fix Clear Button Implementation (1-2 hours) | ISSUE-004 marked RESOLVED | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 523 | Step 2.5: Provider Switching Cleanup (30 mins) | Provider switch removes all shapes from previous provider | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 524 | Step 2.5: Provider Switching Cleanup (30 mins) | No shape accumulation across provider switches | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 525 | Step 2.5: Provider Switching Cleanup (30 mins) | Memory usage stable during provider switching | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 561 | Step 2.6: Memory Leak Stress Test (30 mins) | Stress test completes without errors | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 562 | Step 2.6: Memory Leak Stress Test (30 mins) | Browser memory usage stable (DevTools Memory profiler) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 563 | Step 2.6: Memory Leak Stress Test (30 mins) | No shape accumulation after test | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 564 | Step 2.6: Memory Leak Stress Test (30 mins) | No event listener buildup | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 645 | February 13, 2026 - Phase 1 Implementation (Steps 1.1-1.4) | Manual testing: Start server and open application | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 646 | February 13, 2026 - Phase 1 Implementation (Steps 1.1-1.4) | Test circle tool on first attempt (should work without provider switch) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 647 | February 13, 2026 - Phase 1 Implementation (Steps 1.1-1.4) | Test polygon tool on first attempt | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 648 | February 13, 2026 - Phase 1 Implementation (Steps 1.1-1.4) | Check browser console for initialization milestone logs | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 649 | February 13, 2026 - Phase 1 Implementation (Steps 1.1-1.4) | Verify no "providers not initialized" errors | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 681 | February 13, 2026 - Phase 1 Bug Fix (Single Provider Initialization) | Refresh browser and test circle tool | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 682 | February 13, 2026 - Phase 1 Bug Fix (Single Provider Initialization) | Verify circle renders on first attempt | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 683 | February 13, 2026 - Phase 1 Bug Fix (Single Provider Initialization) | Check console for "After reset - Google boundaries: not initialized" (safe message) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 684 | February 13, 2026 - Phase 1 Bug Fix (Single Provider Initialization) | Verify no crashes | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 714 | February 13, 2026 - Phase 1 Bug Fix #2 (Ternary Operator Precedence) | Hard refresh browser (Ctrl+Shift+R or DevTools cache clear) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 715 | February 13, 2026 - Phase 1 Bug Fix #2 (Ternary Operator Precedence) | Test circle tool - should complete without error | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 716 | February 13, 2026 - Phase 1 Bug Fix #2 (Ternary Operator Precedence) | Check console for "not initialized" messages (safe fallback) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 717 | February 13, 2026 - Phase 1 Bug Fix #2 (Ternary Operator Precedence) | Verify circle renders on Azure Maps | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 780 | February 13, 2026 - Phase 1 Bug Fix #3 (Polygon Tool & Tile Estimation) | Hard refresh browser | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 781 | February 13, 2026 - Phase 1 Bug Fix #3 (Polygon Tool & Tile Estimation) | Draw a polygon around search area | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 782 | February 13, 2026 - Phase 1 Bug Fix #3 (Polygon Tool & Tile Estimation) | Click "Estimate" button - should show tile count | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 783 | February 13, 2026 - Phase 1 Bug Fix #3 (Polygon Tool & Tile Estimation) | Click "Get Objects" button - should start detection | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 784 | February 13, 2026 - Phase 1 Bug Fix #3 (Polygon Tool & Tile Estimation) | Check console for clean execution (only valid shapes logged) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 785 | February 13, 2026 - Phase 1 Bug Fix #3 (Polygon Tool & Tile Estimation) | Verify no "provider not initialized" or "addBoundary" errors | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 861 | February 13, 2026 - Phase 1 Bug Fix #4 (Azure Drawing Event & Shape Retrieval) | Hard refresh browser | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 862 | February 13, 2026 - Phase 1 Bug Fix #4 (Azure Drawing Event & Shape Retrieval) | Draw polygon using polygon tool | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 863 | February 13, 2026 - Phase 1 Bug Fix #4 (Azure Drawing Event & Shape Retrieval) | Complete polygon (double-click or Edit button) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 864 | February 13, 2026 - Phase 1 Bug Fix #4 (Azure Drawing Event & Shape Retrieval) | Check console for "🎨 Azure Maps drawingcomplete event fired" | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 865 | February 13, 2026 - Phase 1 Bug Fix #4 (Azure Drawing Event & Shape Retrieval) | Click "Custom Shape" button | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 866 | February 13, 2026 - Phase 1 Bug Fix #4 (Azure Drawing Event & Shape Retrieval) | Check console for "🔍 Retrieving drawn boundaries from Azure Maps..." | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 867 | February 13, 2026 - Phase 1 Bug Fix #4 (Azure Drawing Event & Shape Retrieval) | Click "Estimate" button → should show tile count | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 868 | February 13, 2026 - Phase 1 Bug Fix #4 (Azure Drawing Event & Shape Retrieval) | Verify polygon recognized as boundary | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1083 | **Step 2.3: Add Boundary Bounds Methods (Foundation)** ⏸️ NOT STARTED | Method compiles without syntax errors | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1084 | **Step 2.3: Add Boundary Bounds Methods (Foundation)** ⏸️ NOT STARTED | No boundaries: Returns viewport bounds (backward compatible) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1085 | **Step 2.3: Add Boundary Bounds Methods (Foundation)** ⏸️ NOT STARTED | Single circle boundary: Returns circle bounding box | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1086 | **Step 2.3: Add Boundary Bounds Methods (Foundation)** ⏸️ NOT STARTED | Multiple boundaries: Returns encompassing bounding box | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1087 | **Step 2.3: Add Boundary Bounds Methods (Foundation)** ⏸️ NOT STARTED | Invalid data: Gracefully falls back to viewport bounds | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1088 | **Step 2.3: Add Boundary Bounds Methods (Foundation)** ⏸️ NOT STARTED | Console logs show calculation details | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1130 | **Step 2.1: Add Active Shapes Tracking** ⏸️ NOT STARTED | AzureMap initializes with empty activeShapes object | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1131 | **Step 2.1: Add Active Shapes Tracking** ⏸️ NOT STARTED | GoogleMap initializes with empty activeShapes object | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1132 | **Step 2.1: Add Active Shapes Tracking** ⏸️ NOT STARTED | Object structure: `{circles: [], polygons: [], markers: []}` | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1133 | **Step 2.1: Add Active Shapes Tracking** ⏸️ NOT STARTED | No errors during map initialization | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1212 | **Step 2.2: Implement Circle Replacement** ⏸️ NOT STARTED | First circle: Creates successfully | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1213 | **Step 2.2: Implement Circle Replacement** ⏸️ NOT STARTED | Second circle: Removes first circle, creates new one | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1214 | **Step 2.2: Implement Circle Replacement** ⏸️ NOT STARTED | Multiple circles: Only latest circle visible | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1215 | **Step 2.2: Implement Circle Replacement** ⏸️ NOT STARTED | Console shows: "🔄 Clearing X circle(s)" | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1216 | **Step 2.2: Implement Circle Replacement** ⏸️ NOT STARTED | Console shows: "✅ Cleared X circle(s)" | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1217 | **Step 2.2: Implement Circle Replacement** ⏸️ NOT STARTED | No accumulation of circles on map | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1308 | **Step 2.4: Update resetBoundaries() Implementation** ⏸️ NOT STARTED | Clear button removes all circles | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1309 | **Step 2.4: Update resetBoundaries() Implementation** ⏸️ NOT STARTED | Clear button removes all drawn polygons | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1310 | **Step 2.4: Update resetBoundaries() Implementation** ⏸️ NOT STARTED | Clear button removes all search area shapes | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1311 | **Step 2.4: Update resetBoundaries() Implementation** ⏸️ NOT STARTED | Multiple Clear clicks work (idempotent) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1312 | **Step 2.4: Update resetBoundaries() Implementation** ⏸️ NOT STARTED | Console shows step-by-step cleanup | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1313 | **Step 2.4: Update resetBoundaries() Implementation** ⏸️ NOT STARTED | Map displays clean state after clear | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1314 | **Step 2.4: Update resetBoundaries() Implementation** ⏸️ NOT STARTED | No shape accumulation | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1353 | **Step 2.6: Update getObjects() to Use Boundary Bounds** ⏸️ NOT STARTED | Small circle in large viewport: Generates minimal tiles (not whole viewport) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1354 | **Step 2.6: Update getObjects() to Use Boundary Bounds** ⏸️ NOT STARTED | Large polygon: Generates appropriate tile coverage | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1355 | **Step 2.6: Update getObjects() to Use Boundary Bounds** ⏸️ NOT STARTED | No boundaries: Uses viewport bounds (backward compatible) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1356 | **Step 2.6: Update getObjects() to Use Boundary Bounds** ⏸️ NOT STARTED | Multiple boundaries: Uses bounding box encompassing all | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1357 | **Step 2.6: Update getObjects() to Use Boundary Bounds** ⏸️ NOT STARTED | Console logs show: "🗺️ Using bounds for tile generation: ..." | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1358 | **Step 2.6: Update getObjects() to Use Boundary Bounds** ⏸️ NOT STARTED | Tile estimation reflects boundary area, not viewport | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1381 | **Step 2.5: Verify Provider Switching Cleanup** ⏸️ NOT STARTED | Switch provider: All shapes cleared from previous provider | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1382 | **Step 2.5: Verify Provider Switching Cleanup** ⏸️ NOT STARTED | Switch back: Clean slate on both providers | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1383 | **Step 2.5: Verify Provider Switching Cleanup** ⏸️ NOT STARTED | No shape accumulation across switches | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | 1384 | **Step 2.5: Verify Provider Switching Cleanup** ⏸️ NOT STARTED | Memory usage stable | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-042-testing-action-log.md | 101 | Action Items | Begin Test Suite 3 (TASK-037 cross-validation) - quickest validation | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-042-testing-action-log.md | 102 | Action Items | Execute Test Suite 1 (TASK-031 interactive highlighting) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-042-testing-action-log.md | 103 | Action Items | Execute Test Suite 2 (TASK-040 visual consistency) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-042-testing-action-log.md | 104 | Action Items | Document all findings | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-042-testing-action-log.md | 105 | Action Items | Update current-tasks.md with completion status | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-CLEANUP-PLAN.md | 265 | Step 7: Testing (30-60 min) | Run detection (ML processing with array sorts) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-CLEANUP-PLAN.md | 266 | Step 7: Testing (30-60 min) | Filter by confidence (minConfidence changes) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-CLEANUP-PLAN.md | 267 | Step 7: Testing (30-60 min) | Export CSV (array iteration) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-CLEANUP-PLAN.md | 268 | Step 7: Testing (30-60 min) | Click detections (onclick handlers) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-CLEANUP-PLAN.md | 269 | Step 7: Testing (30-60 min) | Add manual tower (array manipulation) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-CLEANUP-PLAN.md | 270 | Step 7: Testing (30-60 min) | Switch providers (azureMap handling) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-CLEANUP-PLAN.md | 271 | Step 7: Testing (30-60 min) | Clear all (array clearing) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-CLEANUP-PLAN.md | 321 | Success Criteria | Bundle rebuilds successfully (0 errors) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-CLEANUP-PLAN.md | 322 | Success Criteria | Console warnings reduced by ~97% | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-CLEANUP-PLAN.md | 323 | Success Criteria | All manual tests pass | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-CLEANUP-PLAN.md | 324 | Success Criteria | No regressions in detection, export, or highlighting functionality | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-CLEANUP-PLAN.md | 325 | Success Criteria | Documentation updated | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-CLEANUP-TESTING.md | 318 | Comprehensive Test Summary | Console noise reduced significantly (>90%) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-CLEANUP-TESTING.md | 319 | Comprehensive Test Summary | All functionality works correctly | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-CLEANUP-TESTING.md | 320 | Comprehensive Test Summary | No regressions detected | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-CLEANUP-TESTING.md | 321 | Comprehensive Test Summary | Ready for production | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-CLEANUP-TESTING.md | 328 | Regression Checklist | Detection highlighting still works (TASK-033) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-CLEANUP-TESTING.md | 329 | Regression Checklist | Manual tower highlighting preserved (purple borders) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-CLEANUP-TESTING.md | 330 | Regression Checklist | Export system functional (TASK-036) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-CLEANUP-TESTING.md | 331 | Regression Checklist | Provider switching reliable (TASK-039) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-CLEANUP-TESTING.md | 332 | Regression Checklist | No new JavaScript errors introduced | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-CLEANUP-TESTING.md | 338 | Success Criteria | Bundle rebuilds successfully (0 errors) ✅ COMPLETE (401.1 KB) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-CLEANUP-TESTING.md | 339 | Success Criteria | Console warnings reduced by >90% | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-CLEANUP-TESTING.md | 340 | Success Criteria | All 8 manual tests pass | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-CLEANUP-TESTING.md | 341 | Success Criteria | No regressions in detection, export, or highlighting | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-CLEANUP-TESTING.md | 342 | Success Criteria | ML detection processing works correctly | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-CLEANUP-TESTING.md | 343 | Success Criteria | Confidence filtering functional | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-CLEANUP-TESTING.md | 344 | Success Criteria | CSV export generates valid files | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-CLEANUP-TESTING.md | 345 | Success Criteria | Manual tower workflow operational | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-CLEANUP-TESTING.md | 346 | Success Criteria | Clear all functionality works | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-global-variable-deprecation.md | 73 | Acceptance Criteria | **ProviderStateManager Extended**: Map state, detection state, and progress timer methods added following singleton pattern established in TASK-041 | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-global-variable-deprecation.md | 74 | Acceptance Criteria | **Property Descriptors Implemented**: window.googleMap, window.azureMap, Detection_detections, Detection_minConfidence, progressTimer wrapped with deprecation warnings in webapp/js/src/globals.js | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-global-variable-deprecation.md | 75 | Acceptance Criteria | **Race Condition #1 Fixed**: Provider switching during async initialization no longer causes currentMap corruption (lines 3332-3378 in towerscout.js) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-global-variable-deprecation.md | 76 | Acceptance Criteria | **Race Condition #2 Fixed**: Detection array mutations during sorting/filtering no longer corrupt data (lines 3537, 3616 in towerscout.js) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-global-variable-deprecation.md | 77 | Acceptance Criteria | **Race Condition #3 Fixed**: Progress timer cleanup guaranteed on all exit paths including cancel operations (lines 4412-4424, 9440-9475 in towerscout.js) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-global-variable-deprecation.md | 78 | Acceptance Criteria | **Critical Code Paths Updated**: Provider initialization in GoogleMapWrapper.js and AzureMapWrapper.js use providerManager.setGoogleMap()/setAzureMap() | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-global-variable-deprecation.md | 79 | Acceptance Criteria | **Manual Test Suite Passed**: Provider switch during detection, rapid confidence filtering, and cancel-rerun-cancel scenarios validated without crashes or data corruption | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-global-variable-deprecation.md | 80 | Acceptance Criteria | **Deprecation Warnings Verified**: Browser console logs warnings when legacy code accesses deprecated globals (confirms soft migration active) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-global-variable-deprecation.md | 81 | Acceptance Criteria | **Code Review Clean**: Direct assignments to globals (window.googleMap =, Detection_detections.length =, progressTimer =) only in property descriptor definitions, not in usage code | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-global-variable-deprecation.md | 82 | Acceptance Criteria | **Documentation Complete**: ProviderStateManager method signatures documented, decision record created explaining race condition fixes | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 41 | File: `towerscout-domain.md` | **Current Status**: Update "Remaining Architecture Improvements" section | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 44 | File: `dev-workflow.md` | **Build Process**: Document concatenation-based build system | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 45 | File: `dev-workflow.md` | **Pre-commit Hooks**: Note automatic bundle rebuilding | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 46 | File: `dev-workflow.md` | **Module Structure**: Reference 7-directory organization | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 47 | File: `dev-workflow.md` | **Testing Procedures**: Add TASK-042 manual testing methodology | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 51 | File: `security.md` | **Input Validation**: Note current validation infrastructure (ts_validation.py) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 52 | File: `security.md` | **Rate Limiting**: Document rate limiting status | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 55 | File: `spec-driven-workflow.md` | Review for currency with Sprint 01/02 workflows | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 56 | File: `spec-driven-workflow.md` | Update if needed (check during review) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 59 | New Section Needed: `architecture.md` | **ProviderStateManager**: Document state management architecture | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 60 | New Section Needed: `architecture.md` | **TimerManager**: Document timer lifecycle management | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 61 | New Section Needed: `architecture.md` | **EventListenerManager**: Document DOM event tracking | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 62 | New Section Needed: `architecture.md` | **TowerScoutErrorHandler**: Document error handling patterns | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 63 | New Section Needed: `architecture.md` | **Migration Patterns**: Reference decision record TASK-043 | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 72 | File: `.agent_work/context/guides/TowerScout_Development_Setup_Guide.txt` | Add Sprint 01/02 completion summary | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 73 | File: `.agent_work/context/guides/TowerScout_Development_Setup_Guide.txt` | Note current architecture state (modular frontend) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 74 | File: `.agent_work/context/guides/TowerScout_Development_Setup_Guide.txt` | List known issues and their status | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 77 | File: `.agent_work/context/guides/TowerScout_Development_Setup_Guide.txt` | ~~Remove provider switch workarounds~~ (Already removed - verify) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 78 | File: `.agent_work/context/guides/TowerScout_Development_Setup_Guide.txt` | Add resolved issues from Sprint 01/02: - Memory management (TASK-041) - stress tests show 0.7% decrease - Interactive highlighting (TASK-031) - bidirectional list↔map - Azure Maps visual consistency (TASK-040) - transparency fixed - Boundary accumulation (TASK-045) - independent detection runs | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 85 | File: `.agent_work/context/guides/TowerScout_Development_Setup_Guide.txt` | Document current smooth highlighting behavior | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 86 | File: `.agent_work/context/guides/TowerScout_Development_Setup_Guide.txt` | Note confidence filtering stability | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 87 | File: `.agent_work/context/guides/TowerScout_Development_Setup_Guide.txt` | Add performance expectations (based on TASK-042): - 24 tiles: ~70 seconds, ~158 detections - 57 tiles: ~160 seconds, ~430 detections - Browser responsiveness excellent throughout | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 93 | File: `.agent_work/context/guides/TowerScout_Development_Setup_Guide.txt` | Remove resolved issues (provider switching, memory leaks, highlighting) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 94 | File: `.agent_work/context/guides/TowerScout_Development_Setup_Guide.txt` | Keep actual limitations: - Geocoding rate limiting at ~370 detections (working as designed) - Provider switching detection visibility (NEW-ISSUE-006, Sprint 03) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 104 | File: `.agent_work/context/guides/Azure-Maps-Local-Setup-Guide.md` | **Add**: Performance expectations section | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 105 | File: `.agent_work/context/guides/Azure-Maps-Local-Setup-Guide.md` | **Add**: Troubleshooting common Azure Maps issues | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 108 | File: `README.md` (if exists in webapp/) | Check if exists | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 109 | File: `README.md` (if exists in webapp/) | Update with current architecture if found | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 110 | File: `README.md` (if exists in webapp/) | Add quick start guide referencing setup documentation | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 117 | New File: `.agent_work/context/guides/Developer-Architecture-Guide.md` | **ProviderStateManager**: - Purpose: Centralized state management preventing race conditions - Key methods: Map state, detection state, progress timer - Property descriptors with deprecation warnings - Migration guide from global variables | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 123 | New File: `.agent_work/context/guides/Developer-Architecture-Guide.md` | **Frontend Module Structure**: ``` webapp/js/src/ ├── managers/ # State and lifecycle managers ├── boundaries/ # Boundary type implementations ├── providers/ # Map provider abstractions ├── detection/ # Detection workflow ├── ui/ # User interface modules └── utils/ # Shared utilities ``` | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 134 | New File: `.agent_work/context/guides/Developer-Architecture-Guide.md` | **Build System**: - Concatenation-based (not webpack/rollup) - Pre-commit hooks maintain synchronization - Source files in `webapp/js/src/` - Bundle output: `webapp/js/towerscout.js` - Build command: `node build.js` | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 141 | New File: `.agent_work/context/guides/Developer-Architecture-Guide.md` | **Testing Procedures**: - Manual testing methodology from TASK-042 - 4-stage user journey validation framework - Console logging for debugging - Performance benchmarking approach | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 147 | New File: `.agent_work/context/guides/Developer-Architecture-Guide.md` | **State Management Patterns**: - Reference decision record: 015-global-variable-migration-patterns.md - Property descriptor deprecation pattern - Mutex-protected state mutations - Event listener and timer cleanup | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 173 | Success Criteria | All workarounds removed or verified absent from user documentation | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 174 | Success Criteria | Sprint 01/02 achievements documented with specific examples | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 175 | Success Criteria | Setup guides reflect current architecture (27-file modular structure) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 176 | Success Criteria | Developer documentation includes ProviderStateManager architecture | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 177 | Success Criteria | Testing procedures from TASK-042 documented | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 178 | Success Criteria | No references to outdated workflows (monolithic frontend, apikey.txt) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 179 | Success Criteria | Performance expectations documented (based on TASK-042 benchmarks) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | 180 | Success Criteria | Known issues section updated (resolved vs. remaining) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-045-boundary-accumulation-bug.md | 46 | Acceptance Criteria | **Root cause identified**: Backend code location and data flow causing accumulation documented | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-045-boundary-accumulation-bug.md | 47 | Acceptance Criteria | **Session clearing implemented**: Flask session properly clears boundaries between detection runs | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-045-boundary-accumulation-bug.md | 48 | Acceptance Criteria | **Tile count accuracy**: Backend generates tiles matching frontend estimation (±10%) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-045-boundary-accumulation-bug.md | 49 | Acceptance Criteria | **No accumulation**: 3 consecutive test runs with different boundaries show no data cross-contamination | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-045-boundary-accumulation-bug.md | 50 | Acceptance Criteria | **Logging enhanced**: Backend logs boundary state transitions for debugging | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-045-boundary-accumulation-bug.md | 51 | Acceptance Criteria | **No regressions**: All existing detection functionality works correctly | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-045-boundary-accumulation-bug.md | 52 | Acceptance Criteria | **Documentation updated**: Session management best practices documented | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-045-boundary-accumulation-bug.md | 53 | Acceptance Criteria | **Manual testing passed**: Test procedure executed with 3 different boundaries | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-045-boundary-accumulation-bug.md | 54 | Acceptance Criteria | **Code review complete**: All changes peer-reviewed for session state handling | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 127 | Setup Wizard | Auto-appears on first launch when .env missing or contains placeholder keys | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 128 | Setup Wizard | Blocks app usage until configuration complete (cannot close wizard prematurely) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 129 | Setup Wizard | Multi-step flow: Welcome → API Keys → Provider Selection → Performance Info → Complete | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 130 | Setup Wizard | Google Maps API key input with validation indicator (✅/❌) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 131 | Setup Wizard | Azure Maps API key input with validation indicator (✅/❌) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 132 | Setup Wizard | Provider preference selection (radio buttons for Google/Azure default) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 133 | Setup Wizard | Performance info display shows recent detection statistics | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 134 | Setup Wizard | "Start Using TowerScout" button appears after successful configuration | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 135 | Setup Wizard | Successfully saves API keys to .env file | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 136 | Setup Wizard | Clears `needs_setup` session flag after completion | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 137 | Setup Wizard | Provides clear error messages for invalid keys | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 138 | Setup Wizard | Mobile-responsive design matching existing UI patterns | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 141 | Settings Screen | Accessible via settings icon (⚙️) in top navigation | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 142 | Settings Screen | Opens as modal overlay without clearing session state | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 143 | Settings Screen | Four sections: API Keys, Resources, Performance, System | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 144 | Settings Screen | API Keys section shows masked keys with "Show" toggle | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 145 | Settings Screen | Validation indicators (✅/❌) update on Save click | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 146 | Settings Screen | Resources section displays documentation links (placeholder URLs initially) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 147 | Settings Screen | Resources section displays video guide links (placeholder URLs initially) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 148 | Settings Screen | Performance section shows recent detection statistics (avg tiles/sec from last 5 sessions) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 149 | Settings Screen | Debug Mode toggle persists to localStorage | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 150 | Settings Screen | Clear Cache button successfully clears session and temp files | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 151 | Settings Screen | Close button (X) appears in top-right corner | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 152 | Settings Screen | Warns before closing with unsaved changes (dirty state detection) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 153 | Settings Screen | Successfully updates .env file without app restart | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 154 | Settings Screen | Preserves current detections and map view when opening/closing | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 157 | Backend Infrastructure | `/api/config/validate-key` endpoint validates Google Maps keys via test request | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 158 | Backend Infrastructure | `/api/config/validate-key` endpoint validates Azure Maps keys via test request | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 159 | Backend Infrastructure | `/api/config/save-keys` endpoint updates .env file with proper formatting | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 160 | Backend Infrastructure | `/api/config/save-keys` endpoint reloads runtime environment variables | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 161 | Backend Infrastructure | `/api/config/status` endpoint returns current key configuration state | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 162 | Backend Infrastructure | `/api/config/reset-session` endpoint clears Flask session successfully | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 163 | Backend Infrastructure | `/api/config/performance` endpoint returns recent detection statistics | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 164 | Backend Infrastructure | .env backup created before every write operation | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 165 | Backend Infrastructure | Maximum 5 backups maintained (auto-cleanup oldest) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 166 | Backend Infrastructure | Rollback mechanism works when validation fails | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 167 | Backend Infrastructure | Rate limiting applied to validation endpoints (prevent abuse) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 168 | Backend Infrastructure | All inputs sanitized via `TowerScoutValidator` class | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 171 | Docker Compatibility | .env updates persist across container restarts | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 172 | Docker Compatibility | Config directory mount pattern documented: `-v ./webapp/config:/app/webapp/config:rw` | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 173 | Docker Compatibility | Container user has write permissions (chmod 666) to config/.env | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 174 | Docker Compatibility | Python reads from `config/.env` path via `load_dotenv('config/.env')` | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 175 | Docker Compatibility | Integration tested in Docker environment with non-root user | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 178 | Error Handling | Invalid API key format shows clear error message | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 179 | Error Handling | Failed API validation shows provider-specific error | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 180 | Error Handling | File write errors trigger rollback with user notification | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 181 | Error Handling | Network errors during validation show retry option | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 182 | Error Handling | AJAX failures display user-friendly error messages | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 183 | Error Handling | All errors integrate with existing `TowerScoutErrorHandler` | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 186 | Performance | API key validation completes within 5 seconds | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 187 | Performance | .env file write/reload completes within 2 seconds | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 188 | Performance | Settings modal opens instantly (<500ms) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 189 | Performance | No noticeable performance impact on main application | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1358 | Functional Success | Setup Wizard auto-appears on first launch and blocks app until complete | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1359 | Functional Success | Settings modal provides seamless in-app configuration management | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1360 | Functional Success | API keys validated via test requests before saving | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1361 | Functional Success | Changes persist to host-mounted .env file (Docker-compatible) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1362 | Functional Success | Session state preserved when opening/closing Settings | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1363 | Functional Success | Clear error messages for all failure scenarios | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1366 | User Experience Success | Non-technical users can configure app without editing text files | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1367 | User Experience Success | Configuration process takes <5 minutes from start to finish | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1368 | User Experience Success | Mobile-responsive design works on phones/tablets | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1369 | User Experience Success | Consistent visual design matching existing application | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1370 | User Experience Success | Helpful contextual information (performance stats, resource links) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1373 | Technical Success | Zero .env file corruption incidents | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1374 | Technical Success | No security vulnerabilities introduced | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1375 | Technical Success | Performance targets met (validation <5s, save <2s, modal open <500ms) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1376 | Technical Success | Comprehensive test coverage (unit + integration + frontend) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1377 | Technical Success | Documentation complete and accurate | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1380 | Integration Success | Works seamlessly with Docker containerization (TASK-025) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1381 | Integration Success | No regressions in existing functionality | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1382 | Integration Success | Compatible with TASK-039 Google Maps provider management | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1383 | Integration Success | Integrates cleanly with existing error handling patterns | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1438 | Manual Verification Checklist | First launch: Setup Wizard appears automatically | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1439 | Manual Verification Checklist | Setup Wizard: All 5 steps navigate correctly | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1440 | Manual Verification Checklist | Setup Wizard: API key validation works for both providers | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1441 | Manual Verification Checklist | Setup Wizard: Invalid keys show error, valid keys show success | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1442 | Manual Verification Checklist | Setup Wizard: Configuration saves to .env correctly | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1443 | Manual Verification Checklist | Settings button: Opens modal without clearing session | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1444 | Manual Verification Checklist | Settings modal: Current keys load correctly (masked) | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1445 | Manual Verification Checklist | Settings modal: Validation runs on save | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1446 | Manual Verification Checklist | Settings modal: Unsaved changes warning appears | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1447 | Manual Verification Checklist | Settings modal: Debug mode toggle persists | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1448 | Manual Verification Checklist | Settings modal: Clear cache button works | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1449 | Manual Verification Checklist | Docker: Volume mount pattern works correctly | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1450 | Manual Verification Checklist | Docker: .env changes persist across container restarts | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1451 | Manual Verification Checklist | Mobile: Responsive design works on phone/tablet | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | 1452 | Manual Verification Checklist | Performance: All actions complete within target times | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-066-release-candidate-validation-gate.md | 52 | Acceptance Criteria | If GPU support is claimed for the RC, `-Gpu auto` and `-Gpu on` are validated on an NVIDIA Docker Desktop WSL2 host with readiness diagnostics, fixed-fixture CPU/GPU output parity, and timing evidence. | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-066-release-candidate-validation-gate.md | 353 | Acceptance Criteria Validation | NVIDIA Docker Desktop WSL2 GPU evidence - PENDING separate GPU host validation before any broad GPU support claim. | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-066-release-candidate-validation-gate.md | 354 | Acceptance Criteria Validation | Docker-Desktop-free Podman evidence - PENDING clean-host validation with a provider that does not depend on Docker Desktop's external Compose binary. | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-081-rc3-runtime-hardening-podman-independence.md | 124 | Acceptance Criteria | `.agent_work` validation passes after task and implementation updates. | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-081-rc3-runtime-hardening-podman-independence.md | 303 | Acceptance Criteria Validation | **GPU runtime validation**: blocked on this host because NVIDIA runtime evidence is unavailable. | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-081-rc3-runtime-hardening-podman-independence.md | 322 | Test Results | Full-tree secret scan - NOT CLEAN: surfaced pre-existing sensitive-term findings in older docs/artifacts and hit a console encoding error; not introduced by this change set. | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-081-rc3-runtime-hardening-podman-independence.md | 338 | Test Results | GPU smoke - BLOCKED: `nvidia-smi` is not available on this host and no NVIDIA runtime evidence has been captured. | Historical task | No | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-088-stable-release-and-handoff-closeout.md | 123 | May land immediately after merge without blocking TASK-088 start | Shared rate-limiter key scoping and a non-interference test if the team wants that hygiene landed before package validation. | Historical task | No | Historical checklist residue; do not reopen without owner reselection.

## Source Register
Reviewed Documentation Source Register
Inventory of Markdown documentation under .agent_work/tasks and the requested Handoff-Planning and Reprioritization Effort folders.
Path | Authority / lifecycle | Lines | Bytes | Review method | Interpretation guidance
.agent_work/context/status/Handoff-Planning/2026-07-23-OCTOBER-FIX-FIRST-IMPLEMENTATION-ROADMAP.md | Historical roadmap | 289 | 13253 | Full read for controlling/current guides; structured scan for historical evidence files | Immediate PR #67/Task-087 sequence is superseded; milestones remain context.
.agent_work/context/status/Handoff-Planning/PILOT-FEEDBACK-AND-CDC-AI-ADOPTION-PLAN.md | Supporting or historical status | 129 | 5852 | Full read for controlling/current guides; structured scan for historical evidence files | Consult current board and source precedence before treating as work.
.agent_work/context/status/Handoff-Planning/PILOT-OPERATIONS-PACKET.md | Supporting or historical status | 67 | 2895 | Full read for controlling/current guides; structured scan for historical evidence files | Consult current board and source precedence before treating as work.
.agent_work/context/status/Handoff-Planning/README.md | Supporting or historical status | 64 | 3678 | Full read for controlling/current guides; structured scan for historical evidence files | Consult current board and source precedence before treating as work.
.agent_work/context/status/Handoff-Planning/v0.1.2-Validation-Evidence/RUNLOG.md | Supporting or historical status | 125 | 16587 | Full read for controlling/current guides; structured scan for historical evidence files | Consult current board and source precedence before treating as work.
.agent_work/context/status/Handoff-Planning/v0.1.2-Validation-Evidence/V012-FULL-MATRIX-QA-2026-07-09.md | Supporting or historical status | 43 | 5087 | Full read for controlling/current guides; structured scan for historical evidence files | Consult current board and source precedence before treating as work.
.agent_work/context/status/Handoff-Planning/v0.1.2-Validation-Evidence/V012-Validation-Methodology-and-Reproduction-Guide.md | Supporting or historical status | 108 | 15018 | Full read for controlling/current guides; structured scan for historical evidence files | Consult current board and source precedence before treating as work.
.agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | Current suggested closeout guide | 224 | 36538 | Full read for controlling/current guides; structured scan for historical evidence files | Mapped into release, documentation, sanitization, backlog, and handoff actions.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2-verification.md | Supporting or historical status | 95 | 11291 | Full read for controlling/current guides; structured scan for historical evidence files | Consult current board and source precedence before treating as work.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | Current controlling work plan | 542 | 73998 | Full read for controlling/current guides; structured scan for historical evidence files | Use the W00-W10 Crosswalk; unchecked plan boxes were not maintained as a live tracker.
.agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-prioritization-v2.md | Supporting or historical status | 134 | 16894 | Full read for controlling/current guides; structured scan for historical evidence files | Consult current board and source precedence before treating as work.
.agent_work/tasks/active/TASK-068-windows-script-validation.md | Completed current-sprint record | 130 | 5753 | Full read for current task or structured current-status review | Completed; retain until sprint closeout.
.agent_work/tasks/active/TASK-087/live-wrapper-validation-2026-07-06.md | Current task detail | 203 | 8639 | Structured documentation scan | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-087-host-side-tls-repair-control-plane.md | Current task detail | 3167 | 169388 | Full read for current task or structured current-status review | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-089-cdcai-migration-execution.md | Current task detail | 384 | 21276 | Full read for current task or structured current-status review | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-091-owner-runnable-release-qualification.md | Current task detail | 438 | 25579 | Full read for current task or structured current-status review | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-092-documentation-currentness.md | Current task detail | 53 | 2738 | Full read for current task or structured current-status review | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-093-persistent-data-recovery.md | Current task detail | 64 | 3127 | Full read for current task or structured current-status review | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-095-governance-ai-ready-handoff.md | Current task detail | 346 | 17016 | Full read for current task or structured current-status review | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-097-podman-final-path-qualification.md | Current task detail | 131 | 6747 | Full read for current task or structured current-status review | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-099-august-dependency-advisory-follow-up.md | Completed current-sprint record | 383 | 18116 | Full read for current task or structured current-status review | Completed; retain until sprint closeout.
.agent_work/tasks/active/TASK-101-extract-zip-advisory-release-gate.md | Completed / superseded | 336 | 17451 | Full read for current task or structured current-status review | PR #67 integration boxes were superseded by ADR-021.
.agent_work/tasks/active/TASK-103/DEPENDENCY-SECURITY-DISPOSITION.md | Current task detail | 37 | 2235 | Structured evidence/status scan; current open gates reconciled | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-103/NVIDIA-RUNTIME-COMPONENT-INVENTORY.md | Current task detail | 64 | 2842 | Structured evidence/status scan; current open gates reconciled | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-103/PHASE2-EVIDENCE-INDEX.md | Current task detail | 108 | 6126 | Structured evidence/status scan; current open gates reconciled | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-103/T1000-EVIDENCE-POINTER.md | Current task detail | 14 | 665 | Structured evidence/status scan; current open gates reconciled | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-103/TASK103-IMPLEMENTATION-BRIEF-V3-2026-09-24.md | Current task detail | 452 | 41760 | Structured evidence/status scan; current open gates reconciled | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-103/TRACK-L-EVIDENCE-INDEX.md | Current task detail | 36 | 1849 | Structured evidence/status scan; current open gates reconciled | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-103/W09-EVIDENCE-INDEX.md | Current task detail | 255 | 16384 | Structured evidence/status scan; current open gates reconciled | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-103/W10-LOCAL-FIRST-HOST-EVIDENCE-INDEX.md | Current task detail | 534 | 32409 | Structured evidence/status scan; current open gates reconciled | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/active/TASK-103-cuda128-blackwell-ml-runtime.md | Current task detail | 171 | 9826 | Full read for current task or structured current-status review | Reconcile with the curated Open Actions sheet and current board.
.agent_work/tasks/completed/TASK-025/TASK-025-CONTAINERIZATION-DECISION-ANALYSIS-2026-05-01.md | Historical task | 1748 | 74000 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-025/TASK-025-V1-RUNTIME-CONTRACT-2026-05-05.md | Historical task | 282 | 17101 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-025-docker-containerization.md | Historical task | 1105 | 121167 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-031-interactive-highlighting.md | Historical task | 239 | 9508 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-manual-tower-addition.md | Historical task | 1605 | 72475 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-phase-0-gap-analysis.md | Historical task | 588 | 18113 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-033/TASK-033-PHASE4-DESIGN-DECISIONS.md | Historical task | 277 | 9548 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-IMPLEMENTATION-SUMMARY.md | Historical task | 343 | 11655 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-memory-management.md | Historical task | 409 | 18040 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-035-TESTING-PLAN.md | Historical task | 396 | 10908 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-036/TASK-036-SCOPE-ANALYSIS.md | Historical task | 281 | 8362 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-036/TASK-036-TESTING-CHECKLIST.md | Historical task | 392 | 10854 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-037-UPDATE-SUMMARY.md | Historical task | 107 | 4926 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-037-user-journey-verification.md | Historical task | 1782 | 78615 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-038/INFRASTRUCTURE-README.md | Historical task | 242 | 6994 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-038-COMPLETION-SUMMARY.md | Historical task | 464 | 16668 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-038-frontend-refactoring.md | Historical task | 944 | 38715 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-emergency-geocoding-fixes.md | Historical task | 1066 | 46675 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-039-google-maps-api-upgrade.md | Historical task | 2472 | 101343 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-040-azure-maps-visual-consistency.md | Historical task | 1235 | 48687 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-041-deep-dive-priority-2.md | Historical task | 2733 | 101288 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-042-testing-action-log.md | Historical task | 105 | 3887 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-CLEANUP-PLAN.md | Historical task | 325 | 10393 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-CLEANUP-TESTING.md | Historical task | 400 | 12529 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-043-global-variable-deprecation.md | Historical task | 815 | 47819 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-044-documentation-updates.md | Historical task | 246 | 9235 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-045-boundary-accumulation-bug.md | Historical task | 766 | 33704 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-046-setup-wizard-settings-screen.md | Historical task | 1972 | 83684 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-047-ui-formatting-and-polish.md | Historical task | 290 | 26600 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-049-legacy-code-cleanup.md | Historical task | 232 | 16176 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-050-full-repo-stale-code-and-performance-audit.md | Historical task | 167 | 8913 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-051/TASK-051-cuda-packaging-and-enablement-audit.md | Historical task | 111 | 4630 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-051/TASK-051-dependency-doc-truth-table.md | Historical task | 63 | 5036 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-051/TASK-051-phase-1-decision-memo.md | Historical task | 171 | 7087 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-051/TASK-051-runtime-dependency-matrix.md | Historical task | 100 | 8166 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-051-runtime-dependency-audit-and-decision-gate.md | Historical task | 526 | 33809 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-052-current-integration-smoke-test-baseline.md | Historical task | 156 | 9522 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-053-detection-workflow-stabilization.md | Historical task | 605 | 62950 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-054-local-launch-ux.md | Historical task | 192 | 18506 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-055-yolo-torch-hub-pinned-ref-hardening.md | Historical task | 208 | 10370 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-056/TASK-056-clean-cpu-first-run-proof.md | Historical task | 141 | 6601 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-056-first-run-reliability-and-runtime-determinism-hardening.md | Historical task | 251 | 16476 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-057/TASK-057-broader-app-and-host-smoke.md | Historical task | 116 | 3899 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-057/TASK-057-clean-local-yolo-first-run-proof.md | Historical task | 133 | 6690 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-057/TASK-057-runtime-scope-correction.md | Historical task | 18 | 3047 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-057-local-yolo-runtime-ownership-and-offline-readiness.md | Historical task | 189 | 12916 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-062/TASK-062-runtime-scope-and-loader-contract.md | Historical task | 54 | 1818 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-062-pre-docker-runtime-cleanup-and-yolo-loader-hardening.md | Historical task | 212 | 8943 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-063-pre-docker-release-hardening.md | Historical task | 226 | 22697 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-064-runtime-responsiveness-inference-baseline.md | Historical task | 172 | 16414 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-065/evidence/TASK-065-browser-provider-regression.md | Historical task | 88 | 3345 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-065/evidence/TASK-065-podman-compose-provider-validation.md | Historical task | 77 | 2815 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-065/TASK-025-TO-065-RELEASE-READINESS-ANALYSIS.md | Historical task | 335 | 15430 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-065-release-packaging-runtime-support.md | Historical task | 196 | 26409 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-066-release-candidate-validation-gate.md | Historical task | 396 | 50416 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-067-ci-release-gate-tightening.md | Historical task | 117 | 7673 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-069/TASK-069-AGPL-YOLO-RELEASE-IMPLEMENTATION-2026-05-13.md | Historical task | 77 | 6068 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-069/TASK-069-FINAL-REVIEW-PATH-FORWARD-2026-05-13.md | Historical task | 359 | 16034 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-069/TASK-069-FINAL-STRATEGY-ROADMAP-2026-05-12.md | Historical task | 676 | 27471 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-069/TASK-069-FINALIZATION-PLAN-REVIEW-2026-05-12.md | Historical task | 242 | 14605 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-069/TASK-069-OPEN-SOURCE-COMPLIANCE-STRATEGY-2026-05-12.md | Historical task | 462 | 22060 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-069/TASK-069-REVIEWER-RESPONSE-CRITIQUE-2026-05-12.md | Historical task | 320 | 15975 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-069/TASK-069-SIGN-OFF-PLAN-2026-05-14.md | Historical task | 56 | 4345 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-069/TASK-069-V2-STRATEGY-FEEDBACK-2026-05-12.md | Historical task | 332 | 15183 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-071-end-user-release-docs.md | Historical task | 223 | 23004 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-072-release-asset-bundle-contract.md | Historical task | 203 | 21047 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-073-clean-machine-uat-plan.md | Historical task | 615 | 55065 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-074/task-074-runtime-prerequisite-preflight-review-brief.md | Historical task | 407 | 17319 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-074-runtime-prerequisite-preflight.md | Historical task | 200 | 27516 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-075-single-gpu-capable-package.md | Historical task | 208 | 26692 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-079/task-079-single-gpu-capable-package-plan.md | Historical task | 314 | 18523 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-079-rc1-reliability-fixes.md | Historical task | 394 | 51947 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-080-uat-user-guide-process-simplification.md | Historical task | 1038 | 60825 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-081-rc3-runtime-hardening-podman-independence.md | Historical task | 363 | 27614 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-082-rc4-docs-package-organization.md | Historical task | 479 | 30304 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-083-rc5-podman-independence-gpu-release.md | Historical task | 575 | 42350 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-084/evidence/TowerScout-rc6-gpu-validation-evidence-emailsafe/TowerScout-rc6-gpu-validation-evidence/ARTIFACT-PROVENANCE.md | Historical task | 71 | 3916 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-084/evidence/TowerScout-rc6-gpu-validation-evidence-emailsafe/TowerScout-rc6-gpu-validation-evidence/PUBLIC-SUMMARY.md | Historical task | 60 | 3101 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-084/final-package-gate-checklist-2026-06-16.md | Historical task | 290 | 15608 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-084/official-rc6-release-handoff-2026-06-17.md | Historical task | 138 | 6777 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-084/official-rc6-release-notes.md | Historical task | 66 | 3025 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-084-ga-packaging-hardening-and-podman-provider-onboarding.md | Historical task | 915 | 52139 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-085-dataset-zip-restore-path-traversal-hardening.md | Historical task | 122 | 5585 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-086/official-rc7.1-release-notes-2026-06-29.md | Historical task | 59 | 2798 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-086-provider-tls-auto-repair-and-setup-triage.md | Historical task | 1331 | 78883 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-088-stable-release-and-handoff-closeout.md | Historical task | 987 | 59983 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-090/alert-disposition.md | Historical task | 202 | 16664 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-090/remediation-scope.md | Historical task | 125 | 7530 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-090-runtime-custom-image-dependency-security.md | Historical task | 205 | 8896 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-098/baseline.md | Historical task | 178 | 8499 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.
.agent_work/tasks/completed/TASK-098-dependency-security-remediation.md | Historical task | 1322 | 71375 | Structured metadata and unchecked-checklist scan; historical body not treated as current authority | Historical checklist residue; do not reopen without owner reselection.