## Plan Overview
TowerScout Project-End Plan: October 1-31, 2026
First draft. Simple language is used so the plan can be followed without knowing TowerScout task numbers. October 30 is operational closeout; October 31 is Saturday and the hard end date.
Category | Topic | Explanation
Calendar | Planning window | October 1 through October 30, 2026; October 31 is Saturday and the hard project end.
Calendar | Weekdays available | 22 weekdays when only weekends are excluded; 21 if October 12 is a non-working holiday.
Assessment | Feasibility | Feasible but tight. The plan reserves 3 person-days of contingency and requires documentation/handoff work to overlap technical testing.
Main risk | External availability | Independent Windows hardware/tester and owner/backup time must be booked by October 2.
Current release state | Package | Existing rc4 local evidence is useful, but a new control-package identity is required because packaged manuals changed.
Current release state | Signing | TowerScout stays unsigned under ADR-023; signature-enforcing managed endpoints are outside the standard support claim.
Must finish before freeze | October 9 | Replacement ZIPs, integrity/local checks, official hashes, browser-download proof, and shipped documentation.
Must finish before acceptance | October 16 | Independent four-profile/recovery evidence, final reconciliation, external guide/video readiness, and owner-guide review.
Must finish before rehearsal | October 23 | Owner guide, release notes, custody map, backlog review, media custody, adoption decision or fallback.
Must finish before closeout | October 30 | Authorized adoption or migration-ready fallback, access/custody transfer, backlog cutover, sanitization delta, and sign-off.
Scope rule | Optional work | Do not begin conditional or deferred backlog items unless they become direct acceptance blockers.
Authorization rule | External changes | Publishing, cdcai mutation, account changes, and signing require normal owner authorization.

## Weekly Plan
Prioritized Week-by-Week Project-End Plan
Technical acceptance, documentation, media, sanitization, owner transfer, and contingency are planned together. Filter by Week, Priority, Starting status, or action IDs.
Plan ID | Week | Dates | Priority | Activity | Simple explanation | Why this happens now | Estimated person-days | Owner / participants | Depends on | Expected deliverable | Done when | Must finish by | Starting status | Backlog action IDs
P01 | Opening days | Oct 1-2 | Critical | Accept the unsigned-package manuals | Finish the wording that tells users the package is unsigned, how to verify it, and what computers are outside support. | The manuals are package files; every later package test depends on them. | 0.5 | Documentation owner; release owner | ADR-023 decision | Approved package text | Owner accepts the text and conflict scan is clean. | Oct 2 | In progress | R01,D01
P02 | Opening days | Oct 1-2 | Critical | Book the independent test and owner sessions | Reserve the independent Windows computer, tester, provider access, owner review, and rehearsal times now. | People and suitable hardware are the largest schedule risk. | 0.25 | Project lead; test owner; receiving owner | Owner calendars and host availability | Named dates, roles, and host capability inventory | Every external session has an owner and date. | Oct 2 | Blocked / external | R08,H03,H04
P03 | Opening days | Oct 1-2 | High | Start the owner guide and final backlog | Draft plain-language maintenance instructions and use the comprehensive backlog as the source for the owner-facing version. | These can be prepared while package work is underway and should not be left until the last week. | 1.0 | Maintainer; project lead | Current procedures and this inventory | Owner-guide outline and proposed post-handoff backlog | All required chapters and every carried item have an owner/due date placeholder. | Oct 5 | Open | H01,H07
P04 | Opening days | Oct 1-2 | High | Plan the video and sanitization review | Write the shot list and define exactly what source, packages, evidence, and media will be checked for private information. | Good preparation prevents rushed recordings and unsafe broad scans. | 0.75 | Recorder; security reviewer | Permitted demo area and transfer scope | Video storyboard and sanitization inventory | Recording/privacy choices and transfer categories are written down. | Oct 2 | Open | D07,S01
P05 | Week 1 | Oct 5-6 | Critical | Build and inspect the replacement packages | Give the package a new name, build new CPU/CUDA ZIPs, and verify every checksum, manifest, notice, script, guide, and exclusion. | The old ZIPs contain older manuals and cannot be final downloads. | 1.5 | Release implementer; reviewer | P01; accepted source/images/assets | Two verified replacement control ZIPs | Sidecars/internal checks/manifests/allowlists and secret hygiene pass. | Oct 6 | Blocked by approved docs | R02,R03,R04
P06 | Week 1 | Oct 6-8 | Critical | Repeat local package checks | Use the replacement ZIPs across Docker/Podman CPU/GPU and confirm setup, devices, volumes, stop, and relaunch still work. | A documentation-only ZIP change still creates different distributed bytes. | 1.5 | Release implementer | P05; Docker and Podman available | Replacement-package W09 evidence | Affected cells cite the new hashes and pass. | Oct 8 | Open | R05
P07 | Week 1 | Oct 7-9 | Critical | Publish hashes and perform the real browser-download test | Put the exact hashes in the trusted release record, download through a browser, verify before extraction, and run as an ordinary user. | This is the main proof required by the unsigned-package decision. | 0.75 | Release owner; ordinary-user tester | P05; owner-approved record | Hash/MOTW/wrapper evidence | The exact browser download works without changing persistent policy. | Oct 9 | Blocked by package identity | R06,R07
P08 | Week 1 | Oct 5-9 | High | Finish shipped docs, owner guide v1, and video dry-run | Check Markdown, HTML, Help pages, package copies, Podman Python wording, admin model guidance, and the planned video path. | All shipped instructions must freeze with the candidate. | 1.5 | Documentation owner; owner-guide reviewer; recorder | P05-P06 | Frozen guides, owner guide v1, successful video dry-run | The ZIP and running app show the intended guide versions and working links. | Oct 9 | In progress | D01,D02,D05,D06,D08,H01
P09 | Week 1 | Oct 5-9 | High | Resolve early sanitization and access gaps | Use controlled redacting methods, fix real findings, and confirm repository/package/media access for primary and backup owners. | Late discovery of a credential or access gap could block closeout. | 1.0 | Security reviewer; owner; account admins | P04 | Finding dispositions and access matrix | No unresolved high-risk finding or unnamed access owner remains. | Oct 9 | Open | S02,H04,A05
M1 | Milestone | Oct 9 | Critical | Freeze the final candidate | Stop changing shipped code and package documents except for a true release blocker. | Independent acceptance needs stable bytes. | 0.0 | Release owner | P05-P09 | Frozen source, images, ZIPs, assets, tools, fixtures, and guides | Every identity/hash is recorded and exact tester downloads are available. | Oct 9 | Open milestone | R02-R07,D01-D02
P10 | Week 2 | Oct 12-15 | Critical | Run independent four-profile acceptance | On the independent computer, repeat Docker CPU/GPU and Podman CPU/GPU using only the shipped instructions. | First-host success is not enough for the full support claim. | 3.0 | Independent tester; release implementer available for observation | M1; booked host; provider access | Four independent profile records | Models/devices, Google/Azure, exports, cancel/error recovery, and target identity pass. | Oct 15 | Blocked by host and frozen package | R09,R10,R11,R12,D05
P11 | Week 2 | Oct 15-16 | Critical | Repeat reboot, persistence, and recovery | Confirm settings, providers, assets, sessions, exports, and all eight volumes survive the required failure and reboot checks. | This is the final data-safety proof. | 1.0 | Independent tester | P10; permission to reboot | Independent recovery matrix | No destructive cleanup is used and successful state remains usable. | Oct 16 | Blocked by P10 | R13
P12 | Week 2 | Oct 12-16 | High | Finish public materials and candidate sanitization | Update the external setup guide, create the final video, review every frame, and inspect final source/package/media outputs. | User materials must match the accepted workflow and be safe to distribute. | 2.0 (can overlap testing) | Documentation owner; recorder; security reviewer | M1; final workflow stable | Setup guide, video, transcript/captions, candidate sanitization record | Written guide works without the video and media contains no private values. | Oct 16 | Open | D03,D09,S03
P13 | Week 2 | Oct 15-16 | Critical | Reconcile evidence and decide acceptance | Review every result and either accept all four profiles or describe the exact qualified subset. | No release claim should be made from partial or mismatched evidence. | 0.75 | Release owner; project lead; independent reviewer | P10-P12 | Final acceptance matrix and decision | All hashes/digests/hosts/skips/limitations agree and owners sign the result. | Oct 16 | Open | R14,R15,Q01
P14 | Week 2 | Oct 12-16 | High | Owner reviews the operating guide | The owner and backup walk through responsibilities, access, routine checks, release, recovery, and support instructions. | This leaves one week to fix handoff gaps before the formal rehearsal. | 0.5 (owner time) | Receiving owner and backup | P03,P08,P09 | Reviewed owner guide and rehearsal checklist | Comments are resolved or assigned. | Oct 16 | Blocked by guide/access | H02,H03,H05
M2 | Milestone | Oct 16 | Critical | Complete acceptance | Finish technical acceptance and make user documentation/video ready for approved distribution. | This protects the remaining two weeks for owner transfer and closeout. | 0.0 | Project lead; release owner | P10-P14 | Accepted release or precise blocked subset | Decision, evidence, docs, and known limits are complete. | Oct 16 | Open milestone | R15
P15 | Week 3 | Oct 19-21 | Critical | Use contingency only for real blockers | If acceptance found a defect, make the smallest fix, issue a new identity, and rerun affected checks. Otherwise preserve this time as buffer. | Late optional work would endanger handoff. | 0-2.0 reserved | Release implementer; reviewer | M2 findings | Corrected evidence or preserved unused buffer | No untracked byte change enters the release. | Oct 21 | Reserved contingency | Q03
P16 | Week 3 | Oct 19-22 | High | Prepare release notes, custody map, and migration packet | Fill in final hashes/links/results and document exactly where source, packages, models, evidence, guides, video, and backlog are held. | The owner rehearsal needs final, not placeholder, information. | 1.25 | Maintainer; release owner | M2; P12 | Release notes, custody index, migration-ready packet | All identities and locations are current and no secret is copied into public records. | Oct 22 | Open | D04,H12,A02,Q02
P17 | Week 3 | Oct 19-23 | Critical | Run the owner-operated rehearsal | The owner performs the important release, diagnosis, recovery, and backlog steps with minimal help. | This proves the project can continue after October 31. | 1.0 | Receiving owner; backup; maintainer observes | M2; P14; P16 | Owner rehearsal record and corrected guide | Owner completes critical procedures and remaining assistance is documented. | Oct 23 | Blocked by owner availability | H06
P18 | Week 3 | Oct 19-23 | High | Review backlog and adoption decision | Agree 30/60/90-day priorities, choose the backlog destination, review pilot feedback, and approve or decline cdcai adoption. | The final week depends on whether official transfer is authorized. | 0.75 (owner time) | Project lead; receiving owner; cdcai owner | M2; P16-P17 | Backlog priorities and explicit adoption decision | The baseline, official identity next step, and destination are named. | Oct 23 | Owner-gated | H08,H10,H11,A01,A03,A04
P19 | Week 3 | Oct 19-23 | High | Finish independent video review and media custody | A tester repeats the video path and the owner receives all editable and hosted media assets. | Media that only the outgoing developer controls is not handed off. | 0.5 | Independent tester; recorder; receiving owner | P12 | Video acceptance and custody record | Audience access works and owner can maintain the source files. | Oct 23 | Open | D10
M3 | Milestone | Oct 23 | Critical | Complete owner rehearsal | Owner can operate the release and the adoption path is either authorized or safely deferred. | This leaves one week for transfer verification and sign-off. | 0.0 | Receiving owner; project lead | P16-P19 | Rehearsal sign-off and adoption path | No critical procedure depends only on the outgoing developer. | Oct 23 | Open milestone | H06,A03
P20 | Week 4 | Oct 26-29 | Critical | Execute approved adoption or preserve the fallback | If approved, build/publish official cdcai artifacts and verify them. If not approved, leave cdcai unchanged and deliver the migration-ready packet. | The deadline does not authorize external changes by itself. | 1.5-2.5 | cdcai maintainer; release owner; independent tester | M3; explicit authorization | Official verified release or documented no-adoption handoff | Every external action is authorized and verified, or explicitly not performed. | Oct 29 | Owner-gated | A06,A07,A08,A09,A11
P21 | Week 4 | Oct 26-30 | Critical | Cut over backlog, access, and custody | Move the accepted backlog to one owner-controlled location and verify all repository/package/media/support access. | The new owner needs one trustworthy operating surface after closeout. | 0.75 | Receiving owner; maintainer | M3; H08/H11 decisions | Canonical backlog and final access/custody record | Old boards are clearly historical and every needed destination is accessible. | Oct 30 | Open | H09,A10,H04,H12
P22 | Week 4 | Oct 29-30 | Critical | Run final sanitization delta and sign off | Check late changes, record limitations/residuals, close task dispositions, and sign operational closeout. | October 31 is Saturday and no work should remain for the outgoing developer. | 0.75 | Security reviewer; project lead; receiving owner | P20-P21 | Final sanitization record and closeout sign-off | No unresolved critical exposure, ownership gap, hidden release gate, or outgoing-developer dependency remains. | Oct 30 | Open | S04,H13
M4 | Milestone | Oct 30 | Critical | Operational closeout | End with either completed adoption or a complete migration-ready handoff. | The hard project end is October 31, a Saturday. | 0.0 | Project lead; receiving owner | P20-P22 | Signed project-end state | The owner has artifacts, access, procedures, backlog, and named follow-ups. | Oct 30 | Open milestone | H13,A11

## Workday Calendar
Available Workdays Through Operational Closeout
There are 22 Monday-Friday dates from October 1 through October 30. Confirm whether October 12 is a non-working holiday for the actual team.
Workday number | Date | Day | Plan week | Primary focus | Milestone / note
1 | 2026-10-01 | Thursday | Opening days | Decisions, scheduling, owner guide/backlog/video/sanitization setup | Book external people and hosts
2 | 2026-10-02 | Friday | Opening days | Decisions, scheduling, owner guide/backlog/video/sanitization setup | Book external people and hosts
3 | 2026-10-05 | Monday | Week 1 | Replacement packages, local validation, browser download, shipped docs | Normal planned workday
4 | 2026-10-06 | Tuesday | Week 1 | Replacement packages, local validation, browser download, shipped docs | Normal planned workday
5 | 2026-10-07 | Wednesday | Week 1 | Replacement packages, local validation, browser download, shipped docs | Normal planned workday
6 | 2026-10-08 | Thursday | Week 1 | Replacement packages, local validation, browser download, shipped docs | Normal planned workday
7 | 2026-10-09 | Friday | Week 1 | Replacement packages, local validation, browser download, shipped docs | Candidate freeze
8 | 2026-10-12 | Monday | Week 2 | Independent four-profile testing, recovery, user materials, owner guide review | Possible U.S. federal holiday; confirm team availability
9 | 2026-10-13 | Tuesday | Week 2 | Independent four-profile testing, recovery, user materials, owner guide review | Normal planned workday
10 | 2026-10-14 | Wednesday | Week 2 | Independent four-profile testing, recovery, user materials, owner guide review | Normal planned workday
11 | 2026-10-15 | Thursday | Week 2 | Independent four-profile testing, recovery, user materials, owner guide review | Normal planned workday
12 | 2026-10-16 | Friday | Week 2 | Independent four-profile testing, recovery, user materials, owner guide review | Acceptance complete
13 | 2026-10-19 | Monday | Week 3 | Contingency fixes, final evidence, owner rehearsal, adoption decision | Normal planned workday
14 | 2026-10-20 | Tuesday | Week 3 | Contingency fixes, final evidence, owner rehearsal, adoption decision | Normal planned workday
15 | 2026-10-21 | Wednesday | Week 3 | Contingency fixes, final evidence, owner rehearsal, adoption decision | Normal planned workday
16 | 2026-10-22 | Thursday | Week 3 | Contingency fixes, final evidence, owner rehearsal, adoption decision | Normal planned workday
17 | 2026-10-23 | Friday | Week 3 | Contingency fixes, final evidence, owner rehearsal, adoption decision | Owner rehearsal complete
18 | 2026-10-26 | Monday | Week 4 | Authorized adoption or fallback, transfer verification, backlog cutover, sign-off | Normal planned workday
19 | 2026-10-27 | Tuesday | Week 4 | Authorized adoption or fallback, transfer verification, backlog cutover, sign-off | Normal planned workday
20 | 2026-10-28 | Wednesday | Week 4 | Authorized adoption or fallback, transfer verification, backlog cutover, sign-off | Normal planned workday
21 | 2026-10-29 | Thursday | Week 4 | Authorized adoption or fallback, transfer verification, backlog cutover, sign-off | Normal planned workday
22 | 2026-10-30 | Friday | Week 4 | Authorized adoption or fallback, transfer verification, backlog cutover, sign-off | Operational closeout
— | 2026-10-31 | Saturday | Project end | No planned outgoing-developer work | Hard project end

## Milestones
Project-End Milestones and Stop Rules
A missed gate changes the forecast or qualified subset. It does not reduce the acceptance standard or silently remove handoff work.
Date | Milestone | Required outcome | If it is missed
October 2 | External sessions and preparation locked | Independent host/tester, owner review/rehearsal, video plan, sanitization scope, and initial handoff work have owners/dates. | If host/owner time is not reserved, mark the plan AT_RISK immediately.
October 9 | Final candidate freeze | Replacement ZIPs, hashes, local checks, browser-download proof, shipped docs, and security review are complete. | After this date, only release blockers may change shipped bytes; use a new identity and rerun affected checks.
October 16 | Acceptance complete | Independent four-profile/recovery evidence is reconciled; user docs/video and owner-guide review are ready. | If cells remain incomplete, report the exact qualified subset rather than relaxing acceptance.
October 23 | Owner rehearsal complete | Owner can perform release/recovery/support procedures; backlog and adoption decisions are recorded. | If adoption is not approved, finalize the migration-ready fallback.
October 30 | Operational closeout | Access, custody, backlog, sanitization, adoption/fallback, and final sign-off are complete. | No planned work may depend on the outgoing developer after this date.
October 31 | Hard project end | Saturday; no project work is scheduled. | Emergency work is not part of this plan.

## Capacity
Primary-Implementer Capacity Allocation
Planning allowances, not promises. Owner/tester time is additional and must be scheduled. Optional work is excluded.
Work allocation | Reserved person-days | Necessity | What is included
Replacement package and local requalification | 3 | Required | New ZIP identity, integrity checks, local four-profile affected checks, browser-download proof.
Independent acceptance and recovery | 4 | Required | Four profiles plus reboot/persistence/recovery and final evidence reconciliation.
Public, in-app, external documentation | 2 | Required | Shipped docs, external Setup Guide, release notes, Help/link verification.
Installation/demo video | 1.5 | Required handoff deliverable | Storyboard, dry run, capture/edit/captions/privacy review, tester comparison, custody.
Owner guide and rehearsal | 2.5 | Required | Guide, role/cadence review, walkthrough, owner-operated rehearsal.
Sanitization | 1.5 | Required | Early scope/scan, candidate review, final delta.
Backlog and governance | 1.5 | Required | Owner-facing backlog, task disposition, canonical cutover, optional AI/Issues decisions.
Adoption, access, publication, closeout | 2.5 | Owner-gated | Permissions, adoption/fallback, official transfer if approved, consumer verification, sign-off.
Contingency | 3 | Protected buffer | Blocker correction, reruns, owner delays, limited media/document correction.
Total planned primary-implementer capacity | 21.5 | Fits 22 weekdays | Leaves only 0.5 day unallocated; if October 12 is non-working, nearly all slack is consumed.

## Risks and Decisions
Schedule Risks and Required Decisions
These are the conditions most likely to make the plan fail. The mitigation should be started by the stated trigger, not after the milestone is missed.
Risk ID | Risk | Severity | Mitigation | Owner | Trigger / decision rule
K01 | Independent host or tester is not booked | Critical | Reserve by October 2; record anonymous host capability and a backup window. | Project lead / test owner | If missing by Oct 2, status becomes AT_RISK.
K02 | Owner/backup cannot attend review or rehearsal | High | Book October 16 and October 23 sessions now; use a backup owner. | Project lead | If not booked by Oct 2, protect alternate dates.
K03 | Replacement package changes again after freeze | High | Block optional changes; new identity and affected reruns for any necessary change. | Release owner | Any byte change after Oct 9 triggers scope review.
K04 | Independent testing finds a real defect | High | Use the 2-3 day contingency; fix only the blocker or report a qualified subset. | Release implementer / owner | Do not consume owner-handoff time without reforecasting.
K05 | Podman/NVIDIA/Python prerequisites fail on the independent host | High | Inventory before freeze; prepare approved Python 3.12 and CDI prerequisites; never convert failure to pass. | Test owner | Missing prerequisites remain explicit blockers.
K06 | External Setup Guide/video access is unavailable | Medium | Confirm owner-controlled destination and editing/hosting permissions during Week 1. | Documentation owner | Written guide remains complete even if video link is delayed.
K07 | Sensitive content is found late | High | Start scoped inventory/scan now; keep findings private and rotate actual credentials through owners. | Security reviewer | A substantial incident displaces optional work and changes forecast.
K08 | cdcai adoption approval or permissions arrive late | High | Prepare the migration-ready packet in parallel and use the no-adoption fallback. | cdcai owner / project lead | Never treat the deadline as authorization.
K09 | October 12 is a non-working holiday for participants | Medium | Confirm calendar now; plan has 22 weekdays excluding weekends but only 21 if Oct 12 is unavailable. | Project lead | Use overlap and protected contingency, not reduced acceptance.
K10 | Optional backlog work consumes closeout capacity | High | Do not start conditional/deferred tasks unless they become direct release blockers. | Project lead / maintainer | Filter the backlog by Recommendation before selecting work.

## Source Mapping
Planning Source Mapping
This plan is a first-draft synthesis. Current task status and acceptance continue to come from the listed repository sources.
Role | Source | How it was used
Current board | .agent_work/current-tasks.md | Controls task status and immediate work.
Acceptance | .agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-prioritization-v2.md | Controls supported outcome as amended by ADR-022/023.
Work plan | .agent_work/context/status/Reprioritization Effort/2026-09-21-windows-deployment-hardening-v2.md | Controls W00-W10 sequence; raw checkboxes need current evidence crosswalk.
Closeout guide | .agent_work/context/status/Reprioritization Effort/2026-09-21-post-day-7-backlog-and-handoff-guide.md | Supplies October documentation, media, sanitization, backlog, owner-guide, and rehearsal work.
Unsigned decision | .agent_work/decisions/023-unsigned-windows-package-support-boundary.md | Removes signing as a standard gate and adds browser-download/hash proof.
ML decision | .agent_work/decisions/022-cuda128-blackwell-ml-runtime.md | Controls CPU/cuda128 identities and device/runtime evidence.
Release qualification | .agent_work/tasks/active/TASK-091-owner-runnable-release-qualification.md | Owns downloadable owner-reproducible acceptance.
Documentation | .agent_work/tasks/active/TASK-092-documentation-currentness.md | Owns repository/package/external user information.
Recovery | .agent_work/tasks/active/TASK-093-persistent-data-recovery.md | Owns data persistence and independent recovery.
Governance/handoff | .agent_work/tasks/active/TASK-095-governance-ai-ready-handoff.md | Owns Phase B owner transfer and closeout.
Podman | .agent_work/tasks/active/TASK-097-podman-final-path-qualification.md | Owns independent Podman CPU/GPU and Python prerequisite proof.
ML/package evidence | .agent_work/tasks/active/TASK-103-cuda128-blackwell-ml-runtime.md | Owns replacement package/browser/independent-host open gates.
Adoption | .agent_work/tasks/active/TASK-089-cdcai-migration-execution.md | Owns owner-gated cdcai transfer or migration-ready fallback.
Pilot hold | .agent_work/context/status/Handoff-Planning/PILOT-FEEDBACK-AND-CDC-AI-ADOPTION-PLAN.md | Keeps v0.1.2 immutable and cdcai unchanged until approval.